## RFA_All Discipline
REVIEWS | [14 empty] | REVIEWED DOCUMENTS | [6 empty] | DETAILS
Status | ID | Review name | Workflow | Initiated by | Next action by | Next action due | Created on | Finished on | Total documents | Approved | Rejected | Progress | Current step | Total steps | Document name | Path | Description | Version | Markup | Review status | Action upon completion | Comments | Related attribute actions
OPEN | 4115 | 522803-01-RFAM-HY-0037-01_Quick fill for Hydraulics system | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Pakpin Meepradit, Ronnakon Vutthanunt, Chamrat Jouicepeam, Jakkapan Pannarapong, Mawin Ninkhet | Oct 11, 2024 | Oct 8, 2024 8:15 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFAM-HY-0037-001_Quick fill for Hydraulics system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0037-001_Quick fill for Hydraulics system |  | V1 | 0 |  | --
OPEN | 4114 | 522803-01-RFAM-EL-0077-001_Galvanized Flexible | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, NXT-AUR-EL-Designer, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan, Alain Bernardo Perez | Oct 11, 2024 | Oct 8, 2024 8:13 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFAM-EL-0077-001_Galvanized Flexible.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0077-001_Galvanized Flexible |  | V1 | 0 |  | --
OPEN | 4113 | 522803-01-RFAM-EL-0071-001_ID Lighting | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, NXT-AUR-EL-Designer, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan, Alain Bernardo Perez | Oct 11, 2024 | Oct 8, 2024 8:13 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFAM-EL-0071-001_ID Lighting.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0071-001_ID Lighting |  | V1 | 0 |  | --
OPEN | 4064 | 522803-01-RFAM-EL-0024-003_Public Address System | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan | Oct 9, 2024 | Oct 4, 2024 11:07 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFAM-EL-0024-003_Public Address System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0024-003_Public Address System |  | V1 | 0 |  | --
OPEN | 4062 | 522803-01-RFA-EL-0003-002_ECMS GUI | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan | Oct 9, 2024 | Oct 4, 2024 10:54 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0003-002_ECMS GUI.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0003-002_ECMS GUI |  | V1 | 0 |  | --
OPEN | 4043 | 522803-01-RFA-EL-0045-001_Electrical Arc Flash Study | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan | Oct 8, 2024 | Oct 3, 2024 9:52 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0045-001_Electrical Arc Flash Study.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0045-001_Electrical Arc Flash Study |  | V1 | 0 |  | --
OPEN | 4042 | 522803-01-RFA-EL-0044-001_Electrical Load Flow Study | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Montchai Itisurasing, Kumnod Kongsap, Chamrat Jouicepeam, Jakkapan Pannarapong, Kiattisak Thongoon, Thamrongsak Jantharak, Mawin Ninkhet, Poonnapa Ngautragoon, Trilak Sirisangchai, Nalatthawan Suttipan | Oct 8, 2024 | Oct 3, 2024 9:52 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0044-001_Electrical Load Flow Study.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0044-001_Electrical Load Flow Study |  | V1 | 0 |  | --
OPEN | 4041 | 522803-01-RPT-ST-0029-002_Report of dynamic load test | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 3, 2024 9:26 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RPT-ST-0029-002_Report of dynamic load test.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0029-002_Report of dynamic load test |  | V1 | 0 |  | --
OPEN | 4023 | 522803-01-RFA-EL-0043-001_JSA CxL3 UG Storage Tanks (Fuel Filling) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:41 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0043-001_JSA CxL3 UG Storage Tanks (Fuel Filling).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0043-001_JSA CxL3 UG Storage Tanks (Fuel Filling) |  | V1 | 0 |  | --
OPEN | 4022 | 522803-01-RFA-EL-0041-001_JSA CxL3 Procedure Energization | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:41 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0041-001_JSA CxL3 Procedure Energization.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0041-001_JSA CxL3 Procedure Energization |  | V1 | 0 |  | --
OPEN | 4021 | 522803-01-RFA-EL-0038-001_JSA CxL3 Socket Outlet | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:40 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0038-001_JSA CxL3 Socket Outlet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0038-001_JSA CxL3 Socket Outlet |  | V1 | 0 |  | --
OPEN | 4020 | 522803-01-RFA-EL-0037-001_JSA CxL3 PAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:38 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0037-001_JSA CxL3 PAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0037-001_JSA CxL3 PAS |  | V1 | 0 |  | --
OPEN | 4019 | 522803-01-RFA-EL-0036-001_JSA CxL3 ADS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:37 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0036-001_JSA CxL3 ADS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0036-001_JSA CxL3 ADS |  | V1 | 0 |  | --
OPEN | 4018 | 522803-01-RFA-EL-0035-001_JSA CxL3 FAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:37 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0035-001_JSA CxL3 FAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0035-001_JSA CxL3 FAS |  | V1 | 0 |  | --
OPEN | 4017 | 522803-01-RFA-EL-0034-001_JSA CxL3 Emergency_Exit Light | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:36 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0034-001_JSA CxL3 Emergency_Exit Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0034-001_JSA CxL3 Emergency_Exit Light |  | V1 | 0 |  | --
OPEN | 4016 | 522803-01-RFA-EL-0033-001_JSA CxL3 Lighting System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:35 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0033-001_JSA CxL3 Lighting System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0033-001_JSA CxL3 Lighting System |  | V1 | 0 |  | --
OPEN | 4015 | 522803-01-RFA-EL-0032-001_JSA CxL3 Busway (Data Hall) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:35 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0032-001_JSA CxL3 Busway (Data Hall).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0032-001_JSA CxL3 Busway (Data Hall) |  | V1 | 0 |  | --
OPEN | 4014 | 522803-01-RFA-EL-0031-001_JSA CxL3 Busduct | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:35 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0031-001_JSA CxL3 Busduct.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0031-001_JSA CxL3 Busduct |  | V1 | 0 |  | --
OPEN | 4013 | 522803-01-RFA-EL-0030-001_JSA CxL3 Load Bank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:32 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0030-001_JSA CxL3 Load Bank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0030-001_JSA CxL3 Load Bank |  | V1 | 0 |  | --
OPEN | 4012 | 522803-01-RFA-EL-0029-001_JSA CxL3 ECMS Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:32 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0029-001_JSA CxL3 ECMS Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0029-001_JSA CxL3 ECMS Panel |  | V1 | 0 |  | --
OPEN | 4011 | 522803-01-RFA-EL-0028-001_JSA CxL3 BTU Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:32 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0028-001_JSA CxL3 BTU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0028-001_JSA CxL3 BTU Panel |  | V1 | 0 |  | --
OPEN | 4010 | 522803-01-RFA-EL-0027-001_JSA CxL3 PDU Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:32 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0027-001_JSA CxL3 PDU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0027-001_JSA CxL3 PDU Panel |  | V1 | 0 |  | --
OPEN | 4009 | 522803-01-RFA-EL-0026-001_JSA CxL3 ATS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:31 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0026-001_JSA CxL3 ATS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0026-001_JSA CxL3 ATS |  | V1 | 0 |  | --
OPEN | 4008 | 522803-01-RFA-EL-0025-001_JSA CxL3 LV Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:31 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0025-001_JSA CxL3 LV Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0025-001_JSA CxL3 LV Panel |  | V1 | 0 |  | --
OPEN | 4007 | 522803-01-RFA-EL-0024-001_JSA CxL3 LVSG | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 8, 2024 | Oct 2, 2024 3:31 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-EL-0024-001_JSA CxL3 LVSG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0024-001_JSA CxL3 LVSG |  | V1 | 0 |  | --
OPEN | 4003 | 522803-01-RFAM-SE-0027-001_EACAS Cable | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Asher Katz, Chamrat Jouicepeam, Jakkapan Pannarapong, Thamrongsak Jantharak, Mawin Ninkhet, Sarah Ali, Gus German | Oct 7, 2024 | Oct 2, 2024 2:58 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFAM-SE-0027-001_EACAS Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0027-001_EACAS Cable |  | V1 | 0 |  | --
OPEN | 4002 | 522803-01-RFAM-ME-0010-004_MV Fan | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | GSA, Sygna, NXT-AUR-DocControl | Oct 10, 2024 | Oct 2, 2024 11:21 AM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-RFAM-ME-0010-004_MV Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0010-004_MV Fan |  | V1 | 1 |  | -- | Kloer Chongchaikit(Oct 8, 2024 12:11 AM): ME comment in attached file.
OPEN | 4001 | 522803-01-RFAM-HY-0011-002_Continuous Water Level Measurement | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | GSA, Sygna, NXT-AUR-DocControl | Oct 10, 2024 | Oct 2, 2024 11:20 AM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-RFAM-HY-0011-002_Continuous Water Level Measurement.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0011-002_Continuous Water Level Measurement |  | V1 | 0 |  | --
OPEN | 3994 | 522803-01-RFA-ME-0028-001_JSA of CxL3 VSD | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0028-001_JSA of CxL3 VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0028-001_JSA of CxL3 VSD |  | V1 | 0 |  | --
OPEN | 3993 | 522803-01-RFA-ME-0027-001_JSA of CxL3 MCP-MCC Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0027-001_JSA of CxL3 MCP-MCC Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0027-001_JSA of CxL3 MCP-MCC Panel |  | V1 | 0 |  | --
OPEN | 3992 | 522803-01-RFA-ME-0026-001_JSA of CxL3 CHBT | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0026-001_JSA of CxL3 CHBT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0026-001_JSA of CxL3 CHBT |  | V1 | 0 |  | --
OPEN | 3991 | 522803-01-RFA-ME-0025-001_JSA of CxL3 Space sensor | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0025-001_JSA of CxL3 Space sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0025-001_JSA of CxL3 Space sensor |  | V1 | 0 |  | --
OPEN | 3990 | 522803-01-RFA-ME-0024-001_JSA of CxL3 AC-VRF | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0024-001_JSA of CxL3 AC-VRF.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0024-001_JSA of CxL3 AC-VRF |  | V1 | 0 |  | --
OPEN | 3989 | 522803-01-RFA-ME-0023-001_JSA of CxL3 FCU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0023-001_JSA of CxL3 FCU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0023-001_JSA of CxL3 FCU |  | V1 | 0 |  | --
OPEN | 3988 | 522803-01-RFA-ME-0022-001_JSA of CxL3 EAF | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0022-001_JSA of CxL3 EAF.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0022-001_JSA of CxL3 EAF |  | V1 | 0 |  | --
OPEN | 3987 | 522803-01-RFA-ME-0021-001_JSA of CxL3 AHU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0021-001_JSA of CxL3 AHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0021-001_JSA of CxL3 AHU |  | V1 | 0 |  | --
OPEN | 3986 | 522803-01-RFA-ME-0020-001_JSA of CxL3 PAHU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0020-001_JSA of CxL3 PAHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0020-001_JSA of CxL3 PAHU |  | V1 | 0 |  | --
OPEN | 3985 | 522803-01-RFA-ME-0019-001_JSA of CxL3 Duct work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:38 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0019-001_JSA of CxL3 Duct work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0019-001_JSA of CxL3 Duct work |  | V1 | 0 |  | --
OPEN | 3984 | 522803-01-RFA-ME-0018-001_JSA of CxL3 CDWP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:38 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0018-001_JSA of CxL3 CDWP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0018-001_JSA of CxL3 CDWP |  | V1 | 0 |  | --
OPEN | 3983 | 522803-01-RFA-ME-0017-001_JSA of CxL3 CHWP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:38 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0017-001_JSA of CxL3 CHWP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0017-001_JSA of CxL3 CHWP |  | V1 | 0 |  | --
OPEN | 3982 | 522803-01-RFA-ME-0016-001_JSA of CxL3 CHW,CDW Pipe Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:38 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0016-001_JSA of CxL3 CHW,CDW Pipe Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0016-001_JSA of CxL3 CHW,CDW Pipe Work |  | V1 | 0 |  | --
OPEN | 3981 | 522803-01-RFA-HY-0022-001_JSA of CxL3 Fuel pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:27 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-HY-0022-001_JSA of CxL3 Fuel pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0022-001_JSA of CxL3 Fuel pump |  | V1 | 0 |  | --
OPEN | 3980 | 522803-01-RFA-HY-0026-001_JSA of CxL3 Fuel Control Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 10:18 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-HY-0026-001_JSA of CxL3 Fuel Control Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0026-001_JSA of CxL3 Fuel Control Panel |  | V2 | 0 |  | --
OPEN | 3978 | 522803-01-RFA-HY-0025-001_JSA of CxL3 Fuel Tank Monitoring Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 9:46 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-HY-0025-001_JSA of CxL3 Fuel Tank Monitoring Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0025-001_JSA of CxL3 Fuel Tank Monitoring Panel |  | V1 | 0 |  | --
OPEN | 3977 | 522803-01-RFA-HY-0024-001_JSA of CxL3 Fuel Polishing | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 9:46 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-HY-0024-001_JSA of CxL3 Fuel Polishing.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0024-001_JSA of CxL3 Fuel Polishing |  | V1 | 0 |  | --
OPEN | 3976 | 522803-01-RFA-HY-0023-001_JSA of CxL3 Fuel leak detector | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 7, 2024 | Oct 1, 2024 9:41 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-HY-0023-001_JSA of CxL3 Fuel leak detector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0023-001_JSA of CxL3 Fuel leak detector |  | V1 | 0 |  | --
OPEN | 3962 | 522803-01-RFA-SE-0016-001_JSA for CxL3 PIDS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 30, 2024 2:11 PM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0016-001_JSA for CxL3 PIDS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0016-001_JSA for CxL3 PIDS |  | V1 | 0 |  | --
OPEN | 3948 | 522803-01-RFA-SE-0018-001_JSA for CxL3 VWS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:41 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0018-001_JSA for CxL3 VWS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0018-001_JSA for CxL3 VWS |  | V1 | 0 |  | --
OPEN | 3947 | 522803-01-RFA-SE-0017-001_JSA for CxL3 UVSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:41 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0017-001_JSA for CxL3 UVSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0017-001_JSA for CxL3 UVSS |  | V1 | 0 |  | --
OPEN | 3946 | 522803-01-RFA-SE-0015-001_JSA for CxL3 EKMS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0015-001_JSA for CxL3 EKMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0015-001_JSA for CxL3 EKMS |  | V1 | 0 |  | --
OPEN | 3945 | 522803-01-RFA-SE-0014-001_JSA for CxL3 INTERCOM | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:40 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0014-001_JSA for CxL3 INTERCOM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0014-001_JSA for CxL3 INTERCOM |  | V1 | 0 |  | --
OPEN | 3944 | 522803-01-RFA-SE-0013-001_JSA for CxL3 ISMS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0013-001_JSA for CxL3 ISMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0013-001_JSA for CxL3 ISMS |  | V1 | 0 |  | --
OPEN | 3943 | 522803-01-RFA-SE-0012-001_JSA for CxL3 VSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0012-001_JSA for CxL3 VSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0012-001_JSA for CxL3 VSS |  | V1 | 0 |  | --
OPEN | 3942 | 522803-01-RFA-SE-0011-001_JSA for CxL3 EACAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 28, 2024 8:39 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-SE-0011-001_JSA for CxL3 EACAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0011-001_JSA for CxL3 EACAS |  | V1 | 0 |  | --
OPEN | 3916 | 522803-01-RFA-ME-0015-001_JSA of CxL2 VSD | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:34 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0015-001_JSA of CxL2 VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0015-001_JSA of CxL2 VSD |  | V1 | 0 |  | --
OPEN | 3915 | 522803-01-RFA-ME-0014-001_JSA of CxL2 MCP-MCC Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:34 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0014-001_JSA of CxL2 MCP-MCC Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0014-001_JSA of CxL2 MCP-MCC Panel |  | V1 | 0 |  | --
OPEN | 3914 | 522803-01-RFA-ME-0013-001_JSA of CxL2 CHBT | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:33 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0013-001_JSA of CxL2 CHBT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0013-001_JSA of CxL2 CHBT |  | V1 | 0 |  | --
OPEN | 3913 | 522803-01-RFA-ME-0012-001_JSA of CxL2 AC Drain piping | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:33 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0012-001_JSA of CxL2 AC Drain piping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0012-001_JSA of CxL2 AC Drain piping |  | V1 | 0 |  | --
OPEN | 3912 | 522803-01-RFA-ME-0011-001_JSA of CxL2 Refrigerant Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:33 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0011-001_JSA of CxL2 Refrigerant Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0011-001_JSA of CxL2 Refrigerant Pipe |  | V1 | 0 |  | --
OPEN | 3911 | 522803-01-RFA-ME-0010-001_JSA of CxL2 Space sensor | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:33 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0010-001_JSA of CxL2 Space sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0010-001_JSA of CxL2 Space sensor |  | V1 | 0 |  | --
OPEN | 3910 | 522803-01-RFA-ME-0009-001_JSA of CxL2 AC-VRF | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:29 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0009-001_JSA of CxL2 AC-VRF.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0009-001_JSA of CxL2 AC-VRF |  | V1 | 0 |  | --
OPEN | 3909 | 522803-01-RFA-ME-0008-001_JSA of CxL2 FCU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:28 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0008-001_JSA of CxL2 FCU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0008-001_JSA of CxL2 FCU |  | V1 | 0 |  | --
OPEN | 3908 | 522803-01-RFA-ME-0007-001_JSA of CxL2 EAF | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:28 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0007-001_JSA of CxL2 EAF.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0007-001_JSA of CxL2 EAF |  | V1 | 0 |  | --
OPEN | 3907 | 522803-01-RFA-ME-0006-001_JSA of CxL2 AHU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:28 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0006-001_JSA of CxL2 AHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0006-001_JSA of CxL2 AHU |  | V1 | 0 |  | --
OPEN | 3906 | 522803-01-RFA-ME-0005-001_JSA of CxL2 PAHU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil, Jakkapan Pannarapong, Chatchai Sripradoo, Chamrat Jouicepeam, Kriangsak Sasomchit, Mawin Ninkhet, Nopkhun Samritdee | Oct 3, 2024 | Sep 27, 2024 10:28 AM | -- | 1 | -- | -- | 25.00% | 2 Initial Review 2 | 4 | 522803-01-RFA-ME-0005-001_JSA of CxL2 PAHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0005-001_JSA of CxL2 PAHU |  | V1 | 0 |  | --
OPEN | 3905 | 522803-01-RFA-ME-0004-001_JSA of CxL2 Duct work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | NXT-AUR-DocControl, Thamrongsak Jantharak, Sirapong Suwanpanjasil | Oct 11, 2024 | Sep 27, 2024 10:28 AM | -- | 1 | -- | -- | 50.00% | 3 Initial Review 3 | 4 | 522803-01-RFA-ME-0004-001_JSA of CxL2 Duct work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0004-001_JSA of CxL2 Duct work |  | V1 | 0 |  | --
CLOSED | 3904 | 522803-01-RFA-ME-0003-001_JSA of CxL2 CDWP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 27, 2024 10:27 AM | Oct 9, 2024 1:22 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-ME-0003-001_JSA of CxL2 CDWP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0003-001_JSA of CxL2 CDWP |  | V1 | 0 | Approved | Updated review status
CLOSED | 3903 | 522803-01-RFA-ME-0002-001_JSA of CxL2 CHWP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 27, 2024 10:27 AM | Oct 9, 2024 1:27 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-ME-0002-001_JSA of CxL2 CHWP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1027_RFA-ME_Request for Approval (Mechanical)/522803-01-RFA-ME-0002-001_JSA of CxL2 CHWP |  | V1 | 0 | Approved | Updated review status
CLOSED | 3832 | 522803-01-RFA-HY-0017-001_JSA of CxL2 UG Tanks Calibration | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:14 PM | Oct 9, 2024 1:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0017-001_JSA of CxL2 UG Tanks Calibration.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0017-001_JSA of CxL2 UG Tanks Calibration |  | V1 | 0 | Approved | Updated review status
CLOSED | 3831 | 522803-01-RFA-HY-0021-001_JSA of CxL2 Fuel Control Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:11 PM | Oct 9, 2024 1:28 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0021-001_JSA of CxL2 Fuel Control Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0021-001_JSA of CxL2 Fuel Control Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3830 | 522803-01-RFA-HY-0020-001_JSA of CxL2 Fuel Tank Monitoring Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:10 PM | Oct 9, 2024 1:29 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0020-001_JSA of CxL2 Fuel Tank Monitoring Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0020-001_JSA of CxL2 Fuel Tank Monitoring Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3829 | 522803-01-RFA-HY-0019-001_JSA of CxL2 Fuel Polishing | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:10 PM | Oct 8, 2024 10:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0019-001_JSA of CxL2 Fuel Polishing.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0019-001_JSA of CxL2 Fuel Polishing |  | V1 | 0 | Approved | Updated review status
CLOSED | 3828 | 522803-01-RFA-HY-0018-001_JSA of CxL2 Fuel leak detector | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:10 PM | Oct 8, 2024 10:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0018-001_JSA of CxL2 Fuel leak detector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0018-001_JSA of CxL2 Fuel leak detector |  | V1 | 0 | Approved | Updated review status
CLOSED | 3827 | 522803-01-RFA-HY-0016-001_JSA of CxL2 Fuel piping | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:08 PM | Oct 8, 2024 10:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0016-001_JSA of CxL2 Fuel piping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0016-001_JSA of CxL2 Fuel piping |  | V1 | 0 | Approved | Updated review status
CLOSED | 3826 | 522803-01-RFA-HY-0015-001_JSA of CxL2 Fuel pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:08 PM | Oct 8, 2024 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0015-001_JSA of CxL2 Fuel pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0015-001_JSA of CxL2 Fuel pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3825 | 522803-01-RFA-HY-0014-001_JSA of CxL2 UG Storage Tanks | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 3:08 PM | Oct 8, 2024 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0014-001_JSA of CxL2 UG Storage Tanks.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0014-001_JSA of CxL2 UG Storage Tanks |  | V1 | 0 | Approved | Updated review status
OPEN | 3824 | 522803-01-RFA-MEP-0002-001_LOCK OUT_TAG OUT Procedure (LOTO) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | GSA, NXT-AUR-DocControl | Oct 8, 2024 | Sep 26, 2024 3:05 PM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-RFA-MEP-0002-001_LOCK OUT_TAG OUT Procedure (LOTO).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1021_RFA-XXX_Request for Approval (For exceptional types of discipline)/522803-01-RFA-MEP-0002-001_LOCK OUT_TAG OUT Procedure (LOTO) |  | V1 | 0 |  | --
CLOSED | 3823 | 522803-01-RFA-FP-0008-001_JSA for CxL3 IG-100 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 2:38 PM | Oct 8, 2024 9:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0008-001_JSA for CxL3 IG-100.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0008-001_JSA for CxL3 IG-100 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3822 | 522803-01-RFA-FP-0007-001_JAS for CxL3 Pre-action valve | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 2:35 PM | Oct 8, 2024 9:51 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0007-001_JAS for CxL3 Pre-action valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0007-001_JAS for CxL3 Pre-action valve |  | V1 | 0 | Approved | Updated review status
CLOSED | 3821 | 522803-01-RFA-FP-0006-001_JSA for CxL3 Wet Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 2:35 PM | Oct 8, 2024 9:51 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0006-001_JSA for CxL3 Wet Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0006-001_JSA for CxL3 Wet Pipe |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3820 | 522803-01-RFA-FP-0005-001_JSA for CxL3 Fire Pump and Jockey Pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 2:34 PM | Oct 8, 2024 9:49 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0005-001_JSA for CxL3 Fire Pump and Jockey Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0005-001_JSA for CxL3 Fire Pump and Jockey Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3819 | 522803-01-RFA-FP-0001-001_JSA for CxL2 Fire Pump and Jockey Pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 2:33 PM | Oct 8, 2024 9:45 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0001-001_JSA for CxL2 Fire Pump and Jockey Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0001-001_JSA for CxL2 Fire Pump and Jockey Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3816 | 522803-01-RFA-HY-0013-001_JSA for CxL3 Water Heater | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 1:55 PM | Oct 8, 2024 9:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0013-001_JSA for CxL3 Water Heater.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0013-001_JSA for CxL3 Water Heater |  | V1 | 0 | Approved | Updated review status
CLOSED | 3815 | 522803-01-RFA-HY-0012-001_JSA for CxL3 WWTP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 1:55 PM | Oct 8, 2024 9:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0012-001_JSA for CxL3 WWTP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0012-001_JSA for CxL3 WWTP |  | V1 | 0 | Approved | Updated review status
CLOSED | 3814 | 522803-01-RFA-HY-0011-001_JSA for CxL3 Sanitary Wares | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 1:55 PM | Oct 8, 2024 9:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0011-001_JSA for CxL3 Sanitary Wares.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0011-001_JSA for CxL3 Sanitary Wares |  | V1 | 0 | Approved | Updated review status
CLOSED | 3813 | 522803-01-RFA-HY-0010-001_JSA for CxL3 Water Filtration | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 1:54 PM | Oct 8, 2024 9:55 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0010-001_JSA for CxL3 Water Filtration.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0010-001_JSA for CxL3 Water Filtration |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3812 | 522803-01-RFA-HY-0009-001_JSA for CxL3 Submersible Pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 26, 2024 1:54 PM | Oct 8, 2024 9:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0009-001_JSA for CxL3 Submersible Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0009-001_JSA for CxL3 Submersible Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3792 | 522803-01-RFA-EL-0011-001_JSA CxL2 Busduct | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 25, 2024 3:11 PM | Oct 8, 2024 9:34 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0011-001_JSA CxL2 Busduct.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0011-001_JSA CxL2 Busduct |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3782 | 522803-01-RFA-EL-0019-001_JSA CxL2 PAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 3:49 PM | Oct 8, 2024 9:43 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0019-001_JSA CxL2 PAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0019-001_JSA CxL2 PAS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3780 | 522803-01-RPT-LE-0012-001_Monthly Report for LEED No.12 for September 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Sep 24, 2024 2:15 PM | Oct 7, 2024 8:36 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0012-001_Monthly Report for LEED No.12 for September 2024.pdf.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0012-001_Monthly Report for LEED No.12 for September 2024.pdf |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3779 | 522803-01-RFA-EL-0023-001_JSA CxL2 Emergency_Exit Light | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:38 PM | Oct 8, 2024 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0023-001_JSA CxL2 Emergency_Exit Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0023-001_JSA CxL2 Emergency_Exit Light |  | V1 | 0 | Approved | Updated review status
CLOSED | 3778 | 522803-01-RFA-EL-0020-001_JSA CxL2 Lighting System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:37 PM | Oct 8, 2024 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0020-001_JSA CxL2 Lighting System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0020-001_JSA CxL2 Lighting System |  | V1 | 0 | Approved | Updated review status
CLOSED | 3777 | 522803-01-RFA-EL-0018-001_JSA CxL2 FAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:36 PM | Oct 8, 2024 9:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0018-001_JSA CxL2 FAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0018-001_JSA CxL2 FAS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3776 | 522803-01-RFA-EL-0017-001_JSA CxL2 ADS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:36 PM | Oct 8, 2024 9:36 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0017-001_JSA CxL2 ADS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0017-001_JSA CxL2 ADS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3775 | 522803-01-RFA-EL-0016-001_JSA CxL2 LAN Cable_FOC | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:35 PM | Oct 8, 2024 9:36 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0016-001_JSA CxL2 LAN Cable_FOC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0016-001_JSA CxL2 LAN Cable_FOC |  | V1 | 0 | Approved | Updated review status
CLOSED | 3774 | 522803-01-RFA-EL-0015-001_JSA CxL2 LV Cable | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:35 PM | Oct 8, 2024 9:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0015-001_JSA CxL2 LV Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0015-001_JSA CxL2 LV Cable |  | V1 | 0 | Approved | Updated review status
CLOSED | 3773 | 522803-01-RFA-EL-0014-001_JSA CxL2 MV Cable | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:35 PM | Oct 8, 2024 9:34 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0014-001_JSA CxL2 MV Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0014-001_JSA CxL2 MV Cable |  | V1 | 0 | Approved | Updated review status
CLOSED | 3772 | 522803-01-RFA-EL-0013-001_JSA CxL2 Grounding_LTNG | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:35 PM | Oct 5, 2024 1:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0013-001_JSA CxL2 Grounding_LTNG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0013-001_JSA CxL2 Grounding_LTNG |  | V1 | 0 | Approved | Updated review status
CLOSED | 3771 | 522803-01-RFA-EL-0012-001_JSA CxL2 Busway (Data Hall) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:34 PM | Oct 5, 2024 12:51 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0012-001_JSA CxL2 Busway (Data Hall).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0012-001_JSA CxL2 Busway (Data Hall) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3770 | 522803-01-RFA-EL-0010-001_JSA CxL2 Load Bank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:34 PM | Oct 5, 2024 12:51 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0010-001_JSA CxL2 Load Bank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0010-001_JSA CxL2 Load Bank |  | V1 | 0 | Approved | Updated review status
CLOSED | 3769 | 522803-01-RFA-EL-0009-001_JSA CxL2 ECMS Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:34 PM | Oct 5, 2024 12:52 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0009-001_JSA CxL2 ECMS Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0009-001_JSA CxL2 ECMS Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3768 | 522803-01-RFA-EL-0008-001_JSA CxL2 BTU Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:33 PM | Oct 5, 2024 12:45 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0008-001_JSA CxL2 BTU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0008-001_JSA CxL2 BTU Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3767 | 522803-01-RFA-EL-0007-001_JSA CxL2 PDU Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:33 PM | Oct 5, 2024 12:43 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0007-001_JSA CxL2 PDU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0007-001_JSA CxL2 PDU Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3766 | 522803-01-RFA-EL-0006-001_JSA CxL2 ATS Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:33 PM | Oct 5, 2024 12:29 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0006-001_JSA CxL2 ATS Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0006-001_JSA CxL2 ATS Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3765 | 522803-01-RFA-EL-0005-001_JSA CxL2 LV Panel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 24, 2024 1:33 PM | Oct 5, 2024 12:22 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0005-001_JSA CxL2 LV Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0005-001_JSA CxL2 LV Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 3757 | 522803-01-RFA-SE-0010-001_JSA for CxL2 VWS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:36 PM | Oct 5, 2024 12:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0010-001_JSA for CxL2 VWS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0010-001_JSA for CxL2 VWS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3756 | 522803-01-RFA-SE-0009-001_JSA for CxL2 UVSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:36 PM | Oct 5, 2024 12:02 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0009-001_JSA for CxL2 UVSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0009-001_JSA for CxL2 UVSS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3755 | 522803-01-RFA-SE-0008-001_JSA for CxL2 PIDS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:35 PM | Oct 5, 2024 11:59 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0008-001_JSA for CxL2 PIDS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0008-001_JSA for CxL2 PIDS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3754 | 522803-01-RFA-SE-0007-001_JSA for CxL2 EKMS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:35 PM | Oct 5, 2024 11:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0007-001_JSA for CxL2 EKMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0007-001_JSA for CxL2 EKMS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3753 | 522803-01-RFA-SE-0006-001_JSA for CxL2 INTERCOM | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:35 PM | Oct 2, 2024 4:41 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0006-001_JSA for CxL2 INTERCOM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0006-001_JSA for CxL2 INTERCOM |  | V1 | 0 | Approved | Updated review status
CLOSED | 3752 | 522803-01-RFA-SE-0005-001_JSA for CxL2 ISMS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:35 PM | Oct 2, 2024 4:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0005-001_JSA for CxL2 ISMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0005-001_JSA for CxL2 ISMS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3751 | 522803-01-RFA-SE-0004-001_JSA for CxL2 VSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:35 PM | Oct 2, 2024 4:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0004-001_JSA for CxL2 VSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0004-001_JSA for CxL2 VSS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3750 | 522803-01-RFA-SE-0003-001_JSA for CxL2 EACAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 5:34 PM | Oct 2, 2024 4:35 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0003-001_JSA for CxL2 EACAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0003-001_JSA for CxL2 EACAS |  | V1 | 0 | Approved | Updated review status
CLOSED | 3748 | 522803-01-RFA-HY-0008-001_JSA for CxL Soil Water and Wastewater Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:24 PM | Oct 2, 2024 4:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0008-001_JSA for CxL2 Soil Water and Wastewater Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0008-001_JSA for CxL2 Soil Water and Wastewater Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 3747 | 522803-01-RFA-HY-0007-001_JSA for Water Heater | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:24 PM | Oct 2, 2024 4:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0007-001_JSA for CxL2 Water Heater.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0007-001_JSA for CxL2 Water Heater |  | V1 | 0 | Approved | Updated review status
CLOSED | 3746 | 522803-01-RFA-HY-0006-001_JSA for CxL2 WWTP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:23 PM | Oct 2, 2024 4:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0006-001_JSA for CxL2 WWTP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0006-001_JSA for CxL2 WWTP |  | V1 | 0 | Approved | Updated review status
CLOSED | 3745 | 522803-01-RFA-HY-0005-001_JSA for CxL2 Sanitary Wares | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:23 PM | Oct 2, 2024 4:17 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0005-001_JSA for CxL2 Sanitary Wares.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0005-001_JSA for CxL2 Sanitary Wares |  | V1 | 0 | Approved | Updated review status
CLOSED | 3744 | 522803-01-RFA-HY-0004-001_JSA for CxL2 Water Filtration | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:23 PM | Oct 2, 2024 4:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0004-001_JSA for CxL2 Water Filtration.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0004-001_JSA for CxL2 Water Filtration |  | V1 | 0 | Approved | Updated review status
CLOSED | 3743 | 522803-01-RFA-HY-0003-001_JSA for CxL2 Submersible Pump | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:23 PM | Oct 2, 2024 4:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0003-001_JSA for CxL2 Submersible Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0003-001_JSA for CxL2 Submersible Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3742 | 522803-01-RFA-FP-0004-001_JSA for IG-100 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:21 PM | Oct 2, 2024 4:09 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0004-001_JSA for CxL2 IG-100.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0004-001_JSA for CxL2 IG-100 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3741 | 522803-01-RFA-FP-0003-001_JAS for CxL2 Pre-action valve | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:20 PM | Oct 5, 2024 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0003-001_JAS for CxL2 Pre-action valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0003-001_JAS for CxL2 Pre-action valve |  | V1 | 0 | Approved | Updated review status
CLOSED | 3740 | 522803-01-RFA-FP-0002-001_JSA for CxL 2 Wet Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 23, 2024 4:20 PM | Oct 2, 2024 4:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-FP-0002-001_JSA for CxL2 Wet Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1029_RFA-FP_Request for Approval (Fire Protection)/522803-01-RFA-FP-0002-001_JSA for CxL2 Wet Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 3736 | 522803-01-MS-ST-0008-001_MS for Façade steel structure | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Sep 23, 2024 2:10 PM | Sep 30, 2024 9:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ST-0008-001_MS for Façade steel structure.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0008-001_MS for Façade steel structure |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 3727 | 522803-01-RFA-EL-0004-001_JSA CxL2 LVSG | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Sep 20, 2024 2:50 PM | Oct 2, 2024 4:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0004-001_JSA CxL2 LVSG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0004-001_JSA CxL2 LVSG |  | V1 | 0 | Make correction as noted & proceed | Updated review status
OPEN | 3652 | 522803-01-RFAM-SE-0026-001_VSS Cabinet Outdoor | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | GSA, Sygna, NXT-AUR-DocControl | Sep 25, 2024 | Sep 16, 2024 4:34 PM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-RFAM-SE-0026-001_VSS Cabinet Outdoor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0026-001_VSS Cabinet Outdoor |  | V1 | 0 |  | --
OPEN | 3651 | 522803-01-RFAM-SE-0025-001_PIDS Cabinet Outdoor | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | GSA, Sygna, NXT-AUR-DocControl | Sep 24, 2024 | Sep 16, 2024 4:34 PM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-RFAM-SE-0025-001_PIDS Cabinet Outdoor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0025-001_PIDS Cabinet Outdoor |  | V1 | 0 |  | --
CLOSED | 3593 | 522803-01-RFAM-ME-0058-001_FOC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Sep 13, 2024 1:25 PM | Sep 23, 2024 5:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0058-001_FOC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0058-001_FOC |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Sep 16, 2024 3:34 PM): ME comment in attached file.
CLOSED | 3591 | 522803-01-RFAM-FP-0019-001_Hand Pump | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Sep 13, 2024 10:36 AM | Oct 9, 2024 3:04 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0019-001_Hand Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0019-001_Hand Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 3588 | 522803-01-RFAM-EL-0053-002_Data Hall Busway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Sep 13, 2024 9:03 AM | Oct 7, 2024 1:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0053-002_Data Hall Busway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0053-002_Data Hall Busway |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Oct 7, 2024 1:05 PM): -Please resubmit PAS600+ PM5350 optional in next revision -Please confirm Model, rating and quantity before order the material
CLOSED | 3587 | 522803-01-RFAM-EL-0045-003_Busway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Sep 13, 2024 9:02 AM | Oct 9, 2024 1:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0045-003_Busway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0045-003_Busway |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3579 | 522803-01-RFA-EL-0003-001_ECMS GUI | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Sep 12, 2024 2:29 PM | Oct 3, 2024 10:16 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-EL-0003-001_ECMS GUI.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0003-001_ECMS GUI |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 3525 | 522803-01-RFA-HY-0002-002_FMS GUI | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Sep 11, 2024 1:43 PM | Oct 7, 2024 7:59 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-HY-0002-002_FMS GUI.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0002-002_FMS GUI |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
OPEN | 3520 | 522803-01-MRPT-GEN-0011-001_TTI Monthly Progress Report_Aug 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | GSA, NXT-AUR-DocControl | Oct 1, 2024 | Sep 10, 2024 5:45 PM | -- | 1 | -- | -- | 75.00% | 4 Final Review | 4 | 522803-01-MRPT-GEN-0011-001_TTI Monthly Progress Report_Aug 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0011-001_TTI Monthly Progress Report_Aug 2024 |  | V1 | 0 |  | --
CLOSED | 3518 | 522803-01-RFAM-FP-0006-002_Sprinkler head | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Sep 10, 2024 2:56 PM | Sep 23, 2024 5:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0006-002_Sprinkler head.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0006-002_Sprinkler head |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3453 | 522803-01-RFAM-SE-0011-003_LPR | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Sep 6, 2024 5:51 PM | Sep 24, 2024 1:48 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0011-003_LPR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0011-003_LPR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3367 | 522803-01-RPT-HSE-0010-001_Result of environmental monitoring_No.10 (16 Jul-15 Aug 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Sep 4, 2024 3:16 PM | Oct 8, 2024 10:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0010-001_Result of environmental monitoring_No.10 (16 Jul-15 Aug 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0010-001_Result of environmental monitoring_No.10 (16 Jul-15 Aug 24) |  | V1 | 0 | Approved | Updated review status
CLOSED | 3318 | 522803-01-RFAM-HY-0011-001_Continuous Water Level Measurement | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Sep 2, 2024 4:22 PM | Sep 18, 2024 10:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0011-001_Continuous Water Level Measurement.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0011-001_Continuous Water Level Measurement |  | V1 | 0 | Approved | Updated review status
CLOSED | 3165 | 522803-01-RFAM-SE-0021-001_Security Workstation | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Aug 27, 2024 5:34 PM | Sep 6, 2024 3:17 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0021-001_Security Workstation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0021-001_Security Workstation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3164 | 522803-01-RFAM-SE-0020-001_Enrollment Station | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Aug 27, 2024 5:34 PM | Sep 6, 2024 1:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0020-001_Enrollment Station.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0020-001_Enrollment Station |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3051 | 522803-01-RFAM-SE-0016-002_UTP Cable | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Aug 24, 2024 1:04 PM | Sep 6, 2024 2:47 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0016-002_UTP Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0016-002_UTP Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3047 | 522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 24, 2024 11:04 AM | Oct 4, 2024 6:28 PM | 4 | 4 | 0 | 100% | Review closed | 4 | 522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3047 | 522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 24, 2024 11:04 AM | Oct 4, 2024 6:28 PM | 4 | 4 | 0 | 100% | Review closed | 4 | 20240823_TTI NEXT01 Master Schedule Rev.03-20240823 for submit RFA.mpp | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3047 | 522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 24, 2024 11:04 AM | Oct 4, 2024 6:28 PM | 4 | 4 | 0 | 100% | Review closed | 4 | 20240823_TTI NEXT01 Master Schedule Rev.03-20240823 for submit RFA_Detail.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3047 | 522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 24, 2024 11:04 AM | Oct 4, 2024 6:28 PM | 4 | 4 | 0 | 100% | Review closed | 4 | 20240823_TTI NEXT01 Master Schedule Rev.03-20240823 for submit RFA_Summary.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-003_Master Schedule_Rev.03 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3035 | 522803-01-RFA-HSE-0004-002_SAFETY REWARD AND SAFETY CAMPAIGN | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 23, 2024 3:42 PM | Sep 17, 2024 3:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0004-002_SAFETY REWARD AND SAFETY CAMPAIGN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0004-002_SAFETY REWARD AND SAFETY CAMPAIGN |  | V1 | 0 | Approved | Updated review status
CLOSED | 3006 | 522803-01-RPT-LE-0011-001_Monthly Report for LEED No.11 for August 2024.pdf | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 22, 2024 2:39 PM | Aug 30, 2024 12:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0011-001_Monthly Report for LEED No.11 for August 2024.pdf.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0011-001_Monthly Report for LEED No.11 for August 2024.pdf |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 3005 | 522803-01-CAL-ST-0019-002_Cal for expansion bolt for installing PC wall at Core wall area | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 22, 2024 1:37 PM | Sep 9, 2024 11:02 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0019-002_Cal for expansion bolt for installing PC wall at Core wall area.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0019-002_Cal for expansion bolt for installing PC wall at Core wall area |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2925 | 522803-01-RFAS-MEP-0001-003_MEP SD Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Aug 19, 2024 4:04 PM | Sep 9, 2024 2:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-MEP-0001-003_MEP SD Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1144_RFAS-MEP_Request for Approval Shop Drawings (Mechanical Electrical and Plumbing)/522803-01-RFAS-MEP-0001-003_MEP SD Schedule |  | V2 | 0 | Approved | Updated review status
CLOSED | 2923 | 522803-01-RPT-AR-0002-001_Testing resulted Floor Flatness and Floor Levelness (FM2) at 2nd fl of Data Hall | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 19, 2024 2:48 PM | Sep 9, 2024 8:38 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-AR-0002-001_Testing resulted Floor Flatness and Floor Levelness (FM2) at 2nd fl of Data Hall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1465_RPT-AR_Request for Approval Report (Architecture)/522803-01-RPT-AR-0002-001_Testing resulted Floor Flatness and Floor Levelness (FM2) at 2nd fl of Data Hall |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2917 | 522803-01-RFAM-ME-0029-006_MCP_MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 19, 2024 7:29 AM | Aug 30, 2024 6:24 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-006_MCP_MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-006_MCP_MCC |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Aug 26, 2024 4:39 PM): ME and EE comment in attached file V2.
CLOSED | 2904 | 522803-01-RFAM-EL-0073-002_Cable Lug | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 16, 2024 11:39 AM | Sep 3, 2024 3:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0073-002_Cable Lug.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0073-002_Cable Lug |  | V1 | 0 | Approved | Updated review status
CLOSED | 2903 | 522803-01-RPT-HSE-0009-001_Result of environmental monitoring No.9 (16 Jun-15 Jul 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 16, 2024 11:35 AM | Sep 24, 2024 10:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0009-001_Result of environmental monitoring No.9 (16 Jun-15 Jul 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0009-001_Result of environmental monitoring No.9 (16 Jun-15 Jul 24) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2902 | 522803-01-RPT-HSE-0008-001_Result of environmental monitoring No.8 (16 May-15 Jun 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 16, 2024 11:35 AM | Sep 24, 2024 10:16 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0008-001_Result of environmental monitoring No.8 (16 May-15 Jun 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0008-001_Result of environmental monitoring No.8 (16 May-15 Jun 24) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2901 | 522803-01-RPT-HSE-0007-001_Result of environmental monitoring No.7 (16 Apr-15 May 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 16, 2024 11:34 AM | Aug 26, 2024 10:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0007-001_Result of environmental monitoring No.7 (16 Apr-15 May 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0007-001_Result of environmental monitoring No.7 (16 Apr-15 May 24) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2900 | 522803-01-RPT-HSE-0006-001_Result of environmental monitoring No.6 (16 Mar-15 Apr 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 16, 2024 11:34 AM | Aug 26, 2024 10:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0006-001_Result of environmental monitoring No.6 (16 Mar-15 Apr 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0006-001_Result of environmental monitoring No.6 (16 Mar-15 Apr 24) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2899 | 522803-01-RPT-HSE-0005-001_Result of environmental monitoring No.5 (16 Feb-15 Mar 24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 16, 2024 11:33 AM | Aug 26, 2024 10:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0005-001_Result of environmental monitoring No.5 (16 Feb-15 Mar 24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0005-001_Result of environmental monitoring No.5 (16 Feb-15 Mar 24) |  | V2 | 0 | Approved | Updated review status
CLOSED | 2855 | 522803-01-RFAM-HY-0013-002_Water Heater | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Aug 15, 2024 10:35 AM | Aug 28, 2024 9:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0013-002_Water Heater.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0013-002_Water Heater |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2841 | 522803-01-RPT-AR-0001-001_Check screed thickness 6th Floor | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 14, 2024 2:29 PM | Sep 9, 2024 8:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-AR-0001-001_Check screed thickness 6th Floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1465_RPT-AR_Request for Approval Report (Architecture)/522803-01-RPT-AR-0001-001_Check screed thickness 6th Floor |  | V1 | 0 | Approved | Updated review status
CLOSED | 2834 | 522803-01-RFAM-ME-0029-005_MCP_MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 13, 2024 5:03 PM | Aug 15, 2024 9:04 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-005_MCP_MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-005_MCP_MCC |  | V1 | 1 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Aug 14, 2024 12:18 AM): ME reviewed in attached file.
CLOSED | 2799 | 522803-01-RFAM-ME-0057-001_Cable Tags | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 9, 2024 3:56 PM | Aug 28, 2024 9:24 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0057-001_Cable Tags.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0057-001_Cable Tags |  | V1 | 0 | Approved | Updated review status
CLOSED | 2726 | 522803-01-MRPT-GEN-0010_001_TTI Monthly Construction No.10_JUL 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Aug 6, 2024 4:55 PM | Aug 26, 2024 9:54 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0010_001_TTI Monthly Construction No.10_JUL 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0010_001_TTI Monthly Construction No.10_JUL 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2723 | 522803-01-RFAM-SE-0019-001_UVSS | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Aug 6, 2024 3:12 PM | Aug 9, 2024 1:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0019-001_UVSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0019-001_UVSS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2718 | 522803-01-RFAM-ME-0056-001_Cable Lug | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 6, 2024 9:00 AM | Aug 15, 2024 4:57 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0056-001_Cable Lug.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0056-001_Cable Lug |  | V1 | 1 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Aug 14, 2024 12:21 AM): ME commented in attached file.
CLOSED | 2713 | 522803-01-RFAM-EL-0052-003_Miscellaneous | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Aug 5, 2024 2:38 PM | Aug 16, 2024 10:26 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0052-003_Miscellaneous.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0052-003_Miscellaneous |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2669 | 522803-01-MS-ME-0003-001_Thermal energy storage tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Aug 1, 2024 10:32 AM | Aug 16, 2024 4:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0003-001_Thermal energy storage tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0003-001_Thermal energy storage tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2657 | 522803-01-MS-ME-0008-002_PAHU, AHU, FCU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 5:02 PM | Aug 19, 2024 10:26 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0008-002_PAHU, AHU, FCU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0008-002_PAHU, AHU, FCU |  | V1 | 0 | Approved | Updated review status
CLOSED | 2656 | 522803-01-MS-HY-0012-002_Septic Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 4:44 PM | Aug 23, 2024 9:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0012-002_Septic Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0012-002_Septic Tank |  | V2 | 0 | Approved | Updated review status
CLOSED | 2652 | 522803-01-RFAM-SE-0018-001_Sensor_Locking and Wiegand Interface Cable | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 2:18 PM | Aug 6, 2024 4:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0018-001_Sensor_Locking and Wiegand Interface Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0018-001_Sensor_Locking and Wiegand Interface Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2651 | 522803-01-RFAM-SE-0017-001_FOC Cable | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 2:17 PM | Aug 6, 2024 4:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0017-001_FOC Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0017-001_FOC Cable |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2650 | 522803-01-RFAM-SE-0016-001_UTP Cable | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 2:16 PM | Aug 7, 2024 8:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0016-001_UTP Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0016-001_UTP Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2649 | 522803-01-RFAM-SE-0013-003_Break Glass | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 2:15 PM | Aug 5, 2024 1:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0013-003_Break Glass.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0013-003_Break Glass |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2643 | 522803-01-MS-ME-0016-001_Insulation and Jacket Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 31, 2024 1:15 PM | Aug 23, 2024 9:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0016-001_Insulation and Jacket Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0016-001_Insulation and Jacket Installation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2603 | 522803-01-MS-ME-0004-001_Chilled piping and Cooling piping on cooling tower yard | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 27, 2024 1:31 PM | Aug 13, 2024 2:07 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0004-001_Chilled piping and Cooling piping on cooling tower yard.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0004-001_Chilled piping and Cooling piping on cooling tower yard |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2579 | 522803-01-MS-CSA-0007-002_MS_of Precast Wall Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 26, 2024 5:30 PM | Aug 13, 2024 12:37 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0007-002_MS_of Precast Wall Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0007-002_MS_of Precast Wall Work |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2578 | 522803-01-RFAM-ST-0049-001_Floor Flatness concrete mix design (Siam City) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 26, 2024 5:23 PM | Aug 5, 2024 10:41 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0049-001_Floor Flatness concrete mix design (Siam City).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0049-001_Floor Flatness concrete mix design (Siam City) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2577 | 522803-01-RFAM-ST-0048-001_Floor Flatness concrete mix design (M Concrete) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 26, 2024 4:49 PM | Aug 5, 2024 10:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0048-001_Floor Flatness concrete mix design (M Concrete).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0048-001_Floor Flatness concrete mix design (M Concrete) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2570 | 522803-01-RFAM-MEP-0001-003_Equipment List and Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 26, 2024 11:13 AM | Aug 16, 2024 10:02 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-MEP-0001-003_Equipment List and Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0001-003_Equipment List and Schedule |  | V1 | 0 | Approved | Updated review status
CLOSED | 2567 | 522803-01-RPT-LE-0010-001_Monthly Report for LEED No.10 for July 2024.pdf | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 26, 2024 10:26 AM | Aug 7, 2024 4:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0010-001_Monthly Report for LEED No.10 for July 2024.pdf.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0010-001_Monthly Report for LEED No.10 for July 2024.pdf |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2502 | 522803-01-MS-ME-0020-001_Addition Plate for Maintenance Valve | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 25, 2024 3:32 PM | Aug 9, 2024 4:27 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0020-001_Addition Plate for Maintenance Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0020-001_Addition Plate for Maintenance Valve |  | V1 | 0 | Approved | Updated review status
CLOSED | 2501 | 522803-01-MS-ME-0019-001_Add Insert Plate for CHW and CDW Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 25, 2024 3:25 PM | Aug 13, 2024 2:20 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0019-001_Add Insert Plate for CHW and CDW Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0019-001_Add Insert Plate for CHW and CDW Pipe |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2497 | 522803-01-ITP-MEP-0001-004_MEP ITP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 25, 2024 2:57 PM | Sep 9, 2024 1:39 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ITP-MEP-0001-004_MEP ITP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-MEP-0001-004_MEP ITP |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2493 | 522803-01-MS-SE-0013-001_EKMS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 25, 2024 11:28 AM | Aug 13, 2024 9:01 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0013-001_EKMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0013-001_EKMS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2484 | 522803-01-RFAM-SE-0015-001_Joystick | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 24, 2024 3:56 PM | Jul 31, 2024 8:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0015-001_Joystick.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0015-001_Joystick |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2483 | 522803-01-RFAM-SE-0014-001_VSS | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 24, 2024 3:56 PM | Jul 31, 2024 11:48 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0014-001_VSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0014-001_VSS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2476 | 522803-01-RFAM-EL-0074-003_Rack_Accessories - ISMS ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 23, 2024 4:45 PM | Aug 8, 2024 2:41 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0074-003_Rack_Accessories - ISMS ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0074-003_Rack_Accessories - ISMS ECMS |  | V1 | 0 | Make correction as noted & proceed | Updated review status | Kiattisak Thongoon(Aug 1, 2024 10:21 AM): Approved with Comments
CLOSED | 2474 | 522803-01-RFAM-HY-0019-002_PPR Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jul 23, 2024 2:25 PM | Aug 6, 2024 7:26 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0019-002_PPR Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0019-002_PPR Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 2473 | 522803-01-CAL-ST-0017-004_Calculation sheet of Precast Wall Panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 23, 2024 1:08 PM | Aug 13, 2024 12:02 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0017-004_Calculation sheet of Precast Wall Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0017-004_Calculation sheet of Precast Wall Panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2457 | 522803-01-MS-EL-0015-001_Fire Barrier | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 20, 2024 1:27 PM | Jul 30, 2024 11:00 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0015-001_Fire Barrier.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0015-001_Fire Barrier |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2455 | 522803-01-RFAM-HY-0029-002_Digital Water Meter | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jul 20, 2024 8:29 AM | Aug 6, 2024 7:20 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0029-002_Digital Water Meter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0029-002_Digital Water Meter |  | V1 | 0 | Approved | Updated review status
CLOSED | 2450 | 522803-01-RFA-EL-0001-002_ECMS Point List | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 19, 2024 5:22 PM | Jul 30, 2024 9:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0001-002_ECMS Point List.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0001-002_ECMS Point List |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2437 | 522803-01-RFAM-ME-0001-006_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 19, 2024 8:57 AM | Jul 31, 2024 4:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-006_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-006_VSD |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jul 26, 2024 3:23 PM): ME comment in attached file
CLOSED | 2434 | 522803-01-MS-ME-0018-001_Maintenance and Service Butterfly valve | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 19, 2024 7:48 AM | Aug 9, 2024 4:24 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0018-001_Maintenance and Service Butterfly valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0018-001_Maintenance and Service Butterfly valve |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2428 | 522803-01-MS-SE-0012-001_FOC Termination | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 18, 2024 5:11 PM | Jul 31, 2024 11:30 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0012-001_FOC Termination.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0012-001_FOC Termination |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2406 | 522803-01-MS-SE-0010-001_Intercom System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 18, 2024 8:51 AM | Jul 31, 2024 11:37 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0010-001_Intercom System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0010-001_Intercom System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2397 | 522803-01-RFAM-EL-0069-001_Cable for Sensor | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 17, 2024 5:20 PM | Aug 2, 2024 3:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0069-001_Cable for Sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0069-001_Cable for Sensor |  | V1 | 0 | Approved | Updated review status
CLOSED | 2396 | 522803-01-MS-SE-0011-001_UTP Cable Termination | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 17, 2024 5:16 PM | Aug 5, 2024 4:50 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0011-001_UTP Cable Termination.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0011-001_UTP Cable Termination |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2395 | 522803-01-MS-SE-0009-001_PIDS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 17, 2024 5:16 PM | Aug 5, 2024 5:59 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0009-001_PIDS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0009-001_PIDS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2393 | 522803-01-MS-SE-0008-001_ISMS Server | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 17, 2024 5:09 PM | Aug 19, 2024 4:17 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0008-001_ISMS Server.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0008-001_ISMS Server |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2379 | 522803-01-RPT-ST-0037-001_Report Concrete Slab Accuracy Evaluation After Stressing Tendon Sheet_5th Fl | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 16, 2024 5:08 PM | Jul 25, 2024 4:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0037-001_Report Concrete Slab Accuracy Evaluation After Stressing Tendon Sheet_5th Fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0037-001_Report Concrete Slab Accuracy Evaluation After Stressing Tendon Sheet_5th Fl |  | V1 | 0 | Approved | Updated review status
CLOSED | 2376 | 522803-01-RFAM-SE-0012-002_EACAS Controller | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 16, 2024 1:20 PM | Jul 31, 2024 1:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0012-002_EACAS Controller.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0012-002_EACAS Controller |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2361 | 522803-01-RFAM-SE-0011-002_LPR | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 15, 2024 5:38 PM | Jul 31, 2024 9:12 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0011-002_LPR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0011-002_LPR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2358 | 522803-01-MS-ME-0013-002_Ventilation Fan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 15, 2024 3:48 PM | Aug 19, 2024 4:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0013-002_Ventilation Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0013-002_Ventilation Fan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2354 | 522803-01-RFAM-SE-0007-002_Photo ID Equipment | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 15, 2024 2:23 PM | Jul 31, 2024 1:29 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0007-002_Photo ID Equipment.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0007-002_Photo ID Equipment |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2346 | 522803-01-RFAM-EL-0053-001_Data Hall Busway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 13, 2024 12:40 PM | Aug 16, 2024 10:14 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0053-001_Data Hall Busway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0053-001_Data Hall Busway |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2329 | 522803-01-MS-SE-0007-001_VWS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 12, 2024 2:13 PM | Aug 5, 2024 5:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0007-001_VWS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0007-001_VWS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2312 | 522803-01-RPT-ST-0026-003_Report of Tensile Test for steel (June 2024) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 12, 2024 9:15 AM | Jul 19, 2024 4:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0026-003_Report of Tensile Test for steel (June 2024).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0026-003_Report of Tensile Test for steel (June 2024) |  | V1 | 0 | Approved | Updated review status
CLOSED | 2303 | 522803-01-RPT-ST-0033-001_Report Fuel Tank 1 (Testing Water Leak) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 11, 2024 5:31 PM | Jul 19, 2024 4:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0033-001_Report Fuel Tank 1 (Testing Water Leak).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0033-001_Report Fuel Tank 1 (Testing Water Leak) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2301 | 522803-01-RPT-ST-0036-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at 4th Fl. | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 11, 2024 5:09 PM | Jul 19, 2024 8:58 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0036-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at 4th Fl..pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0036-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at 4th Fl |  | V1 | 0 | Approved | Updated review status
CLOSED | 2296 | 522803-01-MS-CSA-0009-002_Method Statement of Install Retention Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 11, 2024 3:37 PM | Jul 19, 2024 4:29 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0009-002_Method Statement of Install Retention Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0009-002_Method Statement of Install Retention Tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2294 | 522803-01-RFA-HY-0002-001_FMS GUI | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 2:59 PM | Jul 18, 2024 11:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-HY-0002-001_FMS GUI.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0002-001_FMS GUI |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2293 | 522803-01-RFA-HY-0001-001_FMS Point List | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 2:58 PM | Aug 5, 2024 11:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HY-0001-001_FMS Point List.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1028_RFA-HY_Request for Approval (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFA-HY-0001-001_FMS Point List |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2292 | 522803-01-MS-SE-0005-001_Raceway | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 2:53 PM | Aug 5, 2024 6:07 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0005-001_Raceway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0005-001_Raceway |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2282 | 522803-01-MS-SE-0006-001_UVSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 1:09 PM | Aug 5, 2024 5:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0006-001_UVSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0006-001_UVSS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2279 | 522803-01-MS-SE-0004-001_Conduit Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 10:02 AM | Aug 5, 2024 6:14 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0004-001_Conduit Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0004-001_Conduit Installation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2278 | 522803-01-MS-SE-0003-001_Cable Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 11, 2024 10:02 AM | Jul 31, 2024 8:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0003-001_Cable Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0003-001_Cable Installation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2273 | 522803-01-MRPT-GEN-0009_001_TTI Monthly Construction No.09_June 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 10, 2024 5:36 PM | Aug 2, 2024 10:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0009_001_TTI Monthly Construction No.09_June 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0009_001_TTI Monthly Construction No.09_June 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2272 | 522803-01-MS-ST-0007-001_MS for Steel Stage Cooling Tower Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 10, 2024 4:04 PM | Jul 19, 2024 4:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0007-001_MS for Steel Stage Cooling Tower Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0007-001_MS for Steel Stage Cooling Tower Installation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2271 | 522803-01-RPT-ST-0035-001_Report of Concrete Slab Accuracy Evaluation at the G Fl | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 10, 2024 3:58 PM | Jul 19, 2024 8:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0035-001_Report of Concrete Slab Accuracy Evaluation at the G Fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0035-001_Report of Concrete Slab Accuracy Evaluation at the G Fl |  | V1 | 0 | Approved | Updated review status
CLOSED | 2270 | 522803-01-RPT-ST-0034-001_Report of Concrete Slab Accuracy Eva After Stressing Tendon Sht at the 3rd Fl | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 10, 2024 3:55 PM | Jul 19, 2024 8:54 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0034-001_Report of Concrete Slab Accuracy Eva After Stressing Tendon Sht at the 3rd Fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0034-001_Report of Concrete Slab Accuracy Eva After Stressing Tendon Sht at the 3rd Fl |  | V1 | 0 | Approved | Updated review status
CLOSED | 2268 | 522803-01-RFAM-SE-0013-002_Break Glass | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jul 10, 2024 11:02 AM | Jul 19, 2024 4:07 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0013-002_Break Glass.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0013-002_Break Glass |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2267 | 522803-01-MS-SE-0002-001_VSS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 10, 2024 10:52 AM | Aug 5, 2024 5:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0002-001_VSS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0002-001_VSS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2266 | 522803-01-RFA-EL-0002-001_Cable Tag | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 10, 2024 10:45 AM | Aug 13, 2024 10:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-EL-0002-001_Cable Tag.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0002-001_Cable Tag |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2238 | 522803-01-MS-SE-0001-001_EACAS | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 8, 2024 12:58 PM | Aug 5, 2024 5:48 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-SE-0001-001_EACAS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1052_MS-SE_Request for Approval Method Statement (Security)/522803-01-MS-SE-0001-001_EACAS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2236 | 522803-01-RPT-ST-0032-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at the 2nd Fl | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 6, 2024 9:13 PM | Jul 19, 2024 8:50 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0032-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at the 2nd Fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0032-001_Report of Concrete Slab Accuracy Evaluation After Stressing Tendon Sht at the 2nd Fl |  | V1 | 0 | Approved | Updated review status
CLOSED | 2224 | 522803-01-RPT-ST-0031-001_Concrete Slab Evaluation After Stressing Tendon Sht_Mz Fl | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 4, 2024 1:30 PM | Jul 9, 2024 2:56 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0031-001_Concrete Slab Evaluation After Stressing Tendon Sht_Mz Fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0031-001_Concrete Slab Evaluation After Stressing Tendon Sht_Mz Fl |  | V2 | 0 | Approved | Updated review status
CLOSED | 2222 | 522803-01-RFAM-ST-0045-002_Sample of Galvanize Coating for Steel Structure | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 4, 2024 1:13 PM | Jul 16, 2024 12:32 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0045-002_Sample of Galvanize Coating for Steel Structure.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0045-002_Sample of Galvanize Coating for Steel Structure |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2220 | 522803-01-RFAM-ME-0029-004_MCP_MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jul 4, 2024 10:38 AM | Jul 17, 2024 5:41 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-004_MCP_MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-004_MCP_MCC |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jul 8, 2024 1:01 PM): ME comment in attached file.
CLOSED | 2211 | 522803-01-RFAM-ST-0046-002_Lucky Floor at cooling tower | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jul 3, 2024 10:08 AM | Jul 16, 2024 12:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0046-002_Lucky Floor at cooling tower.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0046-002_Lucky Floor at cooling tower |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2199 | 522803-01-MS-EL-0010-001_LV TERMINATION WORK | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jul 1, 2024 3:59 PM | Jul 26, 2024 2:17 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0010-001_LV TERMINATION WORK.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0010-001_LV TERMINATION WORK |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2184 | 522803-01-MS-ME-0008-001_PAHU, AHU, FCU | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 28, 2024 2:07 PM | Jul 23, 2024 3:50 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0008-001_PAHU, AHU, FCU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0008-001_PAHU, AHU, FCU |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2167 | 522803-01-RFAM-ME-0012-007_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 27, 2024 2:42 PM | Jul 8, 2024 9:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-007_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-007_Thermal Energy Storage Tank |  | V1 | 2 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jul 2, 2024 5:48 PM): ME comment in attached file.
CLOSED | 2166 | 522803-01-RFAM-ME-0001-005_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 27, 2024 2:35 PM | Jul 10, 2024 12:14 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-005_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-005_VSD |  | V1 | 2 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Jul 5, 2024 1:09 PM): ME comment in attached file
CLOSED | 2152 | 522803-01-RFAM-ME-0055-001_Painting for Thermal Storage tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 26, 2024 4:23 PM | Jul 3, 2024 12:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0055-001_Painting for Thermal Storage tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0055-001_Painting for Thermal Storage tank |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jul 2, 2024 2:43 PM): ME commented in attached file
CLOSED | 2130 | 522803-01-RPT-LE-0009-001_Monthly Report for LEED No.09 for June 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 25, 2024 11:25 AM | Jul 3, 2024 6:11 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0009-001_Monthly Report for LEED No.09 for June 2024.pdf.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0009-001_Monthly Report for LEED No.09 for June 2024.pdf |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2109 | 522803-01-RFAM-FP-0018-001_Fire Barrier | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jun 24, 2024 11:32 AM | Jul 3, 2024 1:35 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0018-001_Fire Barrier.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0018-001_Fire Barrier |  | V1 | 0 | Approved | Updated review status
CLOSED | 2108 | 522803-01-RFAM-SE-0013-001_Break Glass | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 24, 2024 10:47 AM | Jul 1, 2024 2:01 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0013-001_Break Glass.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0013-001_Break Glass |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2107 | 522803-01-RFAM-SE-0012-001_EACAS Controller | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 24, 2024 10:46 AM | Jul 1, 2024 2:03 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0012-001_EACAS Controller.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0012-001_EACAS Controller |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 2094 | 522803-01-RFAM-HY-0036-001_Fire Barrier | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jun 22, 2024 6:37 PM | Jul 8, 2024 8:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0036-001_Fire Barrier.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0036-001_Fire Barrier |  | V1 | 0 | Approved | Updated review status
CLOSED | 2093 | 522803-01-RFAM-HY-0028-002_Submersible Pump for Sewage | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jun 22, 2024 6:37 PM | Jul 8, 2024 8:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0028-002_Submersible Pump for Sewage.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0028-002_Submersible Pump for Sewage |  | V1 | 0 | Approved | Updated review status
CLOSED | 2088 | 522803-01-RFAM-EL-0007-004_Earthing and Lightning | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 21, 2024 9:53 AM | Jul 15, 2024 3:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0007-004_Earthing and Lightning.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0007-004_Earthing and Lightning |  | V1 | 0 | Approved | Updated review status
CLOSED | 2087 | 522803-01-RFA-HSE-0014-001_Plan and calculation for scaffolding position support roof area | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 21, 2024 9:33 AM | Jul 2, 2024 4:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0014-001_Plan and calculation for scaffolding position support roof area.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0014-001_Plan and calculation for scaffolding position support roof area |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2051 | 522803-01-RFAM-EL-0052-002_Miscellaneous | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 19, 2024 5:45 PM | Jul 23, 2024 1:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0052-002_Miscellaneous.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0052-002_Miscellaneous |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 2050 | 522803-01-RFAM-EL-0056-001_Flexible Cable for STS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 19, 2024 5:24 PM | Jul 23, 2024 1:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0056-001_Flexible Cable for STS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0056-001_Flexible Cable for STS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1996 | 522803-01-RFAM-FP-0017-001_Insulation for exhaust pipe | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jun 17, 2024 3:51 PM | Jun 26, 2024 5:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0017-001_Insulation for exhaust pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0017-001_Insulation for exhaust pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 1989 | 522803-01-RFAM-SE-0008-001_LPR Reader | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 17, 2024 8:22 AM | Jun 25, 2024 9:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0008-001_LPR Reader.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0008-001_LPR Reader |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1988 | 522803-01-RFAM-SE-0011-001_LPR | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 15, 2024 4:10 PM | Jun 25, 2024 9:33 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0011-001_LPR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0011-001_LPR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1987 | 522803-01-RFAM-SE-0010-001_SFP For Network Switch | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 15, 2024 4:08 PM | Jun 19, 2024 2:02 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0010-001_SFP For Network Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0010-001_SFP For Network Switch |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1986 | 522803-01-RFAM-SE-0009-001_Video analytic | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 15, 2024 4:07 PM | Jun 19, 2024 2:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0009-001_Video analytic.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0009-001_Video analytic |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1978 | 522803-01-RFA-EL-0001-001_ECMS Point List | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 5:35 PM | Jul 9, 2024 2:51 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-EL-0001-001_ECMS Point List.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1030_RFA-EL_Request for Approval (Electrical)/522803-01-RFA-EL-0001-001_ECMS Point List |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1977 | 522803-01-RFAM-ST-0047-001_Topping concrete of M concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 14, 2024 5:02 PM | Jun 20, 2024 1:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0047-001_Topping concrete of M concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0047-001_Topping concrete of M concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 1970 | 522803-01-RFAM-SE-0007-001_Photo ID Equipment | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 11:38 AM | Jun 19, 2024 2:16 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0007-001_Photo ID Equipment.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0007-001_Photo ID Equipment |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1969 | 522803-01-RFAM-SE-0006-001_REX Button | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 11:38 AM | Jun 19, 2024 2:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0006-001_REX Button.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0006-001_REX Button |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1968 | 522803-01-RFAM-SE-0005-001_Credentials (HID Cards) | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 11:37 AM | Jun 19, 2024 2:09 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0005-001_Credentials (HID Cards).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0005-001_Credentials (HID Cards) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1967 | 522803-01-RFAM-SE-0004-001_Card Reader | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 11:37 AM | Jun 19, 2024 2:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0004-001_Card Reader.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0004-001_Card Reader |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1963 | 522803-01-RFAM-SE-0003-001_Magnetic Reed Switch | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 9:37 AM | Jun 19, 2024 10:03 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0003-001_Magnetic Reed Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0003-001_Magnetic Reed Switch |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1962 | 522803-01-RFAM-SE-0002-001_Electronic V-Lock Bolt | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 9:37 AM | Jun 18, 2024 9:00 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0002-001_Electronic V-Lock Bolt.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0002-001_Electronic V-Lock Bolt |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1956 | 522803-01-MS-ME-0005-002_CHW,CDW Riser | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 14, 2024 8:16 AM | Jul 17, 2024 3:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0005-002_CHW,CDW Riser.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0005-002_CHW,CDW Riser |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1948 | 522803-01-MS-ME-0002-002_CHW,CDW Piping 1G,1M | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 13, 2024 4:09 PM | Jun 17, 2024 6:04 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0002-002_CHW,CDW Piping 1G,1M.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0002-002_CHW,CDW Piping 1G,1M |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1947 | 522803-01-RFAM-ST-0046-001_Lucky Floor at cooling tower | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 13, 2024 3:43 PM | Jun 20, 2024 1:25 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0046-001_Lucky Floor at cooling tower.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0046-001_Lucky Floor at cooling tower |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1904 | 522803-01-RFAM-ME-0001-004_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 11, 2024 11:59 AM | Jun 17, 2024 3:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-004_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-004_VSD |  | V1 | 13 | Disapproved | Updated review status | Kloer Chongchaikit(Jun 11, 2024 7:57 PM): ME comment in attachment.(Edited Jun 11, 2024 7:57 PM)
CLOSED | 1894 | 522803-01-RFAM-HY-0023-002_Valves for Hydraulics Work | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jun 10, 2024 5:58 PM | Jul 3, 2024 11:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0023-002_Valves for Hydraulics Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0023-002_Valves for Hydraulics Work |  | V1 | 0 | Approved | Updated review status
CLOSED | 1891 | 522803-01-MS-ME-0007-001_HVAC PUMP | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 10, 2024 3:25 PM | Jul 17, 2024 3:00 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0007-001_HVAC PUMP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0007-001_HVAC PUMP |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1879 | 522803-01-RFAM-ST-0045-001_Galvanize coating | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 7, 2024 2:56 PM | Jun 20, 2024 1:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0045-001_Galvanize coating.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0045-001_Galvanize coating |  | V1 | 0 | Approved | Updated review status
CLOSED | 1877 | 522803-01-MRPT-GEN-0008-001_TTI Monthly Construction No.08_May 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 7, 2024 9:48 AM | Jun 17, 2024 1:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0008-001_TTI Monthly Construction No.08_May 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0008-001_TTI Monthly Construction No.08_May 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1876 | 522803-01-RFAM-ST-0044-001-Bolt & nut at canopy | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 7, 2024 9:07 AM | Jun 20, 2024 1:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0044-001-Bolt & nut at canopy.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0044-001-Bolt & nut at canopy |  | V1 | 0 | Approved | Updated review status
CLOSED | 1866 | 522803-01-RFAM-ME-0054-001_VD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 6, 2024 3:54 PM | Jul 8, 2024 8:43 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0054-001_VD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0054-001_VD |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(Jun 30, 2024 6:31 PM): ME commented in attached file.
CLOSED | 1865 | 522803-01-RFAM-ME-0045-002_Vibration Isolator and Flexible | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 6, 2024 3:53 PM | Jun 20, 2024 9:07 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0045-002_Vibration Isolator and Flexible.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0045-002_Vibration Isolator and Flexible |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jun 11, 2024 8:52 PM): ME comment in attached file
CLOSED | 1864 | 522803-01-RFAM-ME-0008-003_Chemical Feed Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 6, 2024 3:45 PM | Jun 20, 2024 10:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0008-003_Chemical Feed Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0008-003_Chemical Feed Pump |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jun 11, 2024 3:01 PM): ME comment in attachment
CLOSED | 1862 | 522803-01-RPT-LE-0008-002_Monthly Report for LEED No.08 for May 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 6, 2024 2:59 PM | Jun 17, 2024 1:31 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0008-002_Monthly Report for LEED No.08 for May 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0008-002_Monthly Report for LEED No.08 for May 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1859 | 522803-01-RPT-ST-0030-001_Report Fuel Tank 2 (Test Water Leak) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 6, 2024 2:47 PM | Jun 20, 2024 1:47 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0030-001_Report Fuel Tank 2 (Test Water Leak).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0030-001_Report Fuel Tank 2 (Test Water Leak) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1853 | 522803-01-RFAM-EL-0038-003_Earth Fault Relay | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 6, 2024 1:44 PM | Jun 21, 2024 8:55 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0038-003_Earth Fault Relay.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0038-003_Earth Fault Relay |  | V1 | 0 | Approved | Updated review status
CLOSED | 1831 | 522803-01-RFAM-HY-0031-001_Pressure Reducing Valves | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jun 5, 2024 9:57 AM | Jul 3, 2024 11:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0031-001_Pressure Reducing Valves.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0031-001_Pressure Reducing Valves |  | V1 | 0 | Approved | Updated review status
CLOSED | 1827 | 522803-01-RFAM-ST-0043-001_Sika MonoTop-102 Water Plug TH | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jun 4, 2024 4:42 PM | Jun 10, 2024 11:41 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0043-001_Sika MonoTop®-102 Water Plug TH.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0043-001_Sika MonoTop®-102 Water Plug TH |  | V1 | 0 | Approved | Updated review status
CLOSED | 1821 | 522803-01-MS-EL-0011-001_FOC Termination | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 4, 2024 2:28 PM | Jul 1, 2024 1:31 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0011-001_FOC Termination.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0011-001_FOC Termination |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1816 | 522803-01-RFAM-EL-0074-002_Rack_Accessories - ISMS ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jun 4, 2024 11:38 AM | Jul 1, 2024 1:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0074-002_Rack_Accessories - ISMS ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0074-002_Rack_Accessories - ISMS ECMS |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1815 | 522803-01-RFAM-HY-0032-001_Panel for Fuel Pump | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jun 4, 2024 11:33 AM | Jun 17, 2024 10:32 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0032-001_Panel for Fuel Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0032-001_Panel for Fuel Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 1809 | 522803-01-MS-ME-0005-001_CHW n CDW Riser Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jun 1, 2024 7:52 AM | Jun 11, 2024 10:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0005-001_CHW n CDW Riser Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0005-001_CHW n CDW Riser Pipe |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1806 | 522803-01-CAL-ST-0017-003_Calculation sheet of Precast Wall Panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 31, 2024 5:43 PM | Jun 28, 2024 2:38 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0017-003_Calculation sheet of Precast Wall Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0017-003_Calculation sheet of Precast Wall Panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1801 | 522803-01-RFAM-ME-0050-001_Fire Stop Material | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 31, 2024 1:44 PM | Jun 17, 2024 9:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0050-001_Fire Stop Material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0050-001_Fire Stop Material |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jun 5, 2024 5:17 PM): ME comment in attached file
CLOSED | 1800 | 522803-01-RFAM-ME-0049-002_AHU | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 31, 2024 1:43 PM | Jun 17, 2024 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0049-002_AHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0049-002_AHU |  | V1 | 5 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jun 6, 2024 5:17 PM): ME commented in attached file.
CLOSED | 1798 | 522803-01-RFAM-EL-0039-002_Network Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 31, 2024 1:31 PM | Jul 12, 2024 9:26 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0039-002_Network Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0039-002_Network Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1793 | 522803-01-MS-CSA-0014-001_MS of PU Foam Injection (PU300) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 30, 2024 5:47 PM | Jun 7, 2024 1:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0014-001_MS of PU Foam Injection (PU300).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0014-001_MS of PU Foam Injection (PU300) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1792 | 522803-01-RFAM-CV-0008-001_Galvanize Grating for Manhole | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 30, 2024 4:16 PM | Jun 17, 2024 1:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0008-001_Galvanize Grating for Manhole.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0008-001_Galvanize Grating for Manhole |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1789 | 522803-01-RFAM-HY-0035-001_Flexible Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 30, 2024 9:18 AM | Jun 17, 2024 10:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0035-001_Flexible Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0035-001_Flexible Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 1788 | 522803-01-RFAM-HY-0034-001_Fuel Pipe Color Code | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 30, 2024 9:18 AM | Jun 17, 2024 9:30 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0034-001_Fuel Pipe Color Code.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0034-001_Fuel Pipe Color Code |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1786 | 522803-01-MS-ST-0006-001_MS for repair crack Epoxy Resin injection | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 30, 2024 8:55 AM | Jun 7, 2024 1:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0006-001_MS for repair crack Epoxy Resin injection.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0006-001_MS for repair crack Epoxy Resin injection |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1778 | 522803-01-RFAM-EL-0062-003_Cable for ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 29, 2024 1:55 PM | Jun 7, 2024 6:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0062-003_Cable for ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0062-003_Cable for ECMS |  | V1 | 0 | Approved | Updated review status
CLOSED | 1773 | 522803-01-MS-CSA-0013-001_MS of Testing Water Leak for Fuel Tank (Test outside Wall) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 29, 2024 11:31 AM | Jun 7, 2024 1:45 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0013-001_MS of Testing Water Leak for Fuel Tank (Test outside Wall).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0013-001_MS of Testing Water Leak for Fuel Tank (Test outside Wall) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1764 | 522803-01-CAL-ST-0021-002_Cal sht of (ALC) Insee superblock wall panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 28, 2024 5:46 PM | Jun 24, 2024 9:50 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0021-002_Cal sht of (ALC) Insee superblock wall panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0021-002_Cal sht of (ALC) Insee superblock wall panel |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1736 | 522803-01-RFAM-SE-0001-002_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 1:24 PM | Jun 11, 2024 5:28 PM | 5 | 4 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-002_Security System_Cover Sheet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-002_Security System |  | V1 | 0 | Approved | Updated review status
CLOSED | 1736 | 522803-01-RFAM-SE-0001-002_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 1:24 PM | Jun 11, 2024 5:28 PM | 5 | 4 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-002_Security System_EACAS Devices (124 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-002_Security System |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1736 | 522803-01-RFAM-SE-0001-002_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 1:24 PM | Jun 11, 2024 5:28 PM | 5 | 4 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-002_Security System_ISMS (209 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-002_Security System |  | V1 | 0 | Approved | Updated review status
CLOSED | 1736 | 522803-01-RFAM-SE-0001-002_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 1:24 PM | Jun 11, 2024 5:28 PM | 5 | 4 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-002_Security System_PIDS (66 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-002_Security System |  | V1 | 0 | Approved | Updated review status
CLOSED | 1736 | 522803-01-RFAM-SE-0001-002_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 1:24 PM | Jun 11, 2024 5:28 PM | 5 | 4 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-002_Security System_UVSS (20 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-002_Security System |  | V1 | 0 | Approved | Updated review status
CLOSED | 1730 | 522803-01-MS-HY-0014-001_Delivery HY Pump Equipment | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 27, 2024 11:20 AM | Jun 17, 2024 5:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0014-001_Delivery HY Pump Equipment.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0014-001_Delivery HY Pump Equipment |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1727 | 522803-01-RPT-ST-0013-002_Trial mix report of Insee concrete on 1Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 27, 2024 11:03 AM | Jun 4, 2024 10:58 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0013-002_Trial mix report of Insee concrete on 1Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0013-002_Trial mix report of Insee concrete on 1Nov23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1724 | 522803-01-RPT-LE-0008-001_Monthly Report for LEED No.08 for May 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 27, 2024 10:35 AM | May 30, 2024 1:28 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0008-001_Monthly Report for LEED No.08 for May 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0008-001_Monthly Report for LEED No.08 for May 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1706 | 522803-01-RFAM-ME-0053-001_Pipe Insulation | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 23, 2024 4:02 PM | Jun 17, 2024 9:34 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0053-001_Pipe Insulation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0053-001_Pipe Insulation |  | V1 | 1 | Approved | Updated review status
CLOSED | 1705 | 522803-01-RFAM-ME-0052-001_VRF | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 23, 2024 4:01 PM | May 31, 2024 10:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0052-001_VRF.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0052-001_VRF |  | V1 | 6 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(May 28, 2024 9:27 PM): ME comment in attachement.
CLOSED | 1703 | 522803-01-MS-HY-0012-001_Septic Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 23, 2024 1:13 PM | Jun 11, 2024 10:49 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-HY-0012-001_Septic Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0012-001_Septic Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1702 | 522803-01-RFAM-EL-0021-003_ LV Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 23, 2024 11:38 AM | Jun 10, 2024 9:11 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0021-003_ LV Switchboard (405 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0021-003_LV Switchboard |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jun 10, 2024 9:09 AM): - refer clarify comment No.2, please follow IFC drawing to provide External protection relay 50/51 50N/51N and 64 - refer CCF EL-007 All Input UPS circuit breaker 1400KVA shall change to 3P+N - All Input UPS 500kVA shall change to 3P+N and upstream of UPS
CLOSED | 1702 | 522803-01-RFAM-EL-0021-003_ LV Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 23, 2024 11:38 AM | Jun 10, 2024 9:11 AM | 2 | 2 | 0 | 100% | Review closed | 4 | Shop drawings_LVSB (1986 pages).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0021-003_LV Switchboard |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jun 10, 2024 9:10 AM): See note in RFAM -EL-0021 and also if some point needs to change, please send RFI first before changing and production
CLOSED | 1700 | 522803-01-CAL-ST-0023-001_Calculation sheet of 6th post tension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 23, 2024 10:09 AM | Jun 4, 2024 10:38 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0023-001_Calculation sheet of 6th post tension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0023-001_Calculation sheet of 6th post tension slab |  | V1 | 0 | Approved | Updated review status
CLOSED | 1697 | 522803-01-RFAM-ST-0042-001_Vcon hollow core slab for Lift slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 23, 2024 8:22 AM | Jun 4, 2024 10:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0042-001_Vcon hollow core slab for Lift slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0042-001_Vcon hollow core slab for Lift slab |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1691 | 522803-01-RFAM-CV-0005-003_Daikure for Galvanized material | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 21, 2024 6:10 PM | Jun 7, 2024 2:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0005-003_Daikure for Galvanized material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0005-003_Daikure for Galvanized material |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1687 | 522803-01-MS-EL-0012-001_UTP TERMINATION | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 21, 2024 4:55 PM | Jun 19, 2024 11:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0012-001_UTP TERMINATION.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0012-001_UTP TERMINATION |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1685 | 522803-01-RFAM-CV-0010-001_Cover for fuel tank 1_2_3_4 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 21, 2024 8:41 AM | May 27, 2024 5:44 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0010-001_Cover for fuel tank 1_2_3_4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0010-001_Cover for fuel tank 1_2_3_4 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1678 | 522803-01-RFAM-HY-0029-001_Digital Water Meter | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 20, 2024 10:05 AM | May 24, 2024 4:53 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0029-001_Digital Water Meter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0029-001_Digital Water Meter |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1677 | 522803-01-RFAM-HY-0022-003_Sand Filter_Water Softener | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 20, 2024 10:04 AM | May 27, 2024 11:02 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0022-003_Sand Filter_Water Softener.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0022-003_Sand Filter_Water Softener |  | V1 | 0 | Approved | Updated review status
CLOSED | 1676 | 522803-01-RFAM-ME-0041-003_Balancing Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 20, 2024 10:00 AM | Jun 10, 2024 10:00 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0041-003_Balancing Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0041-003_Balancing Valve |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(Jun 5, 2024 5:12 PM): ME comment in attachment.
CLOSED | 1664 | 522803-01-RPT-ST-0029-001_Report of dynamic load test | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 17, 2024 3:42 PM | May 27, 2024 5:05 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0029-001_Report of dynamic load test.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0029-001_Report of dynamic load test |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1662 | 522803-01-MS-ME-0012-001_DFCU&ACU (VRF) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 17, 2024 2:17 PM | Jun 6, 2024 2:20 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0012-001_DFCU&ACU (VRF).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0012-001_DFCU&ACU (VRF) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1656 | 522803-01-RFAM-EL-0058-003_Network Rack and Accessories | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 17, 2024 8:11 AM | Jun 4, 2024 9:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0058-003_Network Rack and Accessories.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0058-003_Network Rack and Accessories |  | V1 | 0 | Approved | Updated review status
CLOSED | 1655 | 522803-01-RFAM-HY-0030-001_Insulation for AC Drain | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 17, 2024 8:01 AM | Jun 10, 2024 8:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0030-001_Insulation for AC Drain.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0030-001_Insulation for AC Drain |  | V1 | 0 | Approved | Updated review status
CLOSED | 1654 | 522803-01-RFA-SE-0002-001_SP400 Auto Bollard System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 16, 2024 6:27 PM | Jun 18, 2024 1:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-SE-0002-001_SP400 Auto Bollard System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0002-001_SP400 Auto Bollard System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1653 | 522803-01-RFA-SE-0001-001_Road Blocker | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 16, 2024 6:26 PM | Jun 17, 2024 2:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-SE-0001-001_Road Blocker.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1032_RFA-SE_Request for Approval (Security)/522803-01-RFA-SE-0001-001_Road Blocker |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1641 | 522803-01-CAL-ST-0022-001_Cal for load to back propping under 4th fl | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 15, 2024 4:21 PM | May 20, 2024 11:03 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0022-001_Cal for load to back propping under 4th fl.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0022-001_Cal for load to back propping under 4th fl |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1630 | 522803-01-RFAM-EL-0048-004_Lighting Fixture | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 14, 2024 2:50 PM | Jul 3, 2024 6:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0048-004_Lighting Fixture.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0048-004_Lighting Fixture |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1629 | 522803-01-RFAM-EL-0007-003_Earthing and Lightning | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 14, 2024 2:50 PM | May 24, 2024 12:13 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0007-003_Earthing and Lightning.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0007-003_Earthing and Lightning |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1623 | 522803-01-RFAM-ST-0041-001_Hollow core slab above fuel tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 13, 2024 10:49 AM | May 20, 2024 10:51 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0041-001_Hollow core slab above fuel tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0041-001_Hollow core slab above fuel tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1615 | 522803-01-MS-EL-0013-001_BUSDUCT | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 11, 2024 2:56 PM | Jun 12, 2024 12:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0013-001_BUSDUCT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0013-001_BUSDUCT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1614 | 522803-01-MS-HY-0007-001_Fuel Pipe (Aboveground) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 11, 2024 8:56 AM | Jun 6, 2024 2:31 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0007-001_Fuel Pipe (Aboveground).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0007-001_Fuel Pipe (Aboveground) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1613 | 522803-01-RFAM-EL-0064-001_Cable Ties for LV Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 11, 2024 8:52 AM | Jun 11, 2024 1:11 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0064-001_Cable Ties for LV Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0064-001_Cable Ties for LV Cable |  | V1 | 0 | Approved | Updated review status
CLOSED | 1603 | 522803-01-RFAM-HY-0010-002_Fuel BSP (Above Ground) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 10, 2024 2:24 PM | May 20, 2024 5:41 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0010-002_Fuel BSP (Above Ground).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0010-002_Fuel BSP (Above Ground) |  | V1 | 0 | Approved | Updated review status
CLOSED | 1602 | 522803-01-RFAM-ME-0051-001_FCU | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 10, 2024 2:14 PM | May 31, 2024 9:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0051-001_FCU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0051-001_FCU |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 1600 | 522803-01-CAL-ST-0021-001_Cal sht of (ALC) Insee superblock wall panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 10, 2024 10:20 AM | May 20, 2024 11:00 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0021-001_Cal sht of (ALC) Insee superblock wall panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0021-001_Cal sht of (ALC) Insee superblock wall panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1599 | 522803-01-CAL-ST-0020-001_Calculation sheet of 5th post tension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 10, 2024 10:13 AM | May 20, 2024 10:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0020-001_Calculation sheet of 5th post tension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0020-001_Calculation sheet of 5th post tension slab |  | V1 | 0 | Approved | Updated review status
CLOSED | 1594 | 522803-01-MS-ME-0002-001_CHW and CDW Piping 1G,1M | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 6:11 PM | May 28, 2024 9:31 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0002-001_CHW and CDW Piping 1G,1M.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0002-001_CHW and CDW Piping 1G,1M |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1593 | 522803-01-MS-ME-0013-001_Ventilation Fan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 6:06 PM | Jun 4, 2024 11:31 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ME-0013-001_Ventilation Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0013-001_Ventilation Fan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1583 | 522803-01-CAL-ST-0019-001_Cal for expansion bolt for installing PC wall at Core wall area | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 9, 2024 4:56 PM | May 20, 2024 10:55 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0019-001_Cal for expansion bolt for installing PC wall at Core wall area.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0019-001_Cal for expansion bolt for installing PC wall at Core wall area |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1577 | 522803-01-RFAM-EL-0065-002_ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 2:51 PM | Jun 4, 2024 9:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0065-002_ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0065-002_ECMS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1576 | 522803-01-RFAM-EL-0062-002_Cable for ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 2:03 PM | May 24, 2024 10:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0062-002_Cable for ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0062-002_Cable for ECMS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1575 | 522803-01-RFAM-ME-0029-003_MCP_MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 1:59 PM | May 31, 2024 9:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-003_MCP_MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-003_MCP_MCC |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(May 24, 2024 6:24 PM): EE comment in 522803-01-RFAM-ME-0029-003_MCP_MCC_DC 1 (AUR review) file
CLOSED | 1573 | 522803-01-RFAM-ME-0044-002_Damper | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 9, 2024 11:01 AM | May 31, 2024 9:50 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0044-002_Damper.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0044-002_Damper |  | V1 | 1 | Approved | Updated review status
CLOSED | 1572 | 522803-01-MRPT-GEN-0007-001_TTI Monthly Construction No.07_April 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 9, 2024 9:55 AM | May 17, 2024 10:33 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0007-001_TTI Monthly Construction No.07_April 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0007-001_TTI Monthly Construction No.07_April 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1571 | 522803-01-CAL-ST-0017-002_Calculation Sheet of Precast Wall Panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 9, 2024 9:38 AM | May 13, 2024 3:45 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0017-002_Calculation Sheet of Precast Wall Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0017-002_Calculation Sheet of Precast Wall Panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1560 | 522803-01-RFAM-ME-0040-003_Gas Detector System | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 8, 2024 2:43 PM | May 31, 2024 9:59 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0040-003_Gas Detector System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0040-003_Gas Detector System |  | V1 | 1 | Approved | Updated review status
CLOSED | 1559 | 522803-01-RFAM-ME-0001-003_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 8, 2024 2:42 PM | May 23, 2024 11:41 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-003_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-003_VSD |  | V1 | 5 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(May 16, 2024 10:09 AM): ME comment in attachment
CLOSED | 1547 | 522803-01-RFAM-ME-0049-001_AHU | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 4, 2024 3:53 PM | May 28, 2024 10:30 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0049-001_AHU.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0049-001_AHU |  | V1 | 1 | Make correction as noted & resubmit | Updated review status
CLOSED | 1546 | 522803-01-MS-HY-0010-002_Electrical Work Fuel Control System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 4, 2024 3:39 PM | Jun 6, 2024 1:57 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0010-002_Electrical Work Fuel Control System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0010-002_Electrical Work Fuel Control System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1532 | 522803-01-RFAM-ME-0046-002_Check Valve 14,18 inch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 3, 2024 3:13 PM | May 9, 2024 8:37 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0046-002_Check Valve 14,18 inch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0046-002_Check Valve 14,18 inch |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(May 8, 2024 4:14 PM): ME comment in attached file.
CLOSED | 1530 | 522803-01-RFAM-HY-0027-002_SP for Retention Tank | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | May 3, 2024 10:54 AM | May 20, 2024 5:24 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0027-002_SP for Retention Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0027-002_SP for Retention Tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 1527 | 522803-01-RFAM-CV-0005-002_Daikure for Galvanized material | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | May 3, 2024 9:09 AM | May 13, 2024 3:48 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0005-002_Daikure for Galvanized material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0005-002_Daikure for Galvanized material |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1516 | 522803-01-MS-ME-0010-001_AC Drain Piping | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 2, 2024 4:43 PM | May 29, 2024 4:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0010-001_AC Drain Piping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0010-001_AC Drain Piping |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1515 | 522803-01-MS-ME-0009-001_Refrigerant Piping | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 2, 2024 4:43 PM | May 24, 2024 2:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0009-001_Refrigerant Piping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0009-001_Refrigerant Piping |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1514 | 522803-01-MS-EL-0007-001_DB PANEL | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | May 2, 2024 4:42 PM | May 14, 2024 11:17 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0007-001_DB PANEL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0007-001_DB PANEL |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT deleted a comment. (May 14, 2024 11:17 AM) GSA CLIENT(May 14, 2024 11:17 AM): Room shall be clean during the installation
CLOSED | 1508 | 522803-01-RFAM-ME-0012-006_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 2, 2024 10:44 AM | May 10, 2024 2:28 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-006_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-006_Thermal Energy Storage Tank |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(May 8, 2024 4:09 PM): ME comment in attached file
CLOSED | 1508 | 522803-01-RFAM-ME-0012-006_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | May 2, 2024 10:44 AM | May 10, 2024 2:28 PM | 2 | 2 | 0 | 100% | Review closed | 4 | CFD_time.mp4 | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-006_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1504 | 522803-01-MS-ME-0015-001_Support for CHW,CDW Pipe | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 30, 2024 4:53 PM | May 24, 2024 2:44 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0015-001_Support for CHW,CDW Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0015-001_Support for CHW,CDW Pipe |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1492 | 522803-01-MS-CSA-0010-003_Method statement of fuel tank works_REV.3 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 30, 2024 9:06 AM | May 20, 2024 11:07 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0010-003_Method statement of fuel tank works_REV.3.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0010-003_Method statement of fuel tank works_REV.3 |  | V2 | 0 | Approved | Updated review status
CLOSED | 1491 | 522803-01-MS-CSA-0008-002_Method statement of piling works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 30, 2024 9:05 AM | May 20, 2024 11:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0008-002_Method statement of piling works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0008-002_Method statement of piling works |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1479 | 522803-01-MS-EL-0008-001_PDU PANEL | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 29, 2024 4:14 PM | May 14, 2024 11:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0008-001_PDU PANEL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0008-001_PDU PANEL |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(May 14, 2024 11:18 AM): Room shall be clean during the installation
CLOSED | 1477 | 522803-01-MS-EL-0006-001_MDB PANEL INSTALLATION | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 29, 2024 10:43 AM | May 14, 2024 11:08 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0006-001_MDB PANEL INSTALLATION.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0006-001_MDB PANEL INSTALLATION |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(May 14, 2024 11:08 AM): Room shall be clean during the installation
CLOSED | 1474 | 522803-01-CAL-ST-0018-001_Calculation of back propping for 3rd floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 29, 2024 9:00 AM | May 17, 2024 10:29 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0018-001_Calculation of back propping for 3rd floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0018-001_Calculation of back propping for 3rd floor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1462 | 522803-01-CAL-ST-0017-001_Calculation Sheet of Precast Wall Panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 27, 2024 8:42 AM | May 6, 2024 12:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0017-001_Calculation Sheet of Precast Wall Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0017-001_Calculation Sheet of Precast Wall Panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1450 | 522803-01-RFAM-ME-0005-004_CHW, CDW Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 26, 2024 1:20 PM | May 8, 2024 8:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0005-004_CHW, CDW Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0005-004_CHW, CDW Pump |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(May 3, 2024 3:29 AM): ME comment in attachment Kloer Chongchaikit(May 3, 2024 4:01 AM): ME comment in attached file
CLOSED | 1447 | 522803-01-MS-CSA-0011-001_MS of RC road for exterior works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 26, 2024 9:27 AM | May 20, 2024 11:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0011-001_MS of RC road for exterior works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0011-001_MS of RC road for exterior works |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1445 | 522803-01-RFAM-EL-0030-002_Switch and Outlet | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 26, 2024 8:49 AM | May 16, 2024 4:15 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0030-002_Switch and Outlet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0030-002_Switch and Outlet |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(May 16, 2024 4:15 PM): GSA preferred metallic black switch and outlet all area except interior design concern zone such as outside building , facade, office area, Lobby
CLOSED | 1442 | 522803-01-MS-CSA-0007-001_MS_of Precast Wall Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 25, 2024 5:15 PM | May 6, 2024 12:38 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0007-001_MS_of Precast Wall Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0007-001_MS_of_Precast_Wall Work |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1436 | 522803-01-RPT-LE-0007-001_Monthly Report for LEED No.07 for April 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 25, 2024 1:13 PM | May 7, 2024 9:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0007-001_Monthly Report for LEED No.07 for April 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0007-001_Monthly Report for LEED No.07 for April 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1410 | 522803-01-RFAM-ME-0048-001_Air Grilles | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 23, 2024 1:07 PM | May 27, 2024 11:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0048-001_Air Grilles.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0048-001_Air Grilles |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 1409 | 522803-01-MS-FP-0002-001_Sprinkler | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 23, 2024 12:03 PM | May 17, 2024 3:44 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-FP-0002-001_Sprinkler.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1049_MS-FP_Request for Approval Method Statement (Fire Protection)/522803-01-MS-FP-0002-001_Sprinkler |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1408 | 522803-01-RFAM-EL-0048-003_Lighting Fixture | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 23, 2024 11:38 AM | May 10, 2024 4:33 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0048-003_Lighting Fixture.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0048-003_Lighting Fixture |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1385 | 522803-01-RFAM-ME-0047-001_Duct | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 22, 2024 11:31 AM | May 8, 2024 8:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0047-001_Duct.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0047-001_Duct |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(May 3, 2024 3:15 AM): ME comment in attachment
CLOSED | 1371 | 522803-01-BIM-GEN-0001-002_BIM project Execution Plan Construction Phase | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 19, 2024 2:00 PM | Jun 17, 2024 9:03 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-BIM-GEN-0001-002_BIM project Execution Plan Construction Phase.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1008_BIM-GEN_Request for Approval BIM (General)/522803-01-BIM-GEN-0001-002_BIM project Execution Plan Construction Phase |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1360 | 522803-01-CAL-ST-0016-001_Calculation of Soil protection system analysis and design (Sheet Pile) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 18, 2024 9:30 AM | Apr 24, 2024 2:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0016-001_Calculation of Soil protection system analysis and design (Sheet Pile).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0016-001_Calculation of Soil protection system analysis and design (Sheet Pile) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1359 | 522803-01-MS-CSA-0010-002_Method statement of fuel tank works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 18, 2024 9:26 AM | Apr 22, 2024 11:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0010-002_Method statement of fuel tank works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0010-002_Method statement of fuel tank works |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1354 | 522803-01-MS-CSA-0009-001_Method Statement of Install Retention Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 16, 2024 12:08 PM | Apr 22, 2024 11:20 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0009-001_Method Statement of Install Retention Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0009-001_Method Statement of Install Retention Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1353 | 522803-01-CAL-ST-0015-001_Calculation of back propping for 2nd floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 16, 2024 11:10 AM | Apr 24, 2024 2:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0015-001_Calculation of back propping for 2nd floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0015-001_Calculation of back propping for 2nd floor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1344 | 522803-01-RFAM-HY-0028-001_Submersible Pump for Sewage | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Apr 12, 2024 3:49 PM | May 27, 2024 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0028-001_Submersible Pump for Sewage.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0028-001_Submersible Pump for Sewage |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1335 | 522803-01-RFAM-ST-0040-001_Concrete 210ksc for lintel & stud | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 12, 2024 1:35 PM | Apr 24, 2024 2:56 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0040-001_Siam city Concrete 210ksc for lintel & stud.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0040-001_Concrete 210ksc for lintel & stud |  | V1 | 0 | Approved | Updated review status
CLOSED | 1325 | 522803-01-MS-CSA-0008-001_Method statement of piling works 4 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 11, 2024 5:39 PM | Apr 24, 2024 2:50 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0008-001_Method statement of piling works 4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0008-001_Method statement of piling works 4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1324 | 522803-01-MS-ME-0011-001_Ducting System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 11, 2024 4:11 PM | May 17, 2024 4:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0011-001_Ducting System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0011-001_Ducting System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1321 | 522803-01-RFAM-EL-0058-002_Network Rack and Accessories | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 11, 2024 1:35 PM | Apr 29, 2024 9:45 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0058-002_Network Rack and Accessories.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0058-002_Network Rack and Accessories |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1320 | 522803-01-MS-CSA-0010-001_MS of fuel tank works. | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 11, 2024 11:46 AM | Apr 19, 2024 8:19 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0010-001_MS of fuel tank works..pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0010-001_MS of fuel tank works |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1319 | 522803-01-MS-EL-0004-001_Cable Rack and Ladder | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Apr 11, 2024 11:45 AM | May 16, 2024 4:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0004-001_Cable Rack and Ladder.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0004-001_Cable Rack and Ladder |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1318 | 522803-01-CAL-ST-0014-001_Calculation sheet of 4th fl. posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 11, 2024 11:38 AM | May 6, 2024 12:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0014-001_Calculation sheet of 4th fl. posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0014-001_Calculation sheet of 4th fl. posttension slab |  | V1 | 0 | Approved | Updated review status
CLOSED | 1316 | 522803-01-MS-CSA-0005-005_MS of soil protection work and excavation for exterior works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 11, 2024 10:55 AM | Apr 24, 2024 2:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0005-005_MS of soil protection work and excavation for exterior works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0005-005_MS of soil protection work and excavation for exterior works |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1306 | 522803-01-RFAM-ME-0046-001_Check Valve 14,18 inch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 10, 2024 1:32 PM | Apr 19, 2024 1:42 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0046-001_Check Valve 14,18 inch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0046-001_Check Valve 14,18 inch |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Apr 18, 2024 3:59 PM): ME comment in attached file (see V2 for latest)
CLOSED | 1305 | 522803-01-RFAM-ME-0010-003_MV Fan | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 10, 2024 10:39 AM | Apr 22, 2024 9:01 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0010-003_MV Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0010-003_MV Fan |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(Apr 18, 2024 3:49 PM): ME comment in attached file
CLOSED | 1302 | 522803-01-RFAM-ST-0037-002_Anchor bolt for structure support louver frame | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 9, 2024 5:49 PM | Apr 24, 2024 2:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0037-002_Anchor bolt for structure support louver frame.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0037-002_Anchor bolt for structure support louver frame |  | V1 | 0 | Approved | Updated review status
CLOSED | 1300 | 522803-01-RFAM-HY-0025-002_GSP Fitting | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Apr 9, 2024 5:40 PM | Apr 22, 2024 9:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0025-002_GSP Fitting.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0025-002_GSP Fitting |  | V1 | 0 | Approved | Updated review status
CLOSED | 1292 | 522803-01-RFAM-ME-0045-001_Isolator and Flexible | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 9, 2024 1:26 PM | Apr 18, 2024 9:28 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0045-001_Isolator and Flexible .pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0045-001_Isolator and Flexible |  | V1 | 2 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Apr 14, 2024 8:04 PM): ME comment in attached file
CLOSED | 1291 | 522803-01-RFAM-ME-0012-005_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 9, 2024 1:22 PM | Apr 19, 2024 10:59 AM | 2 | 1 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-005_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-005_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Apr 14, 2024 6:49 AM): ME comment in DC_SAUR file
CLOSED | 1291 | 522803-01-RFAM-ME-0012-005_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 9, 2024 1:22 PM | Apr 19, 2024 10:59 AM | 2 | 1 | 1 | 100% | Review closed | 4 | CFD v4.mp4 | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-005_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1287 | 522803-01-CAL-ST-0010-002_Calculation of back propping for Mezzanine floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 8, 2024 8:40 AM | Apr 11, 2024 1:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0010-002_Calculation of back propping for Mezzanine floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0010-002_Calculation of back propping for Mezzanine floor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1286 | 522803-01-MRPT-GEN-0006_001_TTI Monthly Construction No.06_March 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 8, 2024 8:08 AM | Apr 24, 2024 2:15 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0006_001_TTI Monthly Construction No.06_March 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0006_001_TTI Monthly Construction No.06_March 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1285 | 522803-01-CAL-ST-0012-002_Calculation sheet of 3rd posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 6, 2024 10:41 AM | May 6, 2024 12:26 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0012-002_Calculation sheet of 3rd posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0012-002_Calculation sheet of 3rd posttension slab |  | V1 | 0 | Approved | Updated review status
CLOSED | 1280 | 522803-01-RPT-ST-0026-002_Report of Tensile Test of Steel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 5, 2024 5:26 PM | Apr 10, 2024 10:04 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0026-002_Report of Tensile Test of Steel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0026-002_Report of Tensile Test of Steel |  | V1 | 0 | Approved | Updated review status
CLOSED | 1271 | 522803-01-RFAM-ME-0036-002_Water Detector with Conductivity Cable | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 5, 2024 9:55 AM | Apr 18, 2024 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0036-002_Water Detector with Conductivity Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0036-002_Water Detector with Conductivity Cable |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Apr 15, 2024 1:13 AM): ME comment in attachement
CLOSED | 1270 | 522803-01-RFAM-ME-0040-002_Gas Detector System | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 5, 2024 9:53 AM | Apr 18, 2024 9:16 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0040-002_Gas Detector System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0040-002_Gas Detector System |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Apr 15, 2024 2:01 AM): ME comment in attached file.
CLOSED | 1259 | 522803-01-RFAM-EL-0063-002_Surge Protection Device (Communication System) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 4, 2024 9:34 AM | Apr 29, 2024 12:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0063-002_Surge Protection Device (Communication System).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0063-002_Surge Protection Device (Communication System) |  | V1 | 0 | Approved | Updated review status
CLOSED | 1258 | 522803-01-RFAM-EL-0047-002_Color Code for LV Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 4, 2024 9:33 AM | Apr 23, 2024 5:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0047-002_Color Code for LV Switchboard.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0047-002_Color Code for LV Switchboard |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 23, 2024 5:02 PM): The sample is a bit different from the AIS business card, so GSA accept this sample color.
CLOSED | 1257 | 522803-01-RFAM-EL-0026-002_LV Circuit Breaker | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 4, 2024 9:33 AM | Jun 6, 2024 11:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0026-002_LV Circuit Breaker.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0026-002_LV Circuit Breaker |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1256 | 522803-01-RFAM-EL-0025-002_Power Metering | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Apr 4, 2024 9:32 AM | Apr 22, 2024 1:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0025-002_Power Metering.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0025-002_Power Metering |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 22, 2024 1:49 PM): please up to date SLD before production
CLOSED | 1250 | 522803-01-RFAM-ST-0035-002_Mix design concrete of PC panel of C.post | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 3, 2024 9:39 AM | Apr 5, 2024 4:45 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0035-002_Mix design concrete of PC panel of C.post.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0035-002_Mix design concrete of PC panel of C.post |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1243 | 522803-01-CAL-ST-0013-001_Calculation Sheet for Slab support 3rd-5th FL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 1, 2024 10:34 AM | Apr 5, 2024 4:41 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0013-001_Calculation Sheet for Slab support 3rd-5th FL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0013-001_Calculation Sheet for Slab support 3rd-5th FL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1242 | 522803-01-RPT-ST-0027-002_Tensile Test of Welded joint | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Apr 1, 2024 10:25 AM | Apr 5, 2024 4:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0027-002_Tensile Test of Welded joint.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0027-002_Tensile Test of Welded joint |  | V1 | 0 | Approved | Updated review status
CLOSED | 1240 | 522803-01-RFAM-ME-0012-004_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 30, 2024 8:41 AM | Apr 5, 2024 9:18 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-004_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-004_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1240 | 522803-01-RFAM-ME-0012-004_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 30, 2024 8:41 AM | Apr 5, 2024 9:18 AM | 2 | 0 | 2 | 100% | Review closed | 4 | CFD_time.mp4 | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-004_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1239 | 522803-01-RFAM-HY-0027-001_Submersible Pump for Retention Tank | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 30, 2024 8:09 AM | Apr 17, 2024 3:48 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0027-001_Submersible Pump for Retention Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0027-001_Submersible Pump for Retention Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1238 | 522803-01-RFAM-FP-0014-001_Painting | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 30, 2024 8:04 AM | Apr 5, 2024 9:19 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0014-001_Painting.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0014-001_Painting |  | V1 | 0 | Approved | Updated review status
CLOSED | 1229 | 522803-01-RFAM-ST-0039-002_Asphalt paper below road beam | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 29, 2024 8:20 AM | Apr 5, 2024 10:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0039-002_Asphalt paper below road beam.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0039-002_Asphalt paper below road beam |  | V1 | 0 | Approved | Updated review status
CLOSED | 1225 | 522803-01-RFAM-ME-0041-002_Balancing Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 28, 2024 11:01 AM | Apr 18, 2024 9:56 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0041-002_Balancing Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0041-002_Balancing Valve |  | V1 | 2 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Apr 17, 2024 5:17 PM): ME comment in attached file
CLOSED | 1224 | 522803-01-RFAM-ME-0044-001_Damper | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 28, 2024 10:49 AM | Apr 17, 2024 3:57 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0044-001_Damper.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0044-001_Damper |  | V1 | 6 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Apr 11, 2024 9:45 PM): ME comment in attached file
CLOSED | 1222 | 522803-01-ITP-MEP-0001-003_MEP Inspection Test Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Mar 28, 2024 8:43 AM | Apr 25, 2024 2:23 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ITP-MEP-0001-003_MEP Inspection Test Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-MEP-0001-003_MEP Inspection Test Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1219 | 522803-01-RFAM-ME-0043-001_BSP (Alternative) | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 27, 2024 11:25 AM | Apr 22, 2024 8:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0043-001_BSP (Alternative).PDF | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0043-001_BSP (Alternative) |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Apr 11, 2024 7:23 PM): ME comment in attached file
CLOSED | 1218 | 522803-01-RFAS-ST-0021-001_UNDERGROUND FUEL TANK 1 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 27, 2024 11:20 AM | Apr 5, 2024 11:09 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0021-001_UNDERGROUND FUEL TANK 1.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0021-001_UNDERGROUND FUEL TANK 1 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1216 | 522803-01-RFAM-ME-0027-002_Butterfly Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 27, 2024 10:57 AM | Apr 22, 2024 8:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0027-002_Butterfly Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0027-002_Butterfly Valve |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Apr 11, 2024 9:32 AM): ME comment in attached file
CLOSED | 1215 | 522803-01-RFAM-HY-0012-002_Fuel Tank Monitoring Panel | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 27, 2024 10:56 AM | Apr 10, 2024 9:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0012-002_Fuel Tank Monitoring Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0012-002_Fuel Tank Monitoring Panel |  | V1 | 0 | Approved | Updated review status
CLOSED | 1212 | 522803-01-RFAM-ST-0038-002_Canopy steel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 26, 2024 6:03 PM | Apr 1, 2024 6:15 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0038-002_Canopy steel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0038-002_Canopy steel |  | V1 | 0 | Approved | Updated review status
CLOSED | 1211 | 522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 3:12 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1211 | 522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 3:12 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0035-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1211 | 522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 3:12 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0035-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0035-001_COMBINE WALL LAYOUT L6 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1206 | 522803-01-RFAS-SE-0002-001_VSS SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:34 PM | Apr 4, 2024 3:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-SE-0002-001_VSS SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0002-001_VSS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1206 | 522803-01-RFAS-SE-0002-001_VSS SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:34 PM | Apr 4, 2024 3:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-SE-0002-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0002-001_VSS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1206 | 522803-01-RFAS-SE-0002-001_VSS SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:34 PM | Apr 4, 2024 3:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-SE-0002-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0002-001_VSS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1205 | 522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:32 PM | Apr 25, 2024 2:14 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1205 | 522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:32 PM | Apr 25, 2024 2:14 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0006-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1205 | 522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:32 PM | Apr 25, 2024 2:14 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0006-002_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-002_LTNG SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1204 | 522803-01-RFAS-EL-0004-003_MVSG SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:30 PM | Apr 5, 2024 11:01 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0004-003_MVSG SLD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-003_MVSG SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 5, 2024 10:59 PM): please note incoming 2A will prepare connection for Solar PQM meter and panel block out for install solar PQM
CLOSED | 1204 | 522803-01-RFAS-EL-0004-003_MVSG SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:30 PM | Apr 5, 2024 11:01 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0004-003_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-003_MVSG SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1204 | 522803-01-RFAS-EL-0004-003_MVSG SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 1:30 PM | Apr 5, 2024 11:01 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0004-003_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-003_MVSG SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1200 | 522803-01-RFAS-ME-0009-001_FLOOR OPENING | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 11:43 AM | Apr 29, 2024 9:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0009-001_FLOOR OPENING.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0009-001_FLOOR OPENING |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1200 | 522803-01-RFAS-ME-0009-001_FLOOR OPENING | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 11:43 AM | Apr 29, 2024 9:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0009-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0009-001_FLOOR OPENING |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1200 | 522803-01-RFAS-ME-0009-001_FLOOR OPENING | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 26, 2024 11:43 AM | Apr 29, 2024 9:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0009-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0009-001_FLOOR OPENING |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1199 | 522803-01-RFAS-ST-0018-002_PAVEMENT PLAN PART 5 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 26, 2024 8:45 AM | Apr 5, 2024 4:48 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0018-002_PAVEMENT PLAN PART 5.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0018-002_PAVEMENT PLAN PART 5 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1192 | 522803-01-RFAM-EL-0074-001_Rack_Accessories - ISMS ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 25, 2024 5:13 PM | Apr 22, 2024 5:52 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0074-001_Rack_Accessories - ISMS ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0074-001_Rack_Accessories - ISMS ECMS |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1191 | 522803-01-CAL-ST-0006-003_Calculation sheet of 2nd posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 25, 2024 4:45 PM | Apr 1, 2024 5:50 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0006-003_Calculation sheet of 2nd posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0006-003_Calculation sheet of 2nd posttension slab |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1184 | 522803-01-RFAM-EL-0075-001_Metallic Conduit (Alternative) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 23, 2024 8:45 AM | Mar 29, 2024 3:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0075-001_Metallic Conduit (Alternative).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0075-001_Metallic Conduit (Alternative) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1183 | 522803-01-RFAM-HY-0024-002_Underground Fuel Pipe (BSP) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 23, 2024 8:36 AM | Mar 28, 2024 8:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0024-002_Fuel Pipe (BSP).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0024-002_Fuel Pipe (BSP) |  | V1 | 0 | Approved | Updated review status
CLOSED | 1181 | 522803-01-RFAS-CV-0009-001_TYPICAL INSPECTION CHAMBER (INS) 02 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 22, 2024 6:25 PM | Mar 28, 2024 4:08 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0009-001_TYPICAL INSPECTION CHAMBER (INS) 02.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0009-001_TYPICAL INSPECTION CHAMBER (INS) 02 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1181 | 522803-01-RFAS-CV-0009-001_TYPICAL INSPECTION CHAMBER (INS) 02 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 22, 2024 6:25 PM | Mar 28, 2024 4:08 PM | 2 | 2 | 0 | 100% | Review closed | 4 | S-CV-0202-1 TYPICAL INSPECTION CHAMBER (INS) 02.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0009-001_TYPICAL INSPECTION CHAMBER (INS) 02 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1178 | 522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 22, 2024 4:47 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1178 | 522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 22, 2024 4:47 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0040-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1178 | 522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 22, 2024 4:47 PM | Apr 29, 2024 12:46 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0040-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0040-001_COMBINE WALL LAYOUT L3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1173 | 522803-01-RFAS-ST-0003-007_PAVEMENT PILING PLAN ALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 22, 2024 10:10 AM | Apr 10, 2024 9:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-007_PAVEMENT PILING PLAN ALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-007_PAVEMENT PILING PLAN ALL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1169 | 522803-01-RFAM-EL-0073-001_Cable Lug | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 8:04 PM | Mar 29, 2024 3:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0073-001_Cable Lug.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0073-001_Cable Lug |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 29, 2024 3:00 PM): refer TIA607C some ground bonding cable shall use two hole lug Could you please send two hole lug to approve material as well
CLOSED | 1168 | 522803-01-RFAM-EL-0070-001_Stud bolt | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 8:03 PM | Mar 25, 2024 4:31 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0070-001_Stud bolt.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0070-001_Stud bolt |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1167 | 522803-01-RFAM-EL-0061-002_Fire Stopping | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 8:03 PM | Apr 2, 2024 1:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0061-002_Fire Stopping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0061-002_Fire Stopping |  | V1 | 0 | Approved | Updated review status
CLOSED | 1156 | 522803-01-RPT-LE-0006-001_Monthly Report for LEED No.06 for March 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Mar 21, 2024 2:31 PM | Mar 28, 2024 11:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0006-001_Monthly Report for LEED No.06 for March 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0006-001_Monthly Report for LEED No.06 for March 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1154 | 522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:50 PM | Mar 26, 2024 2:03 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1154 | 522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:50 PM | Mar 26, 2024 2:03 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0043-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1154 | 522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:50 PM | Mar 26, 2024 2:03 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0043-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0043-001_COMBINE CEILING LAYOUT L4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1153 | 522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:48 PM | Apr 5, 2024 11:42 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 5, 2024 11:41 PM): MDF room PDU shall change to 2P 32A all branch circuit; if contractor have any concern for changing please let us know
CLOSED | 1153 | 522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:48 PM | Apr 5, 2024 11:42 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0042-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1153 | 522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:48 PM | Apr 5, 2024 11:42 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0042-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0042-001_LV SLD - PDU WITHIN MDF_MMR ROOM |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1152 | 522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:47 PM | Apr 2, 2024 1:13 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1152 | 522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:47 PM | Apr 2, 2024 1:13 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0041-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1152 | 522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 1:47 PM | Apr 2, 2024 1:13 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0041-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0041-001_COMBINE WALL LAYOUT L4 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1149 | 522803-01-RFAM-FP-0016-002_Fitting BSP | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 11:20 AM | Apr 1, 2024 9:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0016-002_Fitting BSP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0016-002_Fitting BSP |  | V1 | 0 | Approved | Updated review status
CLOSED | 1148 | 522803-01-RFAM-FP-0015-002_Fitting GSP_ HD-GSP | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 21, 2024 11:19 AM | Apr 1, 2024 9:01 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0015-002_Fitting GSP_ HD-GSP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0015-002_Fitting GSP_ HD-GSP |  | V1 | 0 | Approved | Updated review status
CLOSED | 1146 | 522803-01-CAL-ST-0010-001_Calculation of back propping for Mezzanine floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Mar 21, 2024 10:52 AM | Apr 5, 2024 10:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0010-001_Calculation of back propping for Mezzanine floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0010-001_Calculation of back propping for Mezzanine floor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1144 | 522803-01-RFAM-EL-0055-001_Miscellaneous (HDG for Data Hall) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 20, 2024 6:08 PM | Mar 29, 2024 2:53 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0055-001_Miscellaneous (HDG for Data Hall).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0055-001_Miscellaneous (HDG for Data Hall) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1143 | 522803-01-RFAM-ST-0039-001_Asphalt paper below road beam | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 4:26 PM | Mar 26, 2024 11:30 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0039-001_Asphalt paper below road beam.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0039-001_Asphalt paper below road beam |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1142 | 522803-01-RFAM-ST-0038-001_Canopy steel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 4:25 PM | Mar 26, 2024 11:29 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0038-001_Canopy steel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0038-001_Canopy steel |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1141 | 522803-01-RFAS-ST-0013-001_FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 3:49 PM | Apr 5, 2024 10:52 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0013-001 FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE).nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0013-001_FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1141 | 522803-01-RFAS-ST-0013-001_FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 3:49 PM | Apr 5, 2024 10:52 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0013-001_FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0013-001_FRAMING ELEVATION (LOCATION OF BASE PLATE FOR FACADE) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1137 | 522803-01-CAL-ST-0012-001_Calculation sheet of 3rd posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 9:02 AM | Apr 5, 2024 10:22 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0012-001_Calculation sheet of 3rd posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0012-001_Calculation sheet of 3rd posttension slab |  | V2 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1136 | 522803-01-CAL-ST-0006-002_Calculation sheet of 2nd posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 20, 2024 8:59 AM | Mar 22, 2024 1:19 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0006-002_Calculation sheet of 2nd posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0006-002_Calculation sheet of 2nd posttension slab |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1133 | 522803-01-RFAM-EL-0034-003_Battery Charging Unit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 19, 2024 1:31 PM | Mar 29, 2024 2:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0034-003_Battery Charging Unit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0034-003_Battery Charging Unit |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1132 | 522803-01-CAL-ST-0011-001_Calculation sheet for Change sizing of RC Beam Number 1BB03 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 19, 2024 1:17 PM | Mar 22, 2024 1:19 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0011-001_Calculation sheet for Change sizing of RC Beam Number 1BB03.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0011-001_Calculation sheet for Change sizing of RC Beam Number 1BB03 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1131 | 522803-01-CAL-ST-0009-001_Calculation Sheet for Slab support 2 FL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 19, 2024 10:09 AM | Mar 26, 2024 11:16 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0009-001_Calculation Sheet for Slab support 2 FL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0009-001_Calculation Sheet for Slab support 2 FL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1130 | 522803-01-CAL-ST-0008-001_Calculation Crab System support Beam and Slab for 2 fl. High Zone | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 19, 2024 8:45 AM | Apr 5, 2024 8:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0008-001_Calculation Crab System support Beam and Slab for 2 fl. High Zone.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0008-001_Calculation Crab System support Beam and Slab for 2 fl. High Zone |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1129 | 522803-01-RFAS-ST-0020-001_PAVEMENT PLAN PART 1,2,3 and PART 3-1 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 18, 2024 3:30 PM | Apr 10, 2024 9:58 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0020-001_PAVEMENT PLAN PART 1,2,3 and PART 3-1.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0020-001_PAVEMENT PLAN PART 1,2,3 and PART 3-1 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1126 | 522803-01-MS-CSA-0005-004_Method statement of soil protection work and excavation for exterior works. | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 5:56 PM | Apr 5, 2024 10:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0005-004_Method statement of soil protection work and excavation for exterior works..pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0005-004_Method statement of soil protection work and excavation for exterior works |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1125 | 522803-01-RFAS-ST-0018-001_PAVEMENT PLAN PART 5 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 5:41 PM | Mar 26, 2024 12:32 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0018-001_PAVEMENT PLAN PART 5.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0018-001_PAVEMENT PLAN PART 5 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1124 | 522803-01-RFAM-ST-0036-001_Chemical stud bolt for louver frame | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 5:18 PM | Mar 22, 2024 1:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0036-001_Chemical stud bolt for louver frame.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0036-001_Chemical stud bolt for louver frame |  | V1 | 0 | Approved | Updated review status
CLOSED | 1123 | 522803-01-RFAM-ST-0037-001_Anchor bolt for structure support louver frame | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 3:55 PM | Mar 22, 2024 1:34 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0037-001_Anchor bolt for structure support louver frame.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0037-001_Anchor bolt for structure support louver frame |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1119 | 522803-01-RFAS-HY-0022-001_FCS L1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 15, 2024 2:02 PM | Mar 28, 2024 8:50 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0022-001_FCS L1G.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0022-001_FCS L1G |  | V1 | 0 | Approved | Updated review status
CLOSED | 1119 | 522803-01-RFAS-HY-0022-001_FCS L1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 15, 2024 2:02 PM | Mar 28, 2024 8:50 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0022-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0022-001_FCS L1G |  | V1 | 0 | Approved | Updated review status
CLOSED | 1119 | 522803-01-RFAS-HY-0022-001_FCS L1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 15, 2024 2:02 PM | Mar 28, 2024 8:50 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0022-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0022-001_FCS L1G |  | V1 | 0 | Approved | Updated review status
CLOSED | 1118 | 522803-01-MS-EL-0017-001_Street Light | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Mar 15, 2024 1:47 PM | Mar 19, 2024 10:32 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0017-001_Street Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0017-001_Street Light |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1116 | 522803-01-RFAM-EL-0021-002_LV Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 15, 2024 1:08 PM | Apr 6, 2024 12:03 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0021-002_LV Switchboard.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0021-002_LV Switchboard |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Apr 6, 2024 12:03 AM): - Missing Item 8.10.16 in Comply table please declare - Shop drawing does not indicate ERMS function as well please declare before production - if supplier would like to do the work different with IFC drawing and specification please send RFI to approval first - Request change sizing of circuit breaker for Solar panel DB and EV charger DB please see in attached file - please create comment table for tracking and how to respond the comment in next submission
CLOSED | 1112 | 522803-01-RPT-ST-0022-002_Trial mix report of Cpac 1Feb24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 9:20 AM | Mar 20, 2024 8:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0022-002_Trial mix report of Cpac 1Feb24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0022-002_Trial mix report of Cpac 1Feb24 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1111 | 522803-01-RFAM-ST-0035-001_Mix design concrete of PC panel of C.post | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 15, 2024 9:12 AM | Mar 22, 2024 1:31 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0035-001_Mix design concrete of PC panel of C.post.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0035-001_Mix design concrete of PC panel of C.post |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1110 | 522803-01-RPT-ST-0021-002_Trial mix report of ORC11Jan24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 14, 2024 3:55 PM | Mar 20, 2024 8:37 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0021-002_Trial mix report of ORC11Jan24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0021-002_Trial mix report of ORC11Jan24 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1108 | 522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 1:29 PM | Mar 25, 2024 5:04 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1108 | 522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 1:29 PM | Mar 25, 2024 5:04 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0030-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1108 | 522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 1:29 PM | Mar 25, 2024 5:04 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0030-001_RVT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0030-001_COMBINE PIPE_CONDUIT UG |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1107 | 522803-01-RFAM-ME-0031-002_Motorized Damper | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 1:21 PM | Apr 22, 2024 8:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0031-002_Motorized Damper.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0031-002_Motorized Damper |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Apr 11, 2024 9:43 AM): ME reviewed in attached file
CLOSED | 1105 | 522803-01-RFAM-EL-0059-003_Push-In Wire Connector | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 9:24 AM | Mar 26, 2024 2:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0059-003_Push-In Wire Connector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0059-003_Push-In Wire Connector |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1104 | 522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 9:18 AM | May 2, 2024 3:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1104 | 522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 9:18 AM | May 2, 2024 3:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0031-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1104 | 522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 14, 2024 9:18 AM | May 2, 2024 3:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0031-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0031-001_LIGHTING L1G CHILLER PLANT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1103 | 522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 14, 2024 8:50 AM | Mar 26, 2024 11:13 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1103 | 522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 14, 2024 8:50 AM | Mar 26, 2024 11:13 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL_DC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0007-001_Calculation sheet for slab support _MFL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1096 | 522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B |  | V1 | 0 | Approved | Updated review status
CLOSED | 1096 | 522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0021-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B |  | V1 | 0 | Approved | Updated review status
CLOSED | 1096 | 522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0021-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0021-001_FUEL PUMP ROOM SIDE B |  | V1 | 0 | Approved | Updated review status
CLOSED | 1095 | 522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:29 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A |  | V1 | 0 | Approved | Updated review status
CLOSED | 1095 | 522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:29 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0020-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A |  | V1 | 0 | Approved | Updated review status
CLOSED | 1095 | 522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 5:09 PM | Mar 25, 2024 11:29 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0020-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0020-001_FUEL PUMP ROOM SIDE A |  | V1 | 0 | Approved | Updated review status
CLOSED | 1094 | 522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:54 PM | Mar 29, 2024 2:25 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1094 | 522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:54 PM | Mar 29, 2024 2:25 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0002-003_DWG.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1094 | 522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:54 PM | Mar 29, 2024 2:25 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0002-003_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-003_FIRE PUMP ROOM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1093 | 522803-01-RFAS-HY-0017-002_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:47 PM | Mar 28, 2024 8:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0017-002_FUEL TANK A and B.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-002_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1093 | 522803-01-RFAS-HY-0017-002_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:47 PM | Mar 28, 2024 8:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0017-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-002_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1093 | 522803-01-RFAS-HY-0017-002_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 4:47 PM | Mar 28, 2024 8:31 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0017-002_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-002_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1090 | 522803-01-RPT-LE-0005-002_Monthly Report for LEED No.05 for February 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 13, 2024 3:23 PM | Mar 20, 2024 1:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0005-002_Monthly Report for LEED No.05 for February 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0005-002_Monthly Report for LEED No.05 for February 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1089 | 522803-01-RFAS-HY-0015-002_FUEL CONTROL UG | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:45 PM | Mar 28, 2024 8:39 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0015-002_FUEL CONTROL UG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-002_FUEL CONTROL UG |  | V1 | 0 | Approved | Updated review status
CLOSED | 1089 | 522803-01-RFAS-HY-0015-002_FUEL CONTROL UG | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:45 PM | Mar 28, 2024 8:39 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0015-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-002_FUEL CONTROL UG |  | V1 | 0 | Approved | Updated review status
CLOSED | 1089 | 522803-01-RFAS-HY-0015-002_FUEL CONTROL UG | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:45 PM | Mar 28, 2024 8:39 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0015-002_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-002_FUEL CONTROL UG |  | V1 | 0 | Approved | Updated review status
CLOSED | 1088 | 522803-01-RFAS-EL-0039-001_LTNG L2 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:00 PM | Mar 19, 2024 10:28 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0039-001_LTNG L2.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0039-001_LTNG L2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1088 | 522803-01-RFAS-EL-0039-001_LTNG L2 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:00 PM | Mar 19, 2024 10:28 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0039-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0039-001_LTNG L2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1088 | 522803-01-RFAS-EL-0039-001_LTNG L2 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 13, 2024 2:00 PM | Mar 19, 2024 10:28 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0039-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0039-001_LTNG L2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1087 | 522803-01-RFAS-CV-0008-001_TYPICAL INSPECTION CHAMBER (INS) 01 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 13, 2024 1:41 PM | Mar 26, 2024 12:28 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0008-001_TYPICAL INSPECTION CHAMBER (INS) 01.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0008-001_TYPICAL INSPECTION CHAMBER (INS) 01 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1083 | 522803-01-RPT-ST-0027-001_Tensile Test of Welded joint | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 13, 2024 9:57 AM | Mar 14, 2024 9:22 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0027-001_Tensile Test of Welded joint.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0027-001_Tensile Test of Welded joint |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 1082 | 522803-01-RPT-ST-0026-001_Report of Tensile Test of Steel | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 13, 2024 9:55 AM | Mar 14, 2024 9:23 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0026-001_Report of Tensile Test of Steel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0026-001_Report of Tensile Test of Steel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1081 | 522803-01-RFAS-ST-0015-002_MAZZANINE FLOOR FRAMING PLAN_POST TENSION PLAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 12, 2024 4:53 PM | Mar 22, 2024 1:38 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0015-002_MAZZANINE FLOOR FRAMING PLAN_POST TENSION PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0015-002_MAZZANINE FLOOR FRAMING PLAN_POST TENSION PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1077 | 522803-01-RPT-ST-0025-001_Report of Concrete compression Test_Nov-Dec 23-Insee | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 12, 2024 11:18 AM | Mar 26, 2024 12:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0025-001_Report of Concrete compression Test_Nov-Dec 23-Insee.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0025-001_Report of Concrete compression Test_Nov-Dec 23-Insee |  | V1 | 0 | Approved | Updated review status
CLOSED | 1076 | 522803-01-RPT-ST-0024-001_Report of Concrete compression Test_Nov-Dec 23-M-concrete | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 12, 2024 11:16 AM | Mar 26, 2024 12:37 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0024-001_Report of Concrete compression Test_Nov-Dec 23-M-concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0024-001_Report of Concrete compression Test_Nov-Dec 23-M-concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 1073 | 522803-01-RFAM-EL-0024-002_Public Address System | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 12, 2024 8:28 AM | Apr 2, 2024 1:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0024-002_Public Address System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0024-002_Public Address System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1070 | 522803-01-RFAS-CV-0007-001_FENCE PLAN PART 3-1 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 11, 2024 6:37 PM | Mar 26, 2024 12:27 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0007-001_FENCE PLAN PART 3-1.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0007-001_FENCE PLAN PART 3-1 |  | V2 | 0 | Approved | Updated review status
CLOSED | 1069 | 522803-01-RPT-ST-0023-001_Trial mix report of Insee concrete on 5Jan24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 11, 2024 4:15 PM | Mar 14, 2024 9:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0023-001_Trial mix report of Insee concrete on 5Jan24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0023-001_Trial mix report of Insee concrete on 5Jan24 |  | V1 | 0 | Approved | Updated review status
CLOSED | 1068 | 522803-01-RFAM-ST-0034-001_Topping concrete of ORC | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 11, 2024 4:10 PM | Mar 26, 2024 3:23 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0034-001_Topping concrete of ORC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0034-001_Topping concrete of ORC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1064 | 522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 11, 2024 10:27 AM | Apr 3, 2024 10:26 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1064 | 522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 11, 2024 10:27 AM | Apr 3, 2024 10:26 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0008-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1064 | 522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 11, 2024 10:27 AM | Apr 3, 2024 10:26 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0008-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0008-001_DUCT LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1063 | 522803-01-CAL-ST-0005-002_Calculation of Post Tensioned Slab for Mezzanine Floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 11, 2024 8:39 AM | Mar 22, 2024 1:12 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0005-002_Calculation of Post Tensioned Slab for Mezzanine Floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0005-002_Calculation of Post Tensioned Slab for Mezzanine Floor |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1062 | 522803-01-RFAM-HY-0007-002_Booster and Transfer Pump | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 11, 2024 8:00 AM | Mar 25, 2024 10:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0007-002_Booster and Transfer Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0007-002_Booster and Transfer Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 1060 | 522803-01-RFAS-ST-0014-002_CANOPY DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 11, 2024 7:44 AM | Mar 22, 2024 1:36 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0014-002_CANOPY DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0014-002_CANOPY DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1058 | 522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:20 PM | Mar 19, 2024 10:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1058 | 522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:20 PM | Mar 19, 2024 10:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0038-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1058 | 522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:20 PM | Mar 19, 2024 10:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0038-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0038-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 5 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1057 | 522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:19 PM | Apr 2, 2024 1:04 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1057 | 522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:19 PM | Apr 2, 2024 1:04 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0037-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1057 | 522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:19 PM | Apr 2, 2024 1:04 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0037-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0037-001_LIGHTNING PROTECTION SYSTEM LAYOUT - LEVEL 3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1056 | 522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:17 PM | Mar 19, 2024 10:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1056 | 522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:17 PM | Mar 19, 2024 10:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0036-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1056 | 522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:17 PM | Mar 19, 2024 10:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0036-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0036-001_LIGHTNING PROTECTION SYSTEM LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1055 | 522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:13 PM | Mar 29, 2024 1:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1055 | 522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:13 PM | Mar 29, 2024 1:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-SE-0001-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1055 | 522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:13 PM | Mar 29, 2024 1:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-SE-0001-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1152_RFAS-SE_Request for Approval Shop Drawings (Security)/522803-01-RFAS-SE-0001-001_ACCESS CONTROL SYSTEM (ACS) SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1054 | 522803-01-RFAM-EL-0072-001_Cable Tags and Cable Ties | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 3:00 PM | Mar 26, 2024 2:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0072-001_Cable Tags and Cable Ties.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0072-001_Cable Tags and Cable Ties |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1053 | 522803-01-RFAM-EL-0060-002_Modular support | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 2:58 PM | Apr 2, 2024 1:07 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0060-002_Modular support.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0060-002_Modular support |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1051 | 522803-01-RFAS-HY-0002-001_MASTER LAYOUT | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 8:12 AM | Mar 28, 2024 8:44 AM | 4 | 4 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0002-001_MASTER LAYOUT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0002-001_MASTER LAYOUT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1051 | 522803-01-RFAS-HY-0002-001_MASTER LAYOUT | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 8:12 AM | Mar 28, 2024 8:44 AM | 4 | 4 | 0 | 100% | Review closed | 4 | RFAS-HY-0002-001_DWG.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0002-001_MASTER LAYOUT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1051 | 522803-01-RFAS-HY-0002-001_MASTER LAYOUT | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 8:12 AM | Mar 28, 2024 8:44 AM | 4 | 4 | 0 | 100% | Review closed | 4 | RFAS-HY-0002-001_NWC.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0002-001_MASTER LAYOUT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1051 | 522803-01-RFAS-HY-0002-001_MASTER LAYOUT | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 9, 2024 8:12 AM | Mar 28, 2024 8:44 AM | 4 | 4 | 0 | 100% | Review closed | 4 | RFAS-HY-0002-001_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0002-001_MASTER LAYOUT |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1050 | 522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 8, 2024 6:24 PM | Apr 10, 2024 9:23 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1050 | 522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 8, 2024 6:24 PM | Apr 10, 2024 9:23 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-ME-0007-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1050 | 522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 8, 2024 6:24 PM | Apr 10, 2024 9:23 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-ME-0007-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0007-001_CHW SYSTEM - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1043 | 522803-01-RPT-ST-0021-001_Trial mix report of ORC11Jan24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 8, 2024 11:49 AM | Mar 14, 2024 9:26 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0021-001_Trial mix report of ORC11Jan24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0021-001_Trial mix report of ORC11Jan24 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1042 | 522803-01-RPT-ST-0022-001_Trial mix report of Cpac 1Feb24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 8, 2024 10:34 AM | Mar 14, 2024 9:27 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0022-001_Trial mix report of Cpac 1Feb24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0022-001_Trial mix report of Cpac 1Feb24 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1040 | 522803-01-RFA-LE-0005-001_COC and water testing data | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 8, 2024 9:06 AM | Mar 14, 2024 10:05 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-LE-0005-001_COC and water testing data.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0005-001_COC and water testing data |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1038 | 522803-01-RFAM-HY-0022-002_Sand Filter_Water Softener | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 7, 2024 3:11 PM | Mar 25, 2024 10:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0022-002_Sand Filter_Water Softener.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0022-002_Sand Filter_Water Softener |  | V1 | 0 | Approved | Updated review status
CLOSED | 1035 | 522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 7, 2024 2:25 PM | Mar 18, 2024 9:32 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1035 | 522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 7, 2024 2:25 PM | Mar 18, 2024 9:32 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0029-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1035 | 522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 7, 2024 2:25 PM | Mar 18, 2024 9:32 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0029-001_RVT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0029-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT (BUILDING) - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1034 | 522803-00-RFAS-CV-0004-002_FOUNDATION FENCE PART-6_7_8-SECTION FENCE PART-7_8 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 7, 2024 11:44 AM | Mar 26, 2024 3:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0004-002_FOUNDATION FENCE PART-6_7_8-SECTION FENCE PART-7_8.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0004-002_FOUNDATION FENCE PART-6_7_8-SECTION FENCE PART-7_8 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1033 | 522803-01-RPT-ST-0020-001_Trial mix report of ORC19Jan24 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 7, 2024 11:06 AM | Mar 14, 2024 9:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0020-001_Trial mix report of ORC19Jan24.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0020-001_Trial mix report of ORC19Jan24 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1032 | 522803-01-RPT-HSE-0004-001_Result of environmental monitoring_No.4_(16-Jan-15-Feb-24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 7, 2024 10:13 AM | Mar 14, 2024 8:07 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0004-001_Result of environmental monitoring_No.4_(16-Jan-15-Feb-24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0004-001_Result of environmental monitoring_No.4_(16-Jan-15-Feb-24) |  | V2 | 0 | Approved | Updated review status
CLOSED | 1031 | 522803-01-RPT-HSE-0003-001_Result of environmental monitoring_No.3_(16-Dec-23-15-Jan-24) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 7, 2024 10:12 AM | Mar 14, 2024 8:09 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0003-001_Result of environmental monitoring_No.3_(16-Dec-23-15-Jan-24).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0003-001_Result of environmental monitoring_No.3_(16-Dec-23-15-Jan-24) |  | V2 | 0 | Approved | Updated review status
CLOSED | 1026 | 522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 6, 2024 5:08 PM | Mar 29, 2024 2:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1026 | 522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 6, 2024 5:08 PM | Mar 29, 2024 2:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0034-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1026 | 522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 6, 2024 5:08 PM | Mar 29, 2024 2:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0034-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0034-001_DC SUPPLY SCHEMATIC FOR LV SWITCHBOARD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1024 | 522803-01-MS-ST-0005-001_MS_Safety-Quality Procedure of Super Structure Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 6, 2024 3:32 PM | Mar 26, 2024 11:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0005-001_MS_Safety-Quality Procedure of Super Structure Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0005-001_Method Statement_Safety_Quality Procedure of Super Structure Work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1022 | 522803-01-CAL-ST-0006-001_Calculation sheet of 2nd Posttension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 6, 2024 2:49 PM | Mar 20, 2024 7:57 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CAL-ST-0006-001_Calculation sheet of 2nd Posttension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0006-001_Calculation sheet of 2nd Post tension slab |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1020 | 522803-01-MRPT-GEN-0005-001_TTI Monthly Construction No.05_February 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 6, 2024 1:28 PM | Mar 7, 2024 12:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0005-001_TTI Monthly Construction No.05_February 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0005-001_TTI Monthly Construction No.05_February 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1015 | 522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:16 PM | Mar 22, 2024 10:47 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1015 | 522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:16 PM | Mar 22, 2024 10:47 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0033-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1015 | 522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:16 PM | Mar 22, 2024 10:47 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0033-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0033-001_DC SUPPLY SCHEMATIC FOR MV SWITCHGEAR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1014 | 522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:11 PM | Apr 2, 2024 1:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 2, 2024 1:08 AM): As BIM meeting discussed please use top reference line to align any switch in the same reference
CLOSED | 1014 | 522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:11 PM | Apr 2, 2024 1:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0032-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1014 | 522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 2:11 PM | Apr 2, 2024 1:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0032-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0032-001_COMBINE WALL LAYOUT - MEZZANINE FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1013 | 522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 1:44 PM | Mar 22, 2024 4:27 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1013 | 522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 1:44 PM | Mar 22, 2024 4:27 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0003-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1013 | 522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 1:44 PM | Mar 22, 2024 4:27 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0003-001_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0003-001_Fire Protection System Layout - UG |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 1010 | 522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 10:07 AM | Mar 29, 2024 2:12 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1010 | 522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 10:07 AM | Mar 29, 2024 2:12 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0014-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1010 | 522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 10:07 AM | Mar 29, 2024 2:12 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0014-002_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-002_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1007 | 522803-01-RFAM-FP-0012-002_Gas Suppression System (IG-100) | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 5, 2024 9:32 AM | Mar 27, 2024 4:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0012-002_Gas Suppression System (IG-100).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0012-002_Gas Suppression System (IG-100) |  | V1 | 0 | Approved | Updated review status
CLOSED | 1003 | 522803-01-MS-HY-0010-001_Electrical Work Fuel Control System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Mar 4, 2024 4:45 PM | Mar 25, 2024 9:30 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0010-001_Electrical Work Fuel Control System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0010-001_Electrical Work Fuel Control System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1001 | 522803-01-RFAM-ST-0033-001_Repair corner crack at PC panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 4, 2024 4:12 PM | Mar 14, 2024 8:11 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0033-001_Repair corner crack at PC panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0033-001_Repair corner crack at PC panel |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 1000 | 522803-01-RFAM-ME-0035-001_Pre-Cooled Air Handling Unit | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 4, 2024 3:36 PM | Mar 28, 2024 8:21 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0035-001_Pre-Cooled Air Handling Unit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0035-001_Pre-Cooled Air Handling Unit |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(Mar 13, 2024 5:40 PM): ME comment in attached file.
CLOSED | 999 | 522803-01-RFAM-EL-0067-001_Riser Pole Communication System | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 4, 2024 2:14 PM | Mar 14, 2024 11:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0067-001_Riser Pole Communication System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0067-001_Riser Pole Communication System |  | V1 | 0 | Approved | Updated review status
CLOSED | 998 | 522803-01-RFAM-EL-0031-002_Riser Pole Incoming | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 4, 2024 2:09 PM | Mar 14, 2024 11:14 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0031-002_Riser Pole Incoming.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0031-002_Riser Pole Incoming |  | V1 | 0 | Approved | Updated review status
CLOSED | 997 | 522803-01-RFAM-EL-0014-002_Load Break Switch | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 4, 2024 2:07 PM | Mar 19, 2024 10:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0014-002_Load Break Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0014-002_Load Break Switch |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 995 | 522803-01-RPT-LE-0005-001_Monthly Report for LEED No.05 for February 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 4, 2024 9:30 AM | Mar 8, 2024 7:03 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-LE-0005-001_Monthly Report for LEED No.05 for February 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0005-001_Monthly Report for LEED No.05 for February 2024 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 993 | 522803-01-RFAM-ST-0031-001_Welding rod for PC work | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 2, 2024 10:36 AM | Mar 8, 2024 9:34 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0031-001_Welding rod for PC work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0031-001_Welding rod for PC work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 992 | 522803-01-RFAM-ME-0005-003_CHW, CDW Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 9:30 AM | Apr 10, 2024 9:17 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0005-003_CHW, CDW Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0005-003_CHW, CDW Pump |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Mar 13, 2024 10:35 AM): ME reviewed.
CLOSED | 991 | 522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:59 AM | Mar 25, 2024 9:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 |  | V1 | 0 | Approved | Updated review status
CLOSED | 991 | 522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:59 AM | Mar 25, 2024 9:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-FP-0005-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 |  | V1 | 0 | Approved | Updated review status
CLOSED | 991 | 522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:59 AM | Mar 25, 2024 9:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-FP-0005-001_CORE WALL STAIR 1, 2, 3, 4, (2024-02-07) NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0005-001_FH RISER ST 1,2,3,4 |  | V1 | 0 | Approved | Updated review status
CLOSED | 990 | 522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:44 AM | Mar 25, 2024 10:16 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 990 | 522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:44 AM | Mar 25, 2024 10:16 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0001-002_ CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 990 | 522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Mar 2, 2024 8:44 AM | Mar 25, 2024 10:16 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0001-002_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0001-002_WATER SUPPLY UG and WASTEWATER 1G |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 987 | 522803-01-RFAM-ST-0032-001_Repair small crack at PC panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 1, 2024 5:17 PM | Mar 8, 2024 11:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0032-001_Repair small crack at PC panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0032-001_Repair small crack at PC panel |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 986 | 522803-01-RFAM-ST-0029-001_Topping concrete of Namheng | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 1, 2024 4:01 PM | Mar 8, 2024 9:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0029-001_Topping concrete of Namheng.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0029-001_Topping concrete of Namheng |  | V1 | 0 | Approved | Updated review status
CLOSED | 985 | 522803-01-RFAM-ST-0030-001_Anti-rust paint at PC steel plate | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 1, 2024 1:53 PM | Mar 14, 2024 9:33 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0030-001_Anti-rust paint at PC steel plate.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0030-001_Anti-rust paint at PC steel plate |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 984 | 522803-01-MS-ST-0004-001_Testing method of PC welding joint | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Mar 1, 2024 1:27 PM | Mar 20, 2024 8:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0004-001_Testing method of PC welding joint.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0004-001_Testing method of PC welding joint |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 979 | 522803-01-MS-HY-0002-002_Non-Metallic Pipes Connection | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 29, 2024 2:00 PM | Mar 27, 2024 2:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0002-002_Non-Metallic Pipes Connection.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0002-002_Non-Metallic Pipes Connection |  | V1 | 0 | Approved | Updated review status
CLOSED | 978 | 522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 29, 2024 1:38 PM | Mar 29, 2024 2:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 978 | 522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 29, 2024 1:38 PM | Mar 29, 2024 2:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0019-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 978 | 522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 29, 2024 1:38 PM | Mar 29, 2024 2:20 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0019-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0019-001_LOAD BANK DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 975 | 522803-01-RFAM-SE-0001-001_Security System | (TTI) Request for Approval (AUR_Security Team Review) - Main Contractor | sansamon s | -- | -- | Feb 29, 2024 11:37 AM | Apr 17, 2024 9:56 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-SE-0001-001_Security System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1172_RFAM-SE_Request for Approval Material (Security)/522803-01-RFAM-SE-0001-001_Security System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 971 | 522803-01-RFAS-ST-0017-001_WET GARBAGE BUILDING | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 29, 2024 9:44 AM | Mar 20, 2024 8:34 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0017-001_WET GARBAGE BUILDING.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0017-001_WET GARBAGE BUILDING |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 962 | 522803-01-RFAS-CV-0006-001_FENCE PLAN PART 7 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 28, 2024 10:24 AM | Mar 20, 2024 8:32 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0006-001_FENCE PLAN PART 7.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0006-001_FENCE PLAN PART 7 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 961 | 522803-01-RFAM-ST-0028-001_Topping concrete of Siam city | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 28, 2024 9:56 AM | Mar 4, 2024 9:12 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0028-001_Topping concrete of Siam city.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0028-001_Topping concrete of Siam city |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 958 | 522803-01-RFAM-EL-0023-002_Transfer Switches | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 28, 2024 9:28 AM | Mar 19, 2024 1:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0023-002_Transfer Switches.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0023-002_Transfer Switches |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 19, 2024 1:58 PM): How to ACG-150 control Neutral delay? please attached the diagram, logic control remind: Fuji answer ACG-150 can programmable and control delay
CLOSED | 957 | 522803-01-RFAM-EL-0065-001_ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 27, 2024 5:39 PM | Apr 5, 2024 9:00 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0065-001_ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0065-001_ECMS |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 956 | 522803-01-RFAM-EL-0033-002_Power Distribution Unit (PDU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 27, 2024 5:38 PM | Apr 9, 2024 2:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0033-002_Power Distribution Unit (PDU).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0033-002_Power Distribution Unit (PDU) |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Apr 9, 2024 2:05 PM): MDF room PDU shall change branch circuit to 2P 32A
CLOSED | 954 | 522803-01-RFAM-EL-0061-001_Fire Stopping | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 27, 2024 2:29 PM | Mar 13, 2024 11:03 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0061-001_Fire Stopping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0061-001_Fire Stopping |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 949 | 522803-01-MS-EL-0009-001_MV Cable Termination work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 27, 2024 10:21 AM | Mar 7, 2024 11:11 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0009-001_MV Cable Termination work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0009-001_MV Cable Termination work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 947 | 522803-01-MS-HY-0004-001_Underground Fuel Piping | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 27, 2024 10:12 AM | Mar 11, 2024 4:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0004-001_Underground Fuel Piping.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0004-001_Underground Fuel Piping |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 940 | 522803-01-PGM-GEN-0001-002_Master Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 23, 2024 6:52 PM | Mar 25, 2024 1:22 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-PGM-GEN-0001-002_Master Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-002_Master Schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 939 | 522803-01-RFAM-ME-0030-002_Fuel_Water Leak Detector | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 23, 2024 5:47 PM | Mar 6, 2024 3:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0030-002_Fuel_Water Leak Detector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0030-002_Fuel_Water Leak Detector |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Feb 28, 2024 2:48 PM): ME commented in attached file.
CLOSED | 937 | 522803-01-RFAM-EL-0048-002_Lighting Fixture | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 23, 2024 4:59 PM | Mar 14, 2024 11:04 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0048-002_Lighting Fixture.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0048-002_Lighting Fixture |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 14, 2024 11:04 PM): Please follow AUR's comment, TTI shall send Simulation at least in data hall 2nd floor in the first stage and simulation for all room TTI can submit later
CLOSED | 936 | 522803-01-RFAM-ST-0027-001_Steel structure supplier | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 23, 2024 4:57 PM | Mar 4, 2024 9:15 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0027-001_Steel structure supplier.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0027-001_Steel structure supplier |  | V1 | 0 | Approved | Updated review status
CLOSED | 935 | 522803-01-RFAM-EL-0044-002_Street Light | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 23, 2024 4:52 PM | Mar 11, 2024 9:50 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0044-002_Street Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0044-002_Street Light |  | V1 | 0 | Disapproved | Updated review status
CLOSED | 934 | 522803-01-RFAM-EL-0027-002_Low Voltage Current Transformer | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 23, 2024 4:50 PM | Mar 14, 2024 10:57 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0027-002_Low Voltage Current Transformer.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0027-002_Low Voltage Current Transformer |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 933 | 522803-01-RFAS-ST-0014-001_CANOPY DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 23, 2024 3:12 PM | Mar 8, 2024 3:07 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0014-001_CANOPY DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0014-001_CANOPY DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 931 | 522803-01-CAL-ST-0005-001_Calculation of Post Tensioned Slab for Mezzanine Floor | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 23, 2024 1:25 PM | Mar 8, 2024 3:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0005-001_Calculation of Post Tensioned Slab for Mezzanine Floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0005-001_Calculation of Post Tensioned Slab for Mezzanine Floor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 925 | 522803-01-RFAM-ST-0024-002_Fireproof paint | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 23, 2024 9:56 AM | Mar 20, 2024 8:43 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0024-002_Fireproof paint.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0024-002_Fireproof paint |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 921 | 522803-01-RFAS-ST-0015-001_MAZZANINE FLOOR FRAMING PLAN, POST TENSION PLAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 22, 2024 2:30 PM | Mar 8, 2024 3:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0015-001_MAZZANINE FLOOR FRAMING PLAN, POST TENSION PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0015-001_MAZZANINE FLOOR FRAMING PLAN, POST TENSION PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 920 | 522803-01-RFAM-EL-0059-002_Push-In Wire Connector | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 22, 2024 10:45 AM | Mar 8, 2024 12:31 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0059-002_Push-In Wire Connector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0059-002_Push-In Wire Connector |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 919 | 522803-01-RFAM-EL-0057-002_Grounding Joint Cover for Ground Rack in Data Hall | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 22, 2024 10:43 AM | Mar 14, 2024 11:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0057-002_Grounding Joint Cover for Ground Rack in Data Hall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0057-002_Grounding Joint Cover for Ground Rack in Data Hall |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 14, 2024 11:10 PM): Please let us know the material inside H tap cover
CLOSED | 914 | 522803-01-RFAS-ST-0016-001_FACADE STRUCTURE DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 22, 2024 9:15 AM | Feb 29, 2024 2:38 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0016-001_FACADE STRUCTURE DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0016-001_FACADE STRUCTURE DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 913 | 522803-01-RFAM-EL-0062-001_Cable for ECMS | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 22, 2024 8:15 AM | Mar 18, 2024 1:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0062-001_Cable for ECMS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0062-001_Cable for ECMS |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 912 | 522803-01-RFAM-EL-0058-001_Network Rack and Accessories | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 22, 2024 8:09 AM | Apr 4, 2024 11:44 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0058-001_Network Rack and Accessories.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0058-001_Network Rack and Accessories |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 906 | 522803-01-RFAS-CV-0005-001 FENCE PLAN PART 4 & FOUNDATION FENCE PLAN PART 3,4 LEVEL GUTTER & DETAIL FOUNDATION FENCE TYPE 2 , 3A | (TTI) Request for Approval (AUR_Civil Team Review) - Main Contractor | nittaya p | -- | -- | Feb 21, 2024 11:03 AM | Mar 7, 2024 11:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0005-001 FENCE PLAN PART 4 & FOUNDATION FENCE PLAN PART 3,4 LEVEL GUTTER & DETAIL FOUNDATION FENCE TYPE 2 , 3A.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0005-001 FENCE PLAN PART 4 & FOUNDATION FENCE PLAN PART 3,4 LEVEL GUTTER & DETAIL FOUNDATION FENCE TYPE 2 , 3A |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 903 | 522803-01-CAL-ST-0004-001_Calculation temporary brace push pull prop for PC wall | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Feb 21, 2024 10:11 AM | Mar 7, 2024 11:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0004-001_Calculation temporary brace push pull prop for PC wall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0004-001_Calculation temporary brace push pull prop for PC wall |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 902 | 522803-01-RFAS-ST-0012-002 CORE WALL STAIR-04 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Feb 21, 2024 10:00 AM | Mar 4, 2024 9:40 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0012-002 CORE WALL STAIR-04 DETAIL.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0012-002_CORE WALL STAIR-04 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 902 | 522803-01-RFAS-ST-0012-002 CORE WALL STAIR-04 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Feb 21, 2024 10:00 AM | Mar 4, 2024 9:40 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0012-002 CORE WALL STAIR-04 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0012-002_CORE WALL STAIR-04 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 902 | 522803-01-RFAS-ST-0012-002 CORE WALL STAIR-04 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Feb 21, 2024 10:00 AM | Mar 4, 2024 9:40 AM | 3 | 3 | 0 | 100% | Review closed | 4 | AUTOCAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0012-002_CORE WALL STAIR-04 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 899 | 522803-01-RFA-HSE-0013-001_Night shift procedure | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 20, 2024 9:37 PM | Mar 7, 2024 12:29 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0013-001_Night shift procedure.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0013-001_Night shift procedure |  | V1 | 0 | Approved | Updated review status
CLOSED | 898 | 522803-01-RPT-ST-0019-001_Cold press coupler tensile | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 20, 2024 3:37 PM | Feb 29, 2024 2:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0019-001_Cold press coupler tensile .pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0019-001_Cold press coupler tensile |  | V1 | 0 | Approved | Updated review status
CLOSED | 892 | 522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 20, 2024 8:15 AM | Mar 5, 2024 6:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 5, 2024 6:26 PM): All CT to PQM class 0.2
CLOSED | 892 | 522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 20, 2024 8:15 AM | Mar 5, 2024 6:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0004-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 892 | 522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 20, 2024 8:15 AM | Mar 5, 2024 6:26 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0004-002_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-002_MV SWITCHGEAR - SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 891 | 522803-01-RFAM-EL-0068-001_LV Cable (For Earthing) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 20, 2024 8:13 AM | Mar 5, 2024 6:19 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0068-001_LV Cable (For Earthing).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0068-001_LV Cable (For Earthing) |  | V1 | 0 | Approved | Updated review status
CLOSED | 876 | 522803-01-MS-ME-0001-001_Insert Steel Plate Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 19, 2024 11:47 AM | Mar 11, 2024 6:09 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ME-0001-001_Insert Steel Plate Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1047_MS-ME_Request for Approval Method Statement (Mechanical)/522803-01-MS-ME-0001-001_Insert Steel Plate Installation |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 872 | 522803-01-RFAM-ME-0042-001_2 Way-Butterfly Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 19, 2024 9:05 AM | Mar 11, 2024 6:52 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0042-001_2 Way-Butterfly Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0042-001_2 Way-Butterfly Valve |  | V1 | 2 | Make correction as noted & proceed | Updated review status
CLOSED | 871 | 522803-01-RFAM-EL-0063-001_Surge Protection Device (Communication system) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 19, 2024 9:02 AM | Mar 3, 2024 9:57 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0063-001_Surge Protection Device (Communication system).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0063-001_Surge Protection Device (Communication system) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 870 | 522803-01-RFI-ME-0021-001_IP for VSD in MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 19, 2024 8:49 AM | Mar 11, 2024 6:31 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFI-ME-0021-001_IP for VSD in MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1247_RFI-ME_Request for Information (Mechanical)/522803-01-RFI-ME-0021-001_IP for VSD in MCC |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 26, 2024 11:14 AM): ME replied in attached file(Edited Feb 26, 2024 11:15 AM)
CLOSED | 868 | 522803-01-RFAM-HY-0025-001_Fitting GSP | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:46 AM | Feb 28, 2024 5:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0025-001_Fitting GSP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0025-001_Fitting GSP |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 867 | 522803-01-RFAM-FP-0016-001_Fitting BSP | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:45 AM | Mar 8, 2024 3:23 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0016-001_Fitting BSP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0016-001_Fitting BSP |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 866 | 522803-01-RFAM-FP-0015-001_Fitting of GSP_Hot-Dipped GSP | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:44 AM | Mar 6, 2024 3:46 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0015-001_Fitting of GSP_Hot-Dipped GSP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0015-001_Fitting of GSP_Hot-Dipped GSP |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 865 | 522803-01-RFAM-ME-0029-002_MCP_MCC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:26 AM | Mar 7, 2024 1:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-002_MCP_MCC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-002_MCP_MCC |  | V1 | 0 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 28, 2024 3:17 AM): ME commented in attached file. GSA CLIENT(Mar 7, 2024 1:26 PM): - please follow the color code above - please clarify All of the panels in the list are wall-mount type or floor-stand type because your attached Blokset panel test certificates are the floor-stand type - Please cross check kA rating of the circuit breaker with the AUR Electrical team again -CB inside MCC/MCP panel shall be ABB CB.
CLOSED | 864 | 522803-01-RFAM-EL-0066-001_Manhole Cover | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:21 AM | Feb 29, 2024 5:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0066-001_Manhole Cover.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0066-001_Manhole Cover |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 863 | 522803-01-RFAM-EL-0039-001_Network Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:18 AM | Mar 18, 2024 1:05 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0039-001_Network Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0039-001_Network Cable |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 862 | 522803-01-MS-EL-0005-002_Conduit Installation Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:14 AM | Mar 5, 2024 6:02 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0005-002_Conduit Installation Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0005-002_Conduit Installation Work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 861 | 522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:09 AM | Mar 19, 2024 10:22 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 861 | 522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:09 AM | Mar 19, 2024 10:22 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0007-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 861 | 522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:09 AM | Mar 19, 2024 10:22 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0007-002_RVT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-002_LIGHTNING PROTECTION AND GROUNDING SYSTEM LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 860 | 522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:00 AM | Mar 1, 2024 5:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 860 | 522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:00 AM | Mar 1, 2024 5:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0004-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 860 | 522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 10:00 AM | Mar 1, 2024 5:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0004-001_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0004-001_TOILET GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 859 | 522803-01-RFAS-HY-0003-002_Pump Room | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:58 AM | Mar 11, 2024 6:19 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0003-002_Pump Room.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0003-002_Pump Room |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 859 | 522803-01-RFAS-HY-0003-002_Pump Room | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:58 AM | Mar 11, 2024 6:19 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0003-002_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0003-002_Pump Room |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 859 | 522803-01-RFAS-HY-0003-002_Pump Room | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:58 AM | Mar 11, 2024 6:19 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0003-002_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0003-002_Pump Room |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 858 | 522803-01-RFAS-EL-0028-001_UDB and DB | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:55 AM | Mar 7, 2024 11:54 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0028-001_UDB and DB.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0028-001_UDB and DB |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Mar 7, 2024 11:53 PM): please recheck MCCB short circuit kA enough
CLOSED | 858 | 522803-01-RFAS-EL-0028-001_UDB and DB | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:55 AM | Mar 7, 2024 11:54 PM | 2 | 0 | 2 | 100% | Review closed | 4 | RFAS-EL-0028-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0028-001_UDB and DB |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 857 | 522803-01-RFAS-EL-0027-001_ST-01 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:48 AM | Mar 8, 2024 9:34 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0027-001_ST-01 PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0027-001_ST-01 PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 857 | 522803-01-RFAS-EL-0027-001_ST-01 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:48 AM | Mar 8, 2024 9:34 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0027-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0027-001_ST-01 PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 857 | 522803-01-RFAS-EL-0027-001_ST-01 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:48 AM | Mar 8, 2024 9:34 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0027-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0027-001_ST-01 PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 856 | 522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:46 AM | Mar 3, 2024 10:12 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 856 | 522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:46 AM | Mar 3, 2024 10:12 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0026-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 856 | 522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:46 AM | Mar 3, 2024 10:12 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0026-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0026-001_TYPICAL 24 kV RMU AND TRANSFORMER DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 855 | 522803-01-RFAS-EL-0025-001_LV SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:43 AM | Mar 8, 2024 9:26 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0025-001_LV SLD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0025-001_LV SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Mar 8, 2024 9:26 AM): Please re-confirm CB ICKA with AUR
CLOSED | 855 | 522803-01-RFAS-EL-0025-001_LV SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:43 AM | Mar 8, 2024 9:26 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0025-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0025-001_LV SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 855 | 522803-01-RFAS-EL-0025-001_LV SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 17, 2024 9:43 AM | Mar 8, 2024 9:26 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0025-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0025-001_LV SLD |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 854 | 522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 16, 2024 5:09 PM | Mar 7, 2024 11:22 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL |  | V1 | 0 | Approved | Updated review status
CLOSED | 854 | 522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 16, 2024 5:09 PM | Mar 7, 2024 11:22 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0011-002_CORE WALL STAIR-02 DETAIL |  | V1 | 0 | Approved | Updated review status
CLOSED | 848 | 522803-01-MS-CSA-0005-003_Method statement of soil protection work and excavation for exterior works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 16, 2024 8:22 AM | Feb 29, 2024 4:02 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0005-003_Method statement of soil protection work and excavation for exterior works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0005-003_Method statement of soil protection work and excavation for exterior works |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 847 | 522803-01-RFAM-CV-0009-001_Wire mesh for topping above fuel tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 15, 2024 3:13 PM | Feb 21, 2024 9:38 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0009-001_ Wire mesh for topping above fuel tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0009-001_ Wire mesh for topping above fuel tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 842 | 522803-01-RFAM-HY-0015-002_Fuel Management System | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 15, 2024 10:32 AM | Mar 25, 2024 11:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0015-002_Fuel Management System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0015-002_Fuel Management System |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 841 | 522803-01-RFAM-ME-0008-002_Chemical Feed Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 15, 2024 8:20 AM | Mar 15, 2024 5:12 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0008-002_Chemical Feed Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0008-002_Chemical Feed Pump |  | V1 | 1 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Feb 28, 2024 11:16 AM): ME comment in attached file
CLOSED | 840 | 522803-01-MS-HY-0006-002_Pipe Sleeve Installation for Fuel System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 3:19 PM | Mar 6, 2024 10:06 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0006-002_Pipe Sleeve Installation for Fuel System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0006-002_Pipe Sleeve Installation for Fuel System |  | V1 | 0 | Approved | Updated review status
CLOSED | 839 | 522803-01-RFAS-EL-0024-001_LCS SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 1:15 PM | Feb 21, 2024 8:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0024-001_LCS SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0024-001_LCS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 21, 2024 8:13 PM): Due to GSA change Lighting design in some area Please contact K. Sarunyoo for GSA for interior/Exterior lighting design updated
CLOSED | 839 | 522803-01-RFAS-EL-0024-001_LCS SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 1:15 PM | Feb 21, 2024 8:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0024-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0024-001_LCS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 839 | 522803-01-RFAS-EL-0024-001_LCS SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 1:15 PM | Feb 21, 2024 8:13 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0024-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0024-001_LCS SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 838 | 522803-01-RFAM-ME-0033-001_Oxygen Sensor | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 11:26 AM | Mar 8, 2024 3:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0033-001_Oxygen Sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0033-001_Oxygen Sensor |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 28, 2024 4:16 PM): ME commented in attached file.
CLOSED | 834 | 522803-01-RFAM-HY-0005-003_Underground Fuel tank | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 9:44 AM | Feb 23, 2024 11:10 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0005-003_Underground Fuel tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0005-003_Underground Fuel tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 833 | 522803-01-RFAM-EL-0060-001_Modular Support | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 9:40 AM | Mar 3, 2024 10:25 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0060-001_Modular Support.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0060-001_Modular Support |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 829 | 522803-01-RFAS-EL-0023-001_LVSB and DUSB PANEL L2 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:19 AM | Mar 3, 2024 10:29 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0023-001_LVSB and DUSB PANEL L2.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0023-001_LVSB and DUSB PANEL L2 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 829 | 522803-01-RFAS-EL-0023-001_LVSB and DUSB PANEL L2 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:19 AM | Mar 3, 2024 10:29 PM | 2 | 0 | 2 | 100% | Review closed | 4 | RFAS-EL-0023-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0023-001_LVSB and DUSB PANEL L2 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 828 | 522803-01-RFAS-EL-0022-001_ST-04 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:18 AM | Mar 3, 2024 10:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0022-001_ST-04 PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0022-001_ST-04 PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 828 | 522803-01-RFAS-EL-0022-001_ST-04 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:18 AM | Mar 3, 2024 10:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0022-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0022-001_ST-04 PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 828 | 522803-01-RFAS-EL-0022-001_ST-04 PLAN | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:18 AM | Mar 3, 2024 10:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0022-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0022-001_ST-04 PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 827 | 522803-01-RFAS-EL-0021-001_LVDC PANEL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:17 AM | Mar 3, 2024 10:45 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0021-001_LVDC PANEL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0021-001_LVDC PANEL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Mar 3, 2024 10:44 PM): All Circuit Breaker shall DC type, and shall revise drawing to DC CB
CLOSED | 827 | 522803-01-RFAS-EL-0021-001_LVDC PANEL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:17 AM | Mar 3, 2024 10:45 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0021_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0021-001_LVDC PANEL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 827 | 522803-01-RFAS-EL-0021-001_LVDC PANEL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 14, 2024 8:17 AM | Mar 3, 2024 10:45 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0021_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0021-001_LVDC PANEL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 824 | 522803-01-RFAM-EL-0032-002_Load Bank | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 13, 2024 4:31 PM | Feb 21, 2024 4:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0032-002_Load Bank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0032-002_Load Bank |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Feb 21, 2024 4:21 PM): CX Level was cleared For KAIC deviated if supplier will submit the calculation after place order therefore in the future TTI submit the load flow analysis/Short circuit not pass because of kAIC Load bank ,TTI shall improve and/or fix this issue
CLOSED | 822 | 522803-01-RFAM-ST-0026-001_PU foam at opening of PC panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 13, 2024 2:11 PM | Feb 29, 2024 2:53 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0026-001_PU foam at opening of PC panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0026-001_PU foam at opening of PC panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 821 | 522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 13, 2024 1:46 PM | Feb 23, 2024 4:10 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 821 | 522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 13, 2024 1:46 PM | Feb 23, 2024 4:10 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0010-002_CORE WALL STAIR-01 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 820 | 522803-01-MRPT-GEN-0003-001_TTI Monthly Construction No.03_December 2023 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 13, 2024 1:13 PM | Mar 7, 2024 12:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0003-001_TTI Monthly Construction No.03_December 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0003-001_TTI Monthly Construction No.03_December 2023 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 815 | 522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:45 PM | Feb 28, 2024 2:29 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 815 | 522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:45 PM | Feb 28, 2024 2:29 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0018-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 815 | 522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:45 PM | Feb 28, 2024 2:29 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0018-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0018-001_UNDERGROUND FUEL SLEEVE A and B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 814 | 522803-01-RFAS-HY-0017-001_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:42 PM | Mar 1, 2024 4:51 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0017-001_FUEL TANK A and B.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-001_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 814 | 522803-01-RFAS-HY-0017-001_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:42 PM | Mar 1, 2024 4:51 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0017-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-001_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 814 | 522803-01-RFAS-HY-0017-001_FUEL TANK A and B | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 2:42 PM | Mar 1, 2024 4:51 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0017-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0017-001_FUEL TANK A and B |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 805 | 522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:25 AM | Mar 11, 2024 6:24 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND |  | V1 | 0 | Approved | Updated review status
CLOSED | 805 | 522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:25 AM | Mar 11, 2024 6:24 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0016-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND |  | V1 | 0 | Approved | Updated review status
CLOSED | 805 | 522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:25 AM | Mar 11, 2024 6:24 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0016-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0016-001_FUEL SUPPLY SYSTEM LAYOUT - UNDERGROUND |  | V1 | 0 | Approved | Updated review status
CLOSED | 804 | 522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:23 AM | Mar 1, 2024 3:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 804 | 522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:23 AM | Mar 1, 2024 3:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0015-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 804 | 522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:23 AM | Mar 1, 2024 3:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0015-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0015-001_FUEL CONTROL SYSTEM - UNDERGROUND |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 803 | 522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:22 AM | Feb 27, 2024 8:38 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 803 | 522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:22 AM | Feb 27, 2024 8:38 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0012-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 803 | 522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 11:22 AM | Feb 27, 2024 8:38 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0012-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0012-001_MASTER LAYOUT - FUEL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 802 | 522803-01-RFAM-HY-0021-002_Valves (Fuel System) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 9:24 AM | Mar 4, 2024 10:04 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0021-002_Valves (Fuel System).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0021-002_Valves (Fuel System) |  | V1 | 0 | Approved | Updated review status
CLOSED | 801 | 522803-01-RFAM-HY-0024-001_Underground Fuel Pipe (BSP) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 12, 2024 9:09 AM | Mar 4, 2024 8:47 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0024-001_Underground Fuel Pipe (BSP).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0024-001_Underground Fuel Pipe (BSP) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 794 | 522803-01-MS-HY-0003-003_Underground Fuel Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 10, 2024 8:32 AM | Mar 6, 2024 9:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0003-003_Underground Fuel Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0003-003_Underground Fuel Tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 792 | 522803-01-RFAM-ME-0041-001_Balancing Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 10, 2024 8:29 AM | Mar 8, 2024 6:44 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0041-001_Balancing Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0041-001_Balancing Valve |  | V1 | 1 | Make correction as noted & resubmit | Updated review status
CLOSED | 791 | 522803-01-RFAS-CV-0002-003_DETAIL FENCE TYPE 1,1A,2 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 10, 2024 8:22 AM | Feb 20, 2024 9:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0002-003_DETAIL FENCE TYPE 1,1A,2.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0002-003_DETAIL FENCE TYPE 1,1A,2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 790 | 522803-01-RFAM-HY-0014-002_Fuel Sensor | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 4:47 PM | Mar 4, 2024 8:59 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0014-002_Fuel Sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0014-002_Fuel Sensor |  | V1 | 0 | Approved | Updated review status
CLOSED | 789 | 522803-01-RFAM-ME-0001-002_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 4:32 PM | Mar 18, 2024 3:51 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-002_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-002_VSD |  | V1 | 6 | Disapproved | Updated review status
CLOSED | 785 | 522803-01-RFI-ME-0017-001_Additional Doors for Valve Maintenance | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 2:07 PM | Mar 4, 2024 10:38 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFI-ME-0017-001_Additional Doors for Valve Maintenance.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1247_RFI-ME_Request for Information (Mechanical)/522803-01-RFI-ME-0017-001_Additional Doors for Valve Maintenance |  | V1 | 1 | Disapproved | Updated review status | Kloer Chongchaikit(Feb 26, 2024 12:01 PM): ME replied in attachment.
CLOSED | 783 | 522803-01-RFAM-ME-0040-001_Gas Detector System | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:58 PM | Feb 20, 2024 3:00 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0040-001_Gas Detector System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0040-001_Gas Detector System |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 18, 2024 8:30 PM): ME comment in attached file.
CLOSED | 782 | 522803-01-RFAM-ME-0020-002_Water Pressure Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:57 PM | Mar 6, 2024 12:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0020-002_Water Pressure Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0020-002_Water Pressure Transmitter |  | V1 | 1 | Approved | Updated review status
CLOSED | 781 | 522803-01-RFAM-ME-0015-002_Water Diff. Pressure Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:55 PM | Mar 6, 2024 11:58 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0015-002_Water Diff. Pressure Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0015-002_Water Diff. Pressure Switch |  | V1 | 1 | Approved | Updated review status
CLOSED | 779 | 522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:46 PM | Mar 6, 2024 2:52 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 779 | 522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:46 PM | Mar 6, 2024 2:52 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0002-003_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 779 | 522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 1:46 PM | Mar 6, 2024 2:52 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0002-003_RVT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-003_DETAIL OF MANHOLE |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 775 | 522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:27 AM | Feb 15, 2024 12:16 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 775 | 522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:27 AM | Feb 15, 2024 12:16 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0016-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 775 | 522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:27 AM | Feb 15, 2024 12:16 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0016-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0016-001_ST-03 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 774 | 522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:22 AM | Feb 16, 2024 5:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 16, 2024 5:31 PM): GSA: Please submit voltage drop calculation. for the maximum length of cable, the Voltage Drop shall enough for operate the load and meet back up time as specification required.
CLOSED | 774 | 522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:22 AM | Feb 16, 2024 5:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0018-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 774 | 522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:22 AM | Feb 16, 2024 5:31 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0018-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0018-001_POWER SUPPLY 110 VDC LAYOUT - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 773 | 522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:14 AM | Feb 16, 2024 5:47 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Feb 16, 2024 5:47 PM): Approved Single line diagram Solar under provision sum. please wait GSA to select vendor
CLOSED | 773 | 522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:14 AM | Feb 16, 2024 5:47 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0020-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 773 | 522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:14 AM | Feb 16, 2024 5:47 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0020-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0020-001_SINGLE LINE DIAGRAM SOLAR |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 772 | 522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:08 AM | Feb 28, 2024 10:11 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND).PDF | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 772 | 522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:08 AM | Feb 28, 2024 10:11 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0001-003_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 772 | 522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 9:08 AM | Feb 28, 2024 10:11 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-EL-0001-003_RVT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-003_MV_COMS LAYOUT (UNDERGROUND) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 771 | 522803-01-RFAM-ST-0025-001_Wire mesh for screed | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 9, 2024 9:00 AM | Feb 20, 2024 9:17 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0025-001_Wire mesh for screed.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0025-001_Wire mesh for screed |  | V1 | 0 | Approved | Updated review status
CLOSED | 770 | 522803-01-CAL-ST-0003-001_Calculation Lifting Anchor of PC wall | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 9, 2024 8:52 AM | Feb 20, 2024 9:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0003-001_Calculation Lifting Anchor of PC wall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0003-001_Calculation Lifting Anchor of PC wall |  | V1 | 0 | Approved | Updated review status
CLOSED | 769 | 522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:43 AM | Mar 1, 2024 2:51 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 769 | 522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:43 AM | Mar 1, 2024 2:51 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0014-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 769 | 522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:43 AM | Mar 1, 2024 2:51 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0014-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0014-001_TYPICAL DETAILS 7-8 (FUEL) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 768 | 522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:41 AM | Feb 27, 2024 8:59 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 768 | 522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:41 AM | Feb 27, 2024 8:59 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0013-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 768 | 522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:41 AM | Feb 27, 2024 8:59 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0013-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0013-001_FUEL TANK DETAILS |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 767 | 522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:40 AM | Mar 1, 2024 2:40 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 767 | 522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:40 AM | Mar 1, 2024 2:40 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0011-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 767 | 522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 9, 2024 8:40 AM | Mar 1, 2024 2:40 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0011-001_Revit.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0011-001_SINGLE LINE DIAGRAM (FUEL SYSTEM) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 759 | 522803-01-RFAM-ST-0016-002_PC panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 8, 2024 3:27 PM | Feb 23, 2024 11:36 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0016-002_PC panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0016-002_PC panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 758 | 522803-01-RFAM-ME-0012-003_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 8, 2024 2:44 PM | Feb 13, 2024 9:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-003_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-003_Thermal Energy Storage Tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 12, 2024 1:29 PM): ME comment in DC file.
CLOSED | 757 | 522803-01-RPT-LE-0004-002_Monthly Report for LEED No.04 for January 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 8, 2024 10:45 AM | Feb 13, 2024 10:13 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0004-002_Monthly Report for LEED No.04 for January 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0004-002_Monthly Report for LEED No.04 for January 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 756 | 522803-01-RFAM-FP-0004-003_Fire pump and Jockey pump with controller | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 8, 2024 9:47 AM | Feb 15, 2024 10:48 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0004-003_Fire Pump and Jockey Pump with Controller.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0004-003_Fire pump and Jockey pump with controller |  | V1 | 0 | Approved | Updated review status
CLOSED | 754 | 522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 8, 2024 8:18 AM | Feb 16, 2024 9:15 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 754 | 522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 8, 2024 8:18 AM | Feb 16, 2024 9:15 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0008-002_CORE WALL STAIR-03 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 753 | 522803-01-RFAM-EL-0045-002_Busway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 5:03 PM | Feb 24, 2024 12:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0045-002_Busway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0045-002_Busway |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Feb 24, 2024 12:10 PM): - Please checking floor static load with TTI and recheck with your battery cabinet - Sizing of Charger shall enough for future phase, spare panel and enough charging the battery
CLOSED | 746 | 522803-01-MS-ST-0003-0001_Method Statement Safety_Quality Procedure of work for substructure work_1Fl._M | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 7, 2024 1:45 PM | Feb 16, 2024 9:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0003-001_Method Statement Safety_Quality Procedure of work for substructure work_1Fl._M.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0003-001_Method Statement Safety_Quality Procedure of work for substructure work_1Fl._M |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 745 | 522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:44 PM | Feb 22, 2024 5:33 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 745 | 522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:44 PM | Feb 22, 2024 5:33 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0010-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 745 | 522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:44 PM | Feb 22, 2024 5:33 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0010-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0010-001_EQUIPMENT SCHEDULE (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 744 | 522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 11, 2024 8:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC |  | V1 | 0 | Approved | Updated review status
CLOSED | 744 | 522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 11, 2024 8:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0009-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC |  | V1 | 0 | Approved | Updated review status
CLOSED | 744 | 522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 11, 2024 8:57 AM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0009-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0009-001_FUEL CONTROL SCHEMATIC |  | V1 | 0 | Approved | Updated review status
CLOSED | 743 | 522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 1, 2024 2:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 743 | 522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 1, 2024 2:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0008-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 743 | 522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:43 PM | Mar 1, 2024 2:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-HY-0008-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0008-001_FUEL DISTRIBUTION SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 742 | 522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 4:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 742 | 522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 4:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0007-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 742 | 522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 4:23 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0007-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0007-001_LEGENDS AND ABBREVIATION (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 741 | 522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 5:04 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 741 | 522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 5:04 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0006-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 741 | 522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 1:42 PM | Feb 22, 2024 5:04 PM | 3 | 3 | 0 | 100% | Review closed | 4 | RFAS-HY-0006-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0006-001_TYPICAL DETAILS 1-6 (FUEL CONTROL) |  | V1 | 0 | Approved | Updated review status
CLOSED | 739 | 522803-01-RFAM-EL-0022-002_Surge protection device | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 12:01 PM | Feb 15, 2024 12:25 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0022-002_Surge protection device.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0022-002_Surge protection device |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Feb 15, 2024 12:24 PM): -Please see comment in attached file if can not declare maximum discharge current please resubmit with correct specification - some panel missing SPD
CLOSED | 738 | 522803-01-RFAM-EL-0018-002_Shield Twisted Pair Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 12:00 PM | Feb 15, 2024 12:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0018-002_Shield Twisted Pair Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0018-002_Shield Twisted Pair Cable |  | V1 | 0 | Approved | Updated review status
CLOSED | 737 | 522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 11:27 AM | Mar 1, 2024 2:55 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 737 | 522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 11:27 AM | Mar 1, 2024 2:55 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0004-001_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 737 | 522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 7, 2024 11:27 AM | Mar 1, 2024 2:55 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-ME-0004-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0004-001_TYPICAL WIRING SCHEMATIC DIAGRAM |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 734 | 522803-01-RFAS-HY-0005-001_FUEL SYSTEM SOO | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 6, 2024 5:27 PM | Apr 22, 2024 5:40 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0005-001_FUEL SYSTEM SOO.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0005-001_FUEL SYSTEM SOO |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 733 | 522803-01-RFAM-ME-0039-001_Weather Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 6, 2024 5:26 PM | Mar 6, 2024 2:52 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0039-001_Weather Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0039-001_Weather Transmitter |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Feb 28, 2024 3:42 AM): ME commented in attached file.
CLOSED | 732 | 522803-01-RFAM-ME-0038-001_Water Level Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 6, 2024 5:25 PM | Mar 8, 2024 6:19 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0038-001_Water Level Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0038-001_Water Level Switch |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 731 | 522803-01-RFAM-HY-0023-001_Valves for Hydraulics Work | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 6, 2024 1:39 PM | Feb 23, 2024 5:11 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0023-001_Valves for Hydraulics Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0023-001_Valves for Hydraulics Work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 727 | 522803-01-RFAS-ME-0003-001_LEGENDS AND ABBREVIATION | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 4:14 PM | Feb 12, 2024 1:23 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0003-001_LEGENDS AND ABBREVIATION.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0003-001_LEGENDS AND ABBREVIATION |  | V1 | 1 | Approved | Updated review status
CLOSED | 726 | 522803-01-RFAS-ME-0002-001_ACMV PIPING SCHEMATIC | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 4:13 PM | Mar 6, 2024 2:45 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0002-001_ACMV PIPING SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0002-001_ACMV PIPING SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 725 | 522803-01-RFAS-ME-0001-001_ACMV SOO SHEET 1 - 6 | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 4:12 PM | Apr 22, 2024 5:55 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ME-0001-001_ACMV SOO SHEET 1 - 6.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1147_RFAS-ME_Request for Approval Shop Drawings (Mechanical)/522803-01-RFAS-ME-0001-001_ACMV SOO SHEET 1 - 6 |  | V1 | 2 | Make correction as noted & resubmit | Updated review status
CLOSED | 723 | 522803-01-MRPT-GEN-0004_001_TTI Monthly Construction No.04_January 2024 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 5, 2024 1:20 PM | Mar 7, 2024 12:43 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0004-001_TTI Monthly Construction No.04_January 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0004_001_TTI Monthly Construction No.04_January 2024 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 716 | 522803-01-RFAM-ME-0010-002_MV Fan | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 10:04 AM | Mar 4, 2024 9:41 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0010-002_MV Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0010-002_MV Fan |  | V1 | 7 | Make correction as noted & proceed | Updated review status
CLOSED | 715 | 522803-01-RFAS-MEP-0001-002_MEP SD Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 9:14 AM | Feb 15, 2024 11:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-MEP-0001-002_MEP SD Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1144_RFAS-MEP_Request for Approval Shop Drawings (Mechanical Electrical and Plumbing)/522803-01-RFAS-MEP-0001-002_MEP SD Schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 714 | 522803-01-RFAM-EL-0038-002_Earth Fault Relay | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 5, 2024 8:09 AM | Feb 16, 2024 5:52 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0038-002_Earth Fault Relay.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0038-002_Earth Fault Relay |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 713 | 522803-01-RFAS-CV-0004-001_FOUNDATION FENCE PART 6,7,8 & SECTION FENCE PART 7,8 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 2, 2024 6:29 PM | Feb 13, 2024 10:01 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0004-001_FOUNDATION FENCE PART 6,7,8 & SECTION FENCE PART 7,8.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0004-001_FOUNDATION FENCE PART 6,7,8 & SECTION FENCE PART 7,8 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 712 | 522803-01-RFAM-ST-0024-001_Fireproof paint | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Feb 2, 2024 6:00 PM | Feb 8, 2024 3:54 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0024-001_Fireproof paint.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0024-001_Fireproof paint |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 711 | 522803-01-RFI-ST-0011-001_Beams Clash with CHW Pipes at 6FL, Riser A_B | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 5:09 PM | Mar 7, 2024 11:59 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFI-ST-0011-001_Beams Clash with CHW Pipes at 6FL, Riser A_B.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1246_RFI-ST_Request for Information (Structure)/522803-01-RFI-ST-0011-001_Beams Clash with CHW Pipes at 6FL, Riser A_B |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 706 | 522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 1:54 PM | Mar 4, 2024 12:21 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 706 | 522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 1:54 PM | Mar 4, 2024 12:21 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0006-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 706 | 522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 1:54 PM | Mar 4, 2024 12:21 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0006-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0006-001_LIGHTNING PROTECTION AND GROUNDING SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 705 | 522803-01-RFAM-HY-0016-002_Fuel Pump | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 1:26 PM | Feb 13, 2024 9:54 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0016-002_Fuel Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0016-002_Fuel Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 704 | 522803-01-RFAM-HY-0006-002_Fuel Flow Meter | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 1:24 PM | Feb 12, 2024 10:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0006-002_Fuel Flow Meter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0006-002_Fuel Flow Meter |  | V1 | 0 | Approved | Updated review status
CLOSED | 700 | 522803-01-RFAM-EL-0041-002_Explosion Proof Device | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 2, 2024 9:01 AM | Feb 9, 2024 1:11 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0041-002_Explosion Proof Device.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0041-002_Explosion Proof Device |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 699 | 522803-01-RFAS-FP-0002-002_Fire Pump Room | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 1:08 PM | Feb 6, 2024 1:54 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0002-002_Fire Pump Room.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-002_Fire Pump Room |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 699 | 522803-01-RFAS-FP-0002-002_Fire Pump Room | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 1:08 PM | Feb 6, 2024 1:54 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0002-002_DWG.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-002_Fire Pump Room |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 699 | 522803-01-RFAS-FP-0002-002_Fire Pump Room | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 1:08 PM | Feb 6, 2024 1:54 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-FP-0002-002_NWD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-002_Fire Pump Room |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 697 | 522803-01-RFAM-HY-0022-001_Sand Filter_Water Softener | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 10:25 AM | Feb 13, 2024 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0022-001_Sand Filter_Water Softener.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0022-001_Sand Filter_Water Softener |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 696 | 522803-01-RFI-HY-0018-001_Redundant Water Incoming | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 9:00 AM | Feb 13, 2024 9:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFI-HY-0018-001_Redundant Water Incoming.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1248_RFI-HY_Request for Information (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFI-HY-0018-001_Redundant Water Incoming |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 695 | 522803-01-RFAM-ME-0005-002_CHW, CDW Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Feb 1, 2024 8:21 AM | Feb 21, 2024 3:23 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0005-002_CHW, CDW Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0005-002_CHW, CDW Pump |  | V1 | 1 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Feb 18, 2024 8:47 PM): ME comment in AUR reviewed file.
CLOSED | 693 | 522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:30 PM | Feb 19, 2024 4:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM).PDF | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 693 | 522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:30 PM | Feb 19, 2024 4:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0017-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 693 | 522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:30 PM | Feb 19, 2024 4:03 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0017-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0017-001_LV SINGLE LINE DIAGRAM BUILDING LOAD (IT CATCHER SYSTEM) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 692 | 522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:29 PM | Feb 15, 2024 11:18 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C.PDF | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 15, 2024 11:17 AM): Please ask AUR for updated latest IFC for reference to make Shop drawing
CLOSED | 692 | 522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:29 PM | Feb 15, 2024 11:18 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0015-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 692 | 522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:29 PM | Feb 15, 2024 11:18 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0015-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0015-001_LEVEL 5 IT SINGLE LINE DIAGRAM FOR 2MW HYPERSCALE SYSTEM A, B and C |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 691 | 522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:28 PM | Feb 8, 2024 12:17 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 8, 2024 12:17 AM): please add PA in guard house
CLOSED | 691 | 522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:28 PM | Feb 8, 2024 12:17 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0014-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 691 | 522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:28 PM | Feb 8, 2024 12:17 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0014-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0014-001_PUBLIC ADDRESS AND VOICE ALARM SYSTEM SCHEMATIC |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 690 | 522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:25 PM | Feb 19, 2024 3:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 690 | 522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:25 PM | Feb 19, 2024 3:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0013-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 690 | 522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:25 PM | Feb 19, 2024 3:35 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0013-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0013-001_ST-02 ENLARGE PLAN - GROUND FLOOR - LEVEL 6 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 689 | 522803-01-RFAS-EL-0012-001_BTU and BATT PANEL Level 1G, 1M, 2F, 5F and 6F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 5:24 PM | Feb 8, 2024 12:42 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0012-001_BTU and BATT PANEL Level 1G, 1M, 2F, 5F and 6F.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0012-001_BTU and BATT PANEL Level 1G, 1M, 2F, 5F and 6F |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 8, 2024 12:39 AM): Please recheck color please submit catalog of battery Please cross check floor load enough for weight of battery cabinet
CLOSED | 688 | 522803-01-RFAS-FP-0004-001_FH Riser Piping Plan and Section for ST 1,2,3,4 - GROUND FLOOR | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 4:49 PM | Feb 12, 2024 9:39 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0004-001_FH Riser Piping Plan and Section for ST 1,2,3,4 - GROUND FLOOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0004-001_FH Riser Piping Plan and Section for ST 1,2,3,4 - GROUND FLOOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 687 | 522803-01-RFAM-EL-0059-001_Push-In Wire Connector | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 4:48 PM | Feb 8, 2024 12:47 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0059-001_Push-In Wire Connector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0059-001_Push-In Wire Connector |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 685 | 522803-01-RFAM-ME-0030-001_Fuel_Water Leak Detector | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 4:23 PM | Feb 13, 2024 9:15 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0030-001_Fuel_Water Leak Detector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0030-001_Fuel_Water Leak Detector |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 2, 2024 11:42 AM): ME comment in attached file.
CLOSED | 684 | 522803-01-RFAM-ME-0036-001_Water Detector with Conductivity Cable | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 4:18 PM | Mar 8, 2024 6:12 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0036-001_Water Detector with Conductivity Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0036-001_Water Detector with Conductivity Cable |  | V1 | 1 | Make correction as noted & resubmit | Updated review status
CLOSED | 683 | 522803-01-RFAM-FP-0003-002_Pre-Action Valve with Compressor | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 4:11 PM | Feb 15, 2024 10:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0003-002_Pre-Action Valve with Compressor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0003-002_Pre-Action Valve with Compressor |  | V1 | 0 | Approved | Updated review status
CLOSED | 682 | 522803-01-RFAM-EL-0049-002_Inserts | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 1:37 PM | Feb 8, 2024 12:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0049-002_Inserts.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0049-002_Inserts |  | V1 | 0 | Approved | Updated review status
CLOSED | 681 | 522803-01-RFAM-ME-0012-002_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 1:33 PM | Feb 2, 2024 5:15 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-002_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-002_Thermal Energy Storage Tank |  | V1 | 2 | Disapproved | Updated review status | Kloer Chongchaikit(Feb 2, 2024 11:51 AM): ME comment in attached file.
CLOSED | 680 | 522803-01-RFAM-ME-0037-001_IAQ Sensor | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 31, 2024 1:28 PM | Mar 8, 2024 6:41 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0037-001_IAQ Sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0037-001_IAQ Sensor |  | V1 | 1 | Make correction as noted & resubmit | Updated review status
CLOSED | 678 | 522803-01-RFAM-FP-0012-001_Gas Suppression System (IG-100) | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 30, 2024 1:32 PM | Feb 21, 2024 1:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0012-001_Gas Suppression System (IG-100).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0012-001_Gas Suppression System (IG-100) |  | V1 | 0 | Approved | Updated review status
CLOSED | 677 | 522803-01-RFAM-FP-0007-002_Fire Extinguisher | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 30, 2024 1:30 PM | Feb 12, 2024 11:20 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0007-002_Fire Extinguisher.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0007-002_Fire Extinguisher |  | V1 | 0 | Approved | Updated review status
CLOSED | 676 | 522803-01-RFAM-FP-0005-002_Alarm Valve | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 30, 2024 1:25 PM | Feb 12, 2024 11:50 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0005-002_Alarm Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0005-002_Alarm Valve |  | V1 | 0 | Approved | Updated review status
CLOSED | 674 | 522803-01-RPT-ST-0017-001_Trial mix report of ORC 29Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 30, 2024 9:23 AM | Feb 6, 2024 2:43 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0017-001_Trial mix report of ORC 29Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0017-001_Trial mix report of ORC 29Nov23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 673 | 522803-01-RPT-ST-0018-001_Trial mix report of Cpac 17Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 30, 2024 9:16 AM | Feb 6, 2024 2:45 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0018-001_Trial mix report of Cpac 17Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0018-001_Trial mix report of Cpac 17Nov23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 672 | 522803-01-RFAM-ME-0022-002_VAV PSU Panel | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 30, 2024 8:01 AM | Mar 11, 2024 6:46 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0022-002_VAV PSU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0022-002_VAV PSU Panel |  | V1 | 2 | Make correction as noted & proceed | Updated review status
CLOSED | 669 | 522803-01-MS-EL-0005-001_Conduit Installation work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 29, 2024 4:08 PM | Feb 1, 2024 9:48 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-EL-0005-001_Conduit Installation work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0005-001_Conduit Installation work |  | V2 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 665 | 522803-01-RPT-LE-0004-001_Monthly Report for LEED No.04 for January 2024 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 29, 2024 7:54 AM | Jan 31, 2024 11:05 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-LE-0004-001_Monthly Report for LEED No.04 for January 2024.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0004-001_Monthly Report for LEED No.04 for January 2024 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 658 | 522803-01-PGM-GEN-0001-001_Master schedule_(Included provisional sum and MNE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 26, 2024 6:13 PM | Feb 7, 2024 3:14 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-PGM-GEN-0001-001_Master schedule_(Included provissional sum and MNE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-001_Master schedule_(Included provisional sum and MNE) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 658 | 522803-01-PGM-GEN-0001-001_Master schedule_(Included provisional sum and MNE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 26, 2024 6:13 PM | Feb 7, 2024 3:14 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 20240127.mpp | Project Files/03_Construction Stage/02_Main Contractor TTI/1007_PGM-XXX_Request for Approval Construction Programme (For all types of Discipline)/522803-01-PGM-GEN-0001-001_Master schedule_(Included provisional sum and MNE) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 656 | 522803-01-RFAM-ST-0023-001 Water swelling | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 26, 2024 3:05 PM | Jan 30, 2024 2:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0023-001 Water swelling.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0023-001_Water swelling |  | V1 | 0 | Approved | Updated review status
CLOSED | 655 | 522803-01-RFAM-FP-0013-001_Coating and Water Stop for Underground Material | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 26, 2024 2:14 PM | Feb 1, 2024 3:46 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0013-001_Coating and Water Stop for Underground Material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0013-001_Coating and Water Stop for Underground Material |  | V1 | 0 | Approved | Updated review status
CLOSED | 651 | 522803-01-RFAS-ST-0007-002_GROUND FLOOR FRAMING PLAN_Updated | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 11:42 AM | Feb 6, 2024 2:55 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0007-002 GROUND FLOOR FRAMING PLAN.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0007-002 GROUND FLOOR FRAMING PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 651 | 522803-01-RFAS-ST-0007-002_GROUND FLOOR FRAMING PLAN_Updated | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 11:42 AM | Feb 6, 2024 2:55 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0007-002_GROUND FLOOR FRAMING PLAN_Updated.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0007-002 GROUND FLOOR FRAMING PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 649 | 522803-01-RFAS-CV-0002-002_DETAIL FENCE TYPE 1,1A,2_Updated | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 11:35 AM | Feb 6, 2024 3:07 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0002-002_DETAIL FENCE TYPE 1,1A,2_Updated.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0002-002_DETAIL FENCE TYPE 1,1A,2_Updated |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 648 | 522803-01-RFAM-ST-0022-001_B-bond Chemical rebar & bolt | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 11:23 AM | Feb 8, 2024 3:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0022-001_B-bond Chemical rebar & bolt.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0022-001_B-bond Chemical rebar & bolt |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 646 | 522803-01-RFAM-FP-0008-002_Fire Hose Cabinet | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 26, 2024 11:02 AM | Jan 31, 2024 10:15 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0008-002_Fire Hose Cabinet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0008-002_Fire Hose Cabinet |  | V1 | 0 | Approved | Updated review status
CLOSED | 645 | 522803-01-RFAM-CV-0007-001_ RC pipe | (TTI) Request for Approval (AUR_Civil Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 10:29 AM | Feb 6, 2024 3:14 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0007-001_ RC pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0007-001_ RC pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 643 | 522803-01-RFAM-CV-0006-001_HDPE pipe | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 26, 2024 10:03 AM | Feb 7, 2024 10:16 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0006-001_HDPE pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0006-001_HDPE pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 638 | 522803-01-RFAS-CV-0003-001_DETAIL FENCE TYPE 3,3A | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 25, 2024 2:12 PM | Feb 6, 2024 3:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0003-001_DETAIL FENCE TYPE 3,3A.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0003-001_DETAIL FENCE TYPE 3,3A |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 636 | 522803-01-RFAS-EL-0011-001_MSB and LVSB PANEL Level 1M | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:52 PM | Feb 13, 2024 6:37 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0011-001_MSB and LVSB PANEL Level 1M.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0011-001_MSB and LVSB PANEL Level 1M |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 13, 2024 6:37 PM): Please see same comment in Doc NO. 522803-01-RFAS-EL-0005-001 and resubmit.
CLOSED | 636 | 522803-01-RFAS-EL-0011-001_MSB and LVSB PANEL Level 1M | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:52 PM | Feb 13, 2024 6:37 PM | 2 | 0 | 2 | 100% | Review closed | 4 | RFAS-EL-0011-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0011-001_MSB and LVSB PANEL Level 1M |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 635 | 522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:47 PM | Feb 8, 2024 1:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 635 | 522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:47 PM | Feb 8, 2024 1:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0010-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 635 | 522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:47 PM | Feb 8, 2024 1:19 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0010-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0010-001_LV SINGLE LINE DIAGRAM - FAN WALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 634 | 522803-01-RFAM-ME-0029-001_MCP_MCC Panel (Brand ASEFA) | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 25, 2024 1:40 PM | Feb 7, 2024 4:55 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0029-001_MCP_MCC Panel (Brand ASEFA).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0029-001_MCP_MCC Panel (Brand ASEFA) |  | V1 | 5 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Feb 7, 2024 5:05 AM): ME comment in attached file. GSA CLIENT(Feb 7, 2024 4:54 PM): Please resubmit with : - comply table - all material data sheet - highlight or cloud in SLD which panel will apply this RFAM - Type test certificate
CLOSED | 631 | 522803-01-CAL-ST-0002-001_Calculation of forming substructure work, Top slab water tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 25, 2024 10:47 AM | Feb 9, 2024 2:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0002-001_Calculation of forming substructure work, Top slab water tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0002-001_Calculation of forming substructure work, Top slab water tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 617 | 522803-01-MS-EL-0003-002_Earthing and Grounding Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 24, 2024 3:43 PM | Feb 1, 2024 2:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0003-002_Earthing and Grounding Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0003-002_Earthing and Grounding Work |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 616 | 522803-01-MS-HY-0003-002_Underground Fuel Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 24, 2024 3:22 PM | Feb 1, 2024 2:30 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0003-002_Underground Fuel Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0003-002_Underground Fuel Tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 615 | 522803-01-RFAM-EL-0032-001_Load Bank | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 24, 2024 2:58 PM | Feb 8, 2024 2:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0032-001_Load Bank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0032-001_Load Bank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 8, 2024 2:09 AM): please see comment in attached file
CLOSED | 612 | 522803-01-RFAS-CV-0002-001 DETAIL FENCE TYPE 1,1A,2 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 23, 2024 5:20 PM | Feb 6, 2024 2:59 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0002-001 DETAIL FENCE TYPE 1,1A,2.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0002-001 DETAIL FENCE TYPE 1,1A,2 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 610 | 522803-01-RFAM-ME-0034-001_Duct Temp Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 23, 2024 11:23 AM | Feb 20, 2024 2:47 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0034-001_Duct Temp Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0034-001_Duct Temp Transmitter |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 18, 2024 4:05 PM): ME comment in attached document
CLOSED | 609 | 522803-01-RFAM-ME-0032-001_Duct Humidity Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 23, 2024 11:22 AM | Feb 27, 2024 5:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0032-001_Duct Humidity Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0032-001_Duct Humidity Transmitter |  | V1 | 1 | Approved | Updated review status
CLOSED | 608 | 522803-01-RFAM-ME-0031-001_Motorized Damper | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 23, 2024 11:21 AM | Feb 28, 2024 2:55 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0031-001_Motorized Damper.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0031-001_Motorized Damper |  | V1 | 1 | Make correction as noted & resubmit | Updated review status
CLOSED | 601 | 522803-01-RFAM-EL-0034-002_Battery Charging Unit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 22, 2024 1:04 PM | Feb 8, 2024 2:08 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0034-002_Battery Charging Unit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0034-002_Battery Charging Unit |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 8, 2024 2:08 AM): Please resubmit with AUR request Detail of power consumption for each panel shall be submitted
CLOSED | 600 | 522803-01-RFA-HSE-0012-001_Plan for scaffolding position with schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 22, 2024 9:23 AM | Jan 30, 2024 10:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0012-001_Plan for scaffolding position with schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0012-001_Plan for scaffolding position with schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 599 | 522803-01-RFA-HSE-0011-001_Planing for dust protection and fall protection | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 22, 2024 9:22 AM | Feb 1, 2024 9:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0011-001_Planing for dust protection and fall protection.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0011-001_Planing for dust protection and fall protection |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 597 | 522803-01-MS-HY-0001-002_Underground Pipe Work (HDPE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 22, 2024 9:02 AM | Feb 1, 2024 2:26 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0001-002_Underground Pipe Work (HDPE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0001-002_Underground Pipe Work (HDPE) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 596 | 522803-01-MS-FP-0001-002_Underground Pipe Work (HDPE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 22, 2024 9:00 AM | Feb 1, 2024 2:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-FP-0001-002_Underground Pipe Work (HDPE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1049_MS-FP_Request for Approval Method Statement (Fire Protection)/522803-01-MS-FP-0001-002_Underground Pipe Work (HDPE) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 592 | 522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 19, 2024 3:06 PM | Jan 23, 2024 9:40 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 592 | 522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 19, 2024 3:06 PM | Jan 23, 2024 9:40 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0012-001 CORE WALL STAIR-04 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 591 | 522803-01-MS-HY-0006-001_Pipe Sleeve Installation for Fuel System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 2:33 PM | Feb 1, 2024 2:17 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0006-001_Pipe Sleeve Installation for Fuel System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0006-001_Pipe Sleeve Installation for Fuel System |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 589 | 522803-01-RFAM-ME-0028-001_Valve and Piping Accessories | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 1:06 PM | Mar 4, 2024 9:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0028-001_Valve and Piping Accessories.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0028-001_Valve and Piping Accessories |  | V1 | 2 | Make correction as noted & proceed | Updated review status
CLOSED | 588 | 522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 12:02 PM | Feb 5, 2024 12:09 AM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 588 | 522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 12:02 PM | Feb 5, 2024 12:09 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0007-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 588 | 522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 12:02 PM | Feb 5, 2024 12:09 AM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0007-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0007-001_Lightning Protection and Grounding System Layout - Ground Floor |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 587 | 522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 11:46 AM | Feb 1, 2024 10:18 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 587 | 522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 11:46 AM | Feb 1, 2024 10:18 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0009-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 587 | 522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 11:46 AM | Feb 1, 2024 10:18 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0009-001_REVIT.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0009-001_Fire Detection and Alarm System Schematic - Sheet 1 to Sheet 11 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 582 | 522803-01-RFAM-EL-0057-001_Grounding Joint Cover for Ground Rack in Data Hall | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 10:34 AM | Feb 1, 2024 10:30 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0057-001_Grounding Joint Cover for Ground Rack in Data Hall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0057-001_Grounding Joint Cover for Ground Rack in Data Hall |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 581 | 522803-01-RFAM-ME-0007-002_Black Steel Pipe | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 19, 2024 10:27 AM | Jan 25, 2024 5:24 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0007-002_Black Steel Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0007-002_Black Steel Pipe |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jan 24, 2024 10:14 AM): ME reviewed in attached file.
CLOSED | 580 | 522803-01-RPT-ST-0016-001_Trial mix report of Qmix 23Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 18, 2024 5:25 PM | Jan 23, 2024 8:33 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0016-001_Trial mix report of Qmix 23Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0016-001_Trial mix report of Qmix 23 Nov23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 578 | 522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 18, 2024 3:55 PM | Feb 1, 2024 4:29 PM | 4 | 4 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 578 | 522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 18, 2024 3:55 PM | Feb 1, 2024 4:29 PM | 4 | 4 | 0 | 100% | Review closed | 4 | DRAWING FOR APPROVE GROUND FLOOR_PDU_R.2 17-01-24.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 578 | 522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 18, 2024 3:55 PM | Feb 1, 2024 4:29 PM | 4 | 4 | 0 | 100% | Review closed | 4 | DRAWING FOR APPROVE_2 FLOOR_PDU_R.2.17-01-24.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 578 | 522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 18, 2024 3:55 PM | Feb 1, 2024 4:29 PM | 4 | 4 | 0 | 100% | Review closed | 4 | DRAWING FOR APPROVE_5 FLOOR_PDU_R.2.17-01-24.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0008-001_PDU Panel Level 1F, 2F and 5F |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 577 | 522803-01-RPT-ST-0015-001_Trial mix report of M concrete on 08 Dec'23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 18, 2024 2:22 PM | Jan 22, 2024 7:04 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0015-001_Trial mix report of M concrete on 08 Dec'23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0015-001_Trial mix report of M concrete on 08 Dec'23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 575 | 522803-01-RFAS-ST-0001-005_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 18, 2024 2:10 PM | Jan 24, 2024 10:20 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-005_Structure Foundation Plan.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-005_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 575 | 522803-01-RFAS-ST-0001-005_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 18, 2024 2:10 PM | Jan 24, 2024 10:20 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-005_Structure Foundation Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-005_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 569 | 522803-01-RFAM-ME-0011-002_PIBCV Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 18, 2024 7:44 AM | Feb 22, 2024 10:00 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0011-002_PIBCV Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0011-002_PIBCV Valve |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 18, 2024 9:04 PM): ME comment in attached file.
CLOSED | 568 | 522803-01-RFAM-EL-0031-001_Riser Pole Incoming | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 17, 2024 3:48 PM | Jan 29, 2024 1:36 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0031-001_Riser Pole Incoming.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0031-001_Riser Pole Incoming |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 567 | 522803-01-RFAM-EL-0020-001_CB Box & Safety Switch | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 17, 2024 3:46 PM | Feb 1, 2024 1:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0020-001_CB Box_Safety Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0020-001_CB Box_Safety Switch |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 566 | 522803-01-ITP-MEP-0001-002_MEP Inspection Test Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 17, 2024 3:42 PM | Feb 1, 2024 10:33 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ITP-MEP-0001-002_MEP Inspection Test Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-MEP-0001-002_MEP Inspection Test Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 563 | 522803-01-RFAS-HY-0003-001_Pump Room | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 17, 2024 1:18 PM | Feb 6, 2024 1:22 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0003-001_Pump Room.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0003-001_Pump Room |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 562 | 522803-01-RPT-ST-0011-001_Trial mix report of Namheng concrete on 28Nov'23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 17, 2024 11:25 AM | Jan 22, 2024 6:37 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0011-001_Trial mix report of Namheng concrete on 28Nov'23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0011-001_Trial mix report of Namheng concrete on 28Nov'23 |  | V2 | 0 | Approved | Updated review status
CLOSED | 561 | 522803-01-RPT-ST-0014-001_Trial mix report of Insee concrete on 9Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 17, 2024 10:53 AM | Jan 22, 2024 7:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0014-001_Trial mix report of Insee concrete on 9Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0014-001_Trial mix report of Insee concrete on 9Nov23 |  | V2 | 0 | Approved | Updated review status
CLOSED | 560 | 522803-01-RPT-ST-0013-001_Trial mix report of Insee concrete on 1Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 17, 2024 10:53 AM | Jan 22, 2024 6:59 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0013-001_Trial mix report of Insee concrete on 1Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0013-001_Trial mix report of Insee concrete on 1Nov23 |  | V3 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 559 | 522803-01-RPT-ST-0012-001_Trial mix report of Insee concrete on 16Oct23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 17, 2024 10:50 AM | Jan 22, 2024 6:40 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0012-001_Trial mix report of Insee concrete on 16Oct23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0012-001_Trial mix report of Insee concrete on 16Oct23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 557 | 522803-01-RFAM-ME-0027-001_Butterfly Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 17, 2024 9:16 AM | Feb 28, 2024 3:51 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0027-001_Butterfly Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0027-001_Butterfly Valve |  | V2 | 2 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Feb 26, 2024 3:09 PM): ME comment in attached file.
CLOSED | 556 | 522803-01-RFAS-ST-0011-001 CORE WALL STAIR-02 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 17, 2024 9:16 AM | Jan 23, 2024 9:37 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0011-001 CORE WALL STAIR-02 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0011-001_CORE WALL STAIR-02 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 556 | 522803-01-RFAS-ST-0011-001 CORE WALL STAIR-02 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 17, 2024 9:16 AM | Jan 23, 2024 9:37 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0011-001 CORE WALL STAIR-02 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0011-001_CORE WALL STAIR-02 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 555 | 522803-01-RFAS-ST-0010-001 CORE WALL STAIR-01 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 17, 2024 8:58 AM | Jan 23, 2024 9:30 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0010-001 CORE WALL STAIR-01 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0010-001_CORE WALL STAIR-01 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 555 | 522803-01-RFAS-ST-0010-001 CORE WALL STAIR-01 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 17, 2024 8:58 AM | Jan 23, 2024 9:30 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0010-001 CORE WALL STAIR-01 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0010-001_CORE WALL STAIR-01 DETAIL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 553 | 522803-01-MS-CSA-0006-001_Method Statement of core wall works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 16, 2024 1:59 PM | Jan 30, 2024 10:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0006-001_Method Statement of core wall works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0006-001_Method Statment of core wall works |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 549 | 522803-01-RFAM-EL-0051-001_Color Code for Main and Common Body Panel | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 16, 2024 10:58 AM | Jan 19, 2024 8:02 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0051-001_Color Code for Main and Common Body Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0051-001_Color Code for Main and Common Body Panel |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 548 | 522803-01-MS-EL-0002-002_Underground Manhole of Medium Voltage and Communication Installation Work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 16, 2024 10:55 AM | Jan 29, 2024 2:01 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0002-002_Underground Manhole of Medium Voltage and Communication Installation Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0002-002_Underground Manhole of Medium Voltage and Communication Installation Work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 545 | 522803-01-RFA-LE-0004-002_IAQ Management during Construction Plan | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Jan 16, 2024 9:57 AM | Jan 25, 2024 9:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-LE-0004-002_IAQ Management during Construction Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0004-002_IAQ Management during Construction Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 544 | 522803-01-RPT-ST-0010-001_Trial mix report of Namheng concrete on 20Nov'23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 16, 2024 9:43 AM | Jan 18, 2024 5:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0010-001_Trial mix report of Namheng concrete on 20Nov'23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0010-001_Trial mix report of Namheng concrete on 20Nov'23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 543 | 522803-01-RPT-ST-0009-001_Trial mix report of Namheng concrete on 16Nov'23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 16, 2024 9:42 AM | Jan 18, 2024 5:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0009-001_Trial mix report of Namheng concrete on 16Nov'23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0009-001_Trial mix report of Namheng concrete on 16Nov'23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 542 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 15, 2024 4:12 PM | Jan 19, 2024 9:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 542 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 15, 2024 4:12 PM | Jan 19, 2024 9:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 542 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 15, 2024 4:12 PM | Jan 19, 2024 9:08 AM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2_DC.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0009-001 TRENCH DETAIL 1,2 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 540 | 522803-01-RPT-LE-0001-002_Monthly Report for LEED No.01 for October 2023 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Jan 15, 2024 9:21 AM | Jan 18, 2024 10:30 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0001-002_Monthly Report for LEED No.01 for October 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0001-002_Monthly Report for LEED No.01 for October 2023 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 538 | 522803-01-RPT-LE-0002-002_Monthly Report for LEED No.02 for November 2023 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Jan 14, 2024 6:14 PM | Jan 18, 2024 10:47 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0002-002_Monthly Report for LEED No.02 for November 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0002-002_Monthly Report for LEED No.02 for November 2023 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 537 | 522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 13, 2024 9:21 PM | Jan 19, 2024 8:59 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04).nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 537 | 522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 13, 2024 9:21 PM | Jan 19, 2024 8:59 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0005-002 MAINTENANCE PIT DETAIL (No.01-04) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 526 | 522803-01-CXP-MEP-0002-001_Equipment List (CxAlloy) for MEP System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 12, 2024 1:56 PM | Feb 5, 2024 2:16 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CXP-MEP-0002-001_Equipment List (CxAlloy) for MEP System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1084_CXP-MEP_Request for Approval Method Statement (Mechanical Electrical and Plumbing)/522803-01-CXP-MEP-0002-001_Equipment List (CxAlloy) for MEP System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 525 | 522803-01-RFAS-ST-0003-006 PAVEMENT PILING PLAN ALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 12, 2024 1:17 PM | Jan 30, 2024 10:28 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-006 PAVEMENT PILING PLAN ALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-006 PAVEMENT PILING PLAN ALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 524 | 522803-01-CXP-MEP-0001-001_List of Cx Method Statement for MEP System | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 12, 2024 1:11 PM | Jan 24, 2024 3:32 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-CXP-MEP-0001-001_List of Cx Method Statement for MEP System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1084_CXP-MEP_Request for Approval Method Statement (Mechanical Electrical and Plumbing)/522803-01-CXP-MEP-0001-001_List of Cx Method Statement for MEP System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 523 | 522803-01-RFAM-CV-0005-001_ Daikure for Galvanized material | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 12, 2024 11:17 AM | Jan 18, 2024 5:21 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0005-001_ Daikure for Galvanized material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0005-001_ Daikure for Galvanized material |  | V1 | 0 | Approved | Updated review status
CLOSED | 522 | 522803-01-RFAM-ME-0006-001_Side Stream Filtration Unit | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 12, 2024 10:49 AM | Feb 23, 2024 11:13 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0006-001_Side Stream Filtration Unit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0006-001_Side Stream Filtration Unit |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Feb 18, 2024 5:08 PM): ME comment in attached file
CLOSED | 520 | 522803-01-RFAM-HY-0018-001_Fuel Motorized Control Valve | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 12, 2024 8:09 AM | Feb 5, 2024 9:04 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0018-001_Fuel Motorized Control Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0018-001_Fuel Motorized Control Valve |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 519 | 522803-01-RFAM-ME-0009-001_Variable Air Volume (VAV) | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 12, 2024 8:06 AM | Feb 13, 2024 10:01 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0009-001_Variable Air Volume (VAV).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0009-001_Variable Air Volume (VAV) |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 517 | 522803-01-RFAM-ME-0026-001_Copper Tube | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:47 PM | Feb 1, 2024 4:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0026-001_Copper Tube.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0026-001_Copper Tube |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jan 31, 2024 1:23 PM): ME commented in attached file.
CLOSED | 516 | 522803-01-RFAM-ME-0025-001_Pipe Insulation | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:45 PM | Feb 13, 2024 9:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0025-001_Pipe Insulation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0025-001_Pipe Insulation |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 515 | 522803-01-RFAM-HY-0020-001_PVC Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:39 PM | Jan 22, 2024 8:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0020-001_PVC Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0020-001_PVC Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 514 | 522803-01-RFAM-HY-0019-001_PPR Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:38 PM | Jan 22, 2024 7:57 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0019-001_PPR Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0019-001_PPR Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 512 | 522803-01-MS-EL-0001-002_Underground Duct Bank of Installation (RTRC_HDPE Pipe) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:30 PM | Jan 22, 2024 12:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-EL-0001-002_Underground Duct Bank of Installation (RTRC_HDPE Pipe).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0001-002_Underground Duct Bank of Installation (RTRC_HDPE Pipe) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 511 | 522803-01-RFAM-EL-0052-001_Miscellaneous | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:23 PM | Jan 29, 2024 2:25 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0052-001_Miscellaneous.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0052-001_Miscellaneous |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 510 | 522803-01-RFAM-EL-0024-001_Public Address System | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 2:01 PM | Jan 29, 2024 2:35 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0024-001_Public Address System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0024-001_Public Address System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 509 | 522803-01-MS-HY-0005-001_Pipe Sleeve Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | sansamon s | -- | -- | Jan 11, 2024 1:56 PM | Jan 22, 2024 8:26 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-HY-0005-001_Pipe Sleeve Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0005-001_Pipe Sleeve Installation |  | V2 | 0 | Approved | Updated review status
CLOSED | 507 | 522803-01-RFAS-CV-0001-001 Foundation Fence Part-1,2,3,7 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 11, 2024 8:52 AM | Jan 24, 2024 10:24 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-CV-0001-001 Foundation Fence Part-1,2,3,7.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1151_RFAS-CV_Request for Approval Shop Drawings (Civil)/522803-01-RFAS-CV-0001-001_Foundation Fence Part-1,2,3,7 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 506 | 522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 11, 2024 7:57 AM | Jan 19, 2024 9:38 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 506 | 522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 11, 2024 7:57 AM | Jan 19, 2024 9:38 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0008-001_CORE WALL STAIR-03 DETAIL |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 505 | 522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 10, 2024 2:22 PM | Feb 6, 2024 2:52 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 505 | 522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 10, 2024 2:22 PM | Feb 6, 2024 2:52 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0007-001_GROUND FLOOR FRAMING PLAN OVERALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 503 | 522803-01-RFAM-HY-0021-001_Valves | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:59 PM | Jan 24, 2024 10:45 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0021-001_Valves.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0021-001_Valves |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 502 | 522803-01-RFAM-ME-0004-002_BTU Meter_Water Flow Meter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:52 PM | Feb 9, 2024 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0004-002_BTU Meter_Water Flow Meter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0004-002_BTU Meter_Water Flow Meter |  | V2 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 501 | 522803-01-RFAS-HY-0001-001_Hydraulics System | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:39 PM | Feb 2, 2024 1:19 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-HY-0001-001_Hydraulics System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1148_RFAS-HY_Request for Approval Shop Drawings (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAS-HY-0001-001_Hydraulics System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 500 | 522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:20 PM | Feb 1, 2024 5:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 500 | 522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:20 PM | Feb 1, 2024 5:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0001-002_CAD.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 500 | 522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:20 PM | Feb 1, 2024 5:20 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0001-002_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-002_Electrical Services MV and COMS Routing Layout (Underground) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 499 | 522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:19 PM | Feb 13, 2024 6:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 499 | 522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:19 PM | Feb 13, 2024 6:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0005-001_CAD.zip | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 499 | 522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 10, 2024 1:19 PM | Feb 13, 2024 6:34 PM | 3 | 0 | 3 | 100% | Review closed | 4 | RFAS-EL-0005-001_Revit.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0005-001_MSB, LVSB, OUSB, IUSB, and DUSB PANEL Level 1F |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 494 | 522803-01-RFAM-ME-0024-001_Water Pressure Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 9, 2024 4:44 PM | Feb 8, 2024 11:13 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0024-001_Water Pressure Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0024-001_Water Pressure Switch |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 493 | 522803-01-RFAM-ME-0023-001_High Accuracy Water Temp Sensor | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 9, 2024 4:39 PM | Feb 8, 2024 11:04 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0023-001_High Accuracy Water Temp Sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0023-001_High Accuracy Water Temp Sensor |  | V1 | 2 | Make correction as noted & proceed | Updated review status
CLOSED | 492 | 522803-01-RFAM-ME-0016-001 Water Diff. Pressure Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 9, 2024 4:36 PM | Feb 8, 2024 10:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0016-001_Water Diff. Pressure Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0016-001_Water Diff. Pressure Transmitter |  | V1 | 1 | Make correction as noted & proceed | Updated review status
CLOSED | 491 | 522803-01-RFA-HSE-0010-001_Tower crane number TC2 certificate | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 9, 2024 12:28 PM | Jan 10, 2024 2:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0010-001_Tower crane number TC2 certificate.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0010-001_Tower crane number TC2 certificate |  | V1 | 0 | Approved | Updated review status
CLOSED | 488 | 522803-01-RFAM-HY-0010-001_BSP FUEL PIPE (Above Ground) | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Jan 9, 2024 10:04 AM | Jan 22, 2024 6:45 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0010-001_BSP FUEL PIPE (Above Ground).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0010-001_BSP FUEL PIPE (Above Ground) |  | V1 | 0 | Approved | Updated review status
CLOSED | 487 | 522803-01-RFAM-ME-0022-001 VAV PSU Panel | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 9, 2024 9:54 AM | Jan 12, 2024 10:23 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0022-001 VAV PSU Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0022-001_VAV PSU Panel |  | V1 | 3 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jan 10, 2024 3:15 PM): ME counselled with EE and commented in attached file.
CLOSED | 486 | 522803-01-RFAM-EL-0042-001_Central Lighting Control System | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 9, 2024 9:39 AM | May 7, 2024 10:24 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0042-001_Central Lighting Control System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0042-001_Central Lighting Control System |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(May 7, 2024 10:24 AM): outside building , facade, office area, Lobby on process lighting design by lighting designer please contact K.Sarunyu GSA for the detail beforeorder the material
CLOSED | 485 | 522803-01-RFAM-EL-0021-001_Low Voltage Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Jan 8, 2024 5:08 PM | Jan 24, 2024 3:52 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0021-001_Low Voltage Switchboard.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0021-001_Low Voltage Switchboard |  | V2 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 24, 2024 3:52 PM): Please cooperate with AUR to update Cather UPS SLD and resubmit
CLOSED | 484 | 522803-01-RPT-CV-0001-001 Pile factory inspection | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 8, 2024 3:38 PM | Jan 11, 2024 1:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-CV-0001-001 Pile factory inspection.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1471_RPT-CV_Request for Approval Report (Civil)/522803-01-RPT-CV-0001-001 Pile factory inspection |  | V1 | 0 | Approved | Updated review status
CLOSED | 483 | 522803-01-CAL-ST-0001-001_Calculation for forming of substructure Column RC wall and Core wall | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | kanittha sirijantra | -- | -- | Jan 8, 2024 1:34 PM | Jan 16, 2024 1:19 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-CAL-ST-0001-001_Calculation for forming of substructure_Column RC wall and Core wall.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1126_CAL-ST_Request for Approval Calculation (Structure)/522803-01-CAL-ST-0001-001_Calculation for forming of substructure_Column RC wall and Core wall |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 481 | 522803-01-RFAM-EL-0049-001_Inserts | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 8, 2024 10:02 AM | Jan 24, 2024 3:17 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0049-001_Inserts.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0049-001_Inserts |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 480 | 522803-01-RFAM-EL-0048-001_Lighting Fixture | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 8, 2024 10:00 AM | Jan 24, 2024 2:35 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0048-001_Lighting Fixture.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0048-001_Lighting Fixture |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 24, 2024 2:34 PM): Please resubmit with Lux simulation
CLOSED | 478 | 522803-01-RFAM-EL-0050-001_Flexible Metal Conduit, Fitting and Acc | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 3:42 PM | Jan 17, 2024 10:11 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0050-001_Flexible Metal Conduit, Fitting and Acc.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0050-001_Flexible Metal Conduit, Fitting and Acc |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 474 | 522803-01-MS-CSA-0005-002_Method statement of retaining wall and fence gutter | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 5, 2024 1:41 PM | Jan 11, 2024 1:01 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0005-002_Method statement of retaining wall and fence gutter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0005-002_Method statement of retaining wall and fence gutter |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 473 | 522803-01-RFAS-FP-0002-001_Fire Pump Room | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 11:46 AM | Jan 16, 2024 3:44 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-FP-0002-001_Fire Pump Room.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1149_RFAS-FP_Request for Approval Shop Drawings (Fire Protection)/522803-01-RFAS-FP-0002-001_Fire Pump Room |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 472 | 522803-01-RFAM-EL-0033-001_Power Distribution Unit (PDU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 10:06 AM | Jan 24, 2024 4:33 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0033-001_Power Distribution Unit (PDU).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0033-001_Power Distribution Unit (PDU) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 24, 2024 4:32 PM): front access only color code will applied same as LV panel
CLOSED | 471 | 522803-01-RFAM-ME-0007-001_Black Steel Pipe | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 8:41 AM | Jan 10, 2024 3:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0007-001_Black Steel Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0007-001_Black Steel Pipe |  | V1 | 0 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jan 8, 2024 5:28 PM): ME commented in DC file
CLOSED | 470 | 522803-01-RFAM-EL-0043-001_Emergency and Exit Light | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 8:38 AM | Jan 28, 2024 2:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0043-001_Emergency and Exit Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0043-001_Emergency and Exit Light |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jan 28, 2024 2:42 PM): The exit sign backup time shall cover warranties period
CLOSED | 469 | 522803-01-RFAM-EL-0030-001_Switch and Outlet | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 5, 2024 8:35 AM | Jan 21, 2024 9:41 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0030-001_Switch and Outlet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0030-001_Switch and Outlet |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 21, 2024 9:40 AM): Panasonic is fine but can we have a sample to verify the shape, color? the picture in the document looks simple but it is not modernized!
CLOSED | 468 | 522803-01-RPT-LE-0003-001_Monthly Report for LEED No.03 for December 2023 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 3:15 PM | Jan 10, 2024 4:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-LE-0003-001_Monthly Report for LEED No.03 for December 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0003-001_Monthly Report for LEED No.03 for December 2023 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 467 | 522803-01-RPT-ST-0006-002_Trial mix report of Qmix10Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 3:10 PM | Jan 8, 2024 5:47 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0006-002_Trial mix report of Qmix10Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0006-002_Trial mix report of Qmix10Nov23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 466 | 522803-01-RFA-HSE-0009-001_Tower crane number TC1, TC3 certificate | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 3:01 PM | Jan 8, 2024 6:16 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0009-001_Tower crane number TC1, TC3 certificate.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0009-001_Tower crane number TC1, TC3 certificate |  | V1 | 0 | Approved | Updated review status
CLOSED | 463 | 522803-01-RFAM-ME-0021-001_Air Differential Pressure Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 1:59 PM | Jan 16, 2024 11:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0021-001_Air Differential Pressure Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0021-001_Air Differential Pressure Switch |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jan 14, 2024 4:05 PM): ME comment in attached file.
CLOSED | 462 | 522803-01-RFAM-ME-0019-001_Duct Smoke Detector | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 1:55 PM | Jan 11, 2024 2:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0019-001_Duct Smoke Detector.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0019-001_Duct Smoke Detector |  | V1 | 0 | Approved | Updated review status | Kloer Chongchaikit(Jan 9, 2024 1:57 PM): ME reviewed in DC file.(Edited Jan 9, 2024 1:58 PM)
CLOSED | 460 | 522803-01-RFAM-ME-0020-001_Water Pressure Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 1:32 PM | Jan 15, 2024 10:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0020-001_Water Pressure Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0020-001_Water Pressure Transmitter |  | V1 | 1 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jan 11, 2024 1:24 PM): ME commented in attached file.
CLOSED | 459 | 522803-01-RFAM-ME-0018-001_Air Flow Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 1:29 PM | Jan 12, 2024 10:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0018-001_Air Flow Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0018-001_Air Flow Switch |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jan 10, 2024 4:36 PM): ME reviewed in attached file.
CLOSED | 458 | 522803-01-RFAM-ME-0015-001_Water Diff. Pressure Switch | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 1:26 PM | Jan 15, 2024 10:32 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0015-001_Water Diff. Pressure Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0015-001_Water Diff. Pressure Switch |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Jan 10, 2024 3:32 PM): ME commented in attached file.
CLOSED | 455 | 522803-01-RFAM-FP-0004-002_Fire pump and Jockey pump with controller | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 12:01 PM | Jan 12, 2024 5:39 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0004-002_Fire pump and Jockey pump with controller.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0004-002_Fire pump and Jockey pump with controller |  | V1 | 0 | Approved | Updated review status
CLOSED | 454 | 522803-01-RFAM-ME-0017-001_CO2 sensor | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 11:47 AM | Jan 12, 2024 9:27 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0017-001_CO2 sensor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0017-001_CO2 sensor |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jan 10, 2024 1:39 PM): ME commented in attached file.
CLOSED | 453 | 522803-01-RFAM-ME-0014-001_RH Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 11:31 AM | Jan 12, 2024 5:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0014-001_RH Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0014-001_RH Transmitter |  | V1 | 2 | Approved | Updated review status | Kloer Chongchaikit(Jan 9, 2024 5:26 PM): ME reviewed in attached file.
CLOSED | 452 | 522803-01-RFAM-ME-0013-001_RT Transmitter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | sansamon s | -- | -- | Jan 4, 2024 11:25 AM | Jan 12, 2024 5:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0013-001_RT Transmitter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0013-001_RT Transmitter |  | V1 | 1 | Approved | Updated review status | Kloer Chongchaikit(Jan 9, 2024 5:24 PM): ME reviewed in the attached file.
CLOSED | 451 | 522803-01-RPT-HSE-0002-001_Result of environmental monitoring No.2 (16 Nov-15 Dec 23) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 11:09 AM | Jan 8, 2024 6:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0002-001_Result of environmental monitoring No.2 (16 Nov-15 Dec 23).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0002-001_Result of environmental monitoring No.2 (16 Nov-15 Dec 23) |  | V1 | 0 | Approved | Updated review status
CLOSED | 450 | 522803-01-RPT-HSE-0001-001_Result of environmental monitoring No.1 (1-15 Nov 23) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 11:06 AM | Jan 8, 2024 6:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-HSE-0001-001_Result of environmental monitoring No.1 (1-15 Nov 23).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1462_RPT-HSE_Request for Approval Report (Health Safety Environment)/522803-01-RPT-HSE-0001-001_Result of environmental monitoring No.1 (1-15 Nov 23) |  | V1 | 0 | Approved | Updated review status
CLOSED | 449 | 522803-01-RFAM-ST-0010-004_CPAC_s ready mix concrete_adjust water per binder | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Jan 4, 2024 9:40 AM | Jan 11, 2024 1:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0010-004_CPAC_s ready mix concrete_adjust water per binder.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0010-004_CPAC_s ready mix concrete_adjust water per binder |  | V1 | 0 | Approved | Updated review status
CLOSED | 448 | 522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Jan 3, 2024 11:14 AM | Jan 28, 2024 2:36 PM | 3 | 3 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jan 28, 2024 2:35 PM): please proceed with latest drawing
CLOSED | 448 | 522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Jan 3, 2024 11:14 AM | Jan 28, 2024 2:36 PM | 3 | 3 | 0 | 100% | Review closed | 4 | CAD_Detail of mamhole MV _ COMMU_23-12-2023_R01.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 448 | 522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Jan 3, 2024 11:14 AM | Jan 28, 2024 2:36 PM | 3 | 3 | 0 | 100% | Review closed | 4 | TSC_V23_NEXT-01_EXTERNAL WORK_SHOP_EL.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-002_DETAIL OF MANHOLE (MV and COMMU) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 447 | 522803-01-RFAM-HY-0005-002_Underground fuel tank | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Jan 3, 2024 10:51 AM | Jan 24, 2024 9:41 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0005-002_Underground fuel tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0005-002_Underground fuel tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 443 | 522803-01-RFAM-EL-0045-001_Busway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 4:59 PM | Jan 21, 2024 9:31 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0045-001_Busway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0045-001_Busway |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 21, 2024 9:31 AM): -bus duct outside the room on the roof floor shall IP68 (IP68 โซนนอกห้องทั้งหมด ในชั้น Roof) -As AUR comment please highlight bus duct for Mechanic load. GSA CLIENT(Jan 21, 2024 9:31 AM): Please revise and resubmit this document
CLOSED | 436 | 522803-01-MS-HY-0003-001_UG Fuel Tank | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 3:17 PM | Jan 16, 2024 2:29 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-HY-0003-001_UG Fuel Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0003-001_UG Fuel Tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 435 | 522803-01-RFAM-ME-0012-001_Thermal Energy Storage Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 3:15 PM | Jan 10, 2024 8:50 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0012-001_Thermal Energy Storage Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0012-001_Thermal Energy Storage Tank |  | V1 | 1 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Jan 3, 2024 1:25 PM): Mech reviewed in DC file
CLOSED | 434 | 522803-01-RFAM-HY-0017-001_Galvanized Steel Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 3:12 PM | Jan 9, 2024 6:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0017-001_Galvanized Steel Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0017-001_Galvanized Steel Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 433 | 522803-01-RFAM-FP-0011-001_Galvanized steel pipe and Hot Dipped Galvanized steel pipe | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 3:09 PM | Jan 5, 2024 11:13 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0011-001_Galvanized steel pipe and Hot Dipped Galvanized steel pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0011-001_Galvanized steel pipe and Hot Dipped Galvanized steel pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 432 | 522803-01-RFAM-FP-0010-001_Black steel pipe | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 3:05 PM | Jan 5, 2024 1:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0010-001_Black steel pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0010-001_Black steel pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 431 | 522803-01-RFAM-EL-0047-001_Color Code for LV Switchboard | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 2:52 PM | Jan 17, 2024 8:23 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0047-001_Color Code for LV Switchboard.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0047-001_Color Code for LV Switchboard |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 17, 2024 8:22 PM): Please resubmit with the color as GSA selected and submit example painting to GSA
CLOSED | 430 | 522803-01-RFAM-EL-0046-001_Low Voltage Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 2:48 PM | Jan 21, 2024 9:17 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0046-001_Low Voltage Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0046-001_Low Voltage Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jan 21, 2024 9:17 AM): Please update cable sizing around UPS ares because UPS configuration will change after GSA award UPS supplier
CLOSED | 429 | 522803-01-RFAM-EL-0011-002_Raceway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 2:42 PM | Jan 21, 2024 9:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0011-002_Raceway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0011-002_Raceway |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jan 21, 2024 9:13 AM): บริเวณที่เป็น Epoxy powder coating ต้องไม่ให้มีสีถลอก บริเวณที่ตัด หรือเจาะ ต้องเก็บสีเพื่อกันสนิมและความสวยงามให้เรียบร้อย GSA มีสิทธ์ของเปลี่ยนสินค้าทั้งท่อนในกรณีที่งานไม่เรียบร้อย ถึงแม้ว่าใน Raceway นั้นมีสายไฟฟ้าเดินแล้วก็ตาม
CLOSED | 428 | 522803-01-RFAM-EL-0007-002_Earthing and Lightning system | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 27, 2023 2:36 PM | Jan 31, 2024 11:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0007-002_Earthing and Lightning system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0007-002_Earthing and Lightning system |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Jan 31, 2024 11:55 PM): Grounding system shall comply with TIA942B, TIA607C as minimum, Please see comment in attached file and cross check illustrative above if we missing some point
CLOSED | 425 | 522803-01-RPT-LE-0002-001_Monthly Report for LEED No.02 for November 2023 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Dec 26, 2023 10:24 AM | Jan 9, 2024 11:59 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-LE-0002-001_Monthly Report for LEED No.02 for November 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0002-001_Monthly Report for LEED No.02 for November 2023 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 424 | 522803-01-RPT-LE-0001-001_Monthly Report for LEED No.01 for October 2023 | (TTI) Request for Approval (AUR_LEED Team Review) - Main Contractor | nittaya p | -- | -- | Dec 26, 2023 10:23 AM | Jan 4, 2024 4:53 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-LE-0001-001_Monthly Report for LEED No.01 for October 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1475_RPT-LE_Request for Approval Report (LEED)/522803-01-RPT-LE-0001-001_Monthly Report for LEED No.01 for October 2023 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 420 | 522803-01-RFAS-EL-0003-001_LV SINGLE LINE DIAGRAM BUILDING LOAD MSB | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 26, 2023 8:48 AM | Jan 24, 2024 12:40 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0003-001_LV SINGLE LINE DIAGRAM BUILDING LOAD MSB.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0003-001_LV SINGLE LINE DIAGRAM BUILDING LOAD MSB |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 24, 2024 12:32 PM): please revise and resubmit as comment.
CLOSED | 418 | 522803-01-RFAM-EL-0044-001_Street Light | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 25, 2023 2:49 PM | Jan 21, 2024 9:45 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0044-001_Street Light.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0044-001_Street Light |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 21, 2024 9:45 AM): please resubmit with AUR comment
CLOSED | 415 | 522803-01-RFA-LE-0004-001_IAQ Management during Construction Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 25, 2023 9:41 AM | Dec 28, 2023 5:47 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-LE-0004-001_IAQ Management during Construction Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0004-001_IAQ Management during Construction Plan |  | V2 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 414 | 522803-01-RFA-LE-0002-002_Waste Management Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 23, 2023 11:46 AM | Dec 28, 2023 5:52 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-LE-0002-002_Waste Management Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0002-002_Waste Management Plan |  | V1 | 0 | Approved | Updated review status
CLOSED | 413 | 522803-01-RFAS-ST-0006-001_SECTION RETAINING WALL THAIWATSADU SIDE | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 22, 2023 2:06 PM | Jan 16, 2024 1:23 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0006-001_SECTION RETAINING WALL THAIWATSADU SIDE.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0006-001_SECTION RETAINING WALL THAIWATSADU SIDE |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 412 | 522803-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 22, 2023 2:05 PM | Jan 3, 2024 4:44 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 5228203-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4.nwd | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 412 | 522803-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 22, 2023 2:05 PM | Jan 3, 2024 4:44 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 5228203-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0005-001_DETAIL MAINTENANCE PIT FOR TOILET No1-4 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 411 | 522803-01-RFA-LE-0001-002_ESC Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 22, 2023 1:36 PM | Dec 28, 2023 6:05 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-LE-0001-002_ESC Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0001-002_ESC Plan |  | V1 | 0 | Approved | Updated review status
CLOSED | 410 | 522803-01-ITP-HSE-0001-002_Environmental workplace monitoring plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 22, 2023 1:27 PM | Jan 9, 2024 8:21 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-ITP-HSE-0001-002_Environmental workplace monitoring plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-HSE-0001-002_Environmental workplace monitoring plan |  | V1 | 0 | Approved | Updated review status
CLOSED | 409 | 522803-01-RFAM-FP-0007-001_Fire extinguisher | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 21, 2023 3:51 PM | Jan 8, 2024 1:43 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0007-001_Fire extinguisher.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0007-001_Fire extinguisher |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 408 | 522803-01-RPT-ST-0008-001_Trial mix report of M concrete on 7Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 21, 2023 1:34 PM | Jan 8, 2024 5:51 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0008-001_Trial mix report of M concrete on 7Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0008-001_Trial mix report of M concrete on 7Nov23 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 407 | 522803-01-RFAM-EL-0040-001_Load Center | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 21, 2023 12:23 PM | Jan 9, 2024 2:36 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0040-001_Load Center.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0040-001_Load Center |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 406 | 522803-01-RFAM-FP-0009-001_Valve | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 21, 2023 12:12 PM | Jan 8, 2024 4:32 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0009-001_Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0009-001_Valve |  | V1 | 0 | Approved | Updated review status
CLOSED | 405 | 522803-01-RFAM-FP-0008-001 Fire hose cabinet | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 21, 2023 12:09 PM | Jan 8, 2024 4:47 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0008-001_Fire hose cabinet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0008-001_Fire hose cabinet |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 404 | 522803-01-RFAM-EL-0041-001_Explosion Proof Device | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 4:56 PM | Jan 10, 2024 1:15 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0041-001_Explosion Proof Device.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0041-001_Explosion Proof Device |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 403 | 522803-01-RFAM-ME-0011-001_PIBCV Valve | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 4:56 PM | Jan 12, 2024 5:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0011-001_PIBCV Valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0011-001_PIBCV Valve |  | V1 | 0 | Make correction as noted & proceed | Updated review status | Kloer Chongchaikit(Jan 8, 2024 12:16 PM): ME comment in DC file.
CLOSED | 402 | 522803-01-RFAM-FP-0005-001_Alarm valve | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 4:55 PM | Dec 28, 2023 4:07 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0005-001_Alarm valve.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0005-001_Alarm valve |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 401 | 522803-01-RFAM-FP-0006-001_Sprinkler head | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 4:55 PM | Dec 28, 2023 5:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0006-001_Sprinkler head.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0006-001_Sprinkler head |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 397 | 522803-01-RFA-ST-0001-001_Concrete casting section | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 4:41 PM | Jan 3, 2024 7:47 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-ST-0001-001_Concrete casting section.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1026_RFA-ST_Request for Approval (Structure)/522803-01-RFA-ST-0001-001_Concrete casting section |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 395 | 522803-01-RFAS-EL-0004-001_MVSG SLD | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 3:37 PM | Feb 1, 2024 5:48 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0004-001_MVSG SLD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0004-001_MVSG SLD |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Feb 1, 2024 5:48 PM): please no hatch in HVSB SLD SLD has not updated please resubmit with update DWG
CLOSED | 389 | 522803-01-RFAM-HY-0014-001_FUEL SENSOR | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 20, 2023 1:58 PM | Dec 28, 2023 11:15 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0014-001_FUEL SENSOR.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0014-001_FUEL SENSOR |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 388 | 522803-01-RFAS-ST-0003-005_PAVEMENT PILING PLAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 19, 2023 4:59 PM | Dec 26, 2023 10:34 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-005_PAVEMENT PILING PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-005_PAVEMENT PILING PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 386 | 522803-01-RFAM-ME-0010-001_MV Fan | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 19, 2023 11:19 AM | Jan 9, 2024 2:27 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0010-001_MV Fan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0010-001_MV Fan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Jan 3, 2024 6:41 PM): Mech reviewed in DC file
CLOSED | 383 | 522803-01-RFAM-HY-0015-001 Fuel Management System | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 4:23 PM | Jan 12, 2024 11:18 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0015-001_Fuel Management System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0015-001_Fuel Management System |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 382 | 522803-01-RFAM-ME-0008-001_Chemical feed pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 1:27 PM | Dec 28, 2023 6:32 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0008-001_Chemical feed pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0008-001_Chemical feed pump |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Dec 26, 2023 7:21 PM): ME reviewed in DC file.(Edited Dec 26, 2023 7:21 PM)
CLOSED | 381 | 522803-01-RFAM-EL-0035-001_Cable Basket Tray | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 1:21 PM | Dec 28, 2023 6:10 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0035-001_Cable Basket Tray.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0035-001_Cable Basket Tray |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 28, 2023 6:09 PM): Please clear the brand/model as the AUR comment
CLOSED | 380 | 522803-01-RFAM-EL-0034-001_Battery Charging Unit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 1:20 PM | Dec 29, 2023 12:29 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0034-001_Battery Charging Unit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0034-001_Battery Charging Unit |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 29, 2023 12:28 AM): please comments \in attached file
CLOSED | 379 | 522803-01-RFAM-HY-0016-001_FUEL PUMP | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 12:00 PM | Jan 12, 2024 5:23 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0016-001_FUEL PUMP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0016-001_FUEL PUMP |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 378 | 522803-01-RFAM-ST-0020-001_EPS foam | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 18, 2023 9:09 AM | Dec 26, 2023 10:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0020-001_EPS foam.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0020-001_EPS foam |  | V1 | 0 | Approved | Updated review status
CLOSED | 377 | 522803-01-RFAM-EL-0027-001_Low Voltage Current Transformer | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 15, 2023 3:31 PM | Dec 28, 2023 6:23 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0027-001_Low Voltage Current Transformer.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0027-001_Low Voltage Current Transformer |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 28, 2023 6:22 PM): the drawing will be updated please update the reason why selected 2 brands
CLOSED | 373 | 522803-01-RPT-ST-0007-001_Lab test data of existing soil of Next01 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 15, 2023 11:28 AM | Jan 8, 2024 5:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0007-001_Lab test data of existing soil of Next01.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0007-001_Lab test data of existing soil of Next01 |  | V1 | 0 | Approved | Updated review status
CLOSED | 372 | 522803-01-MS-EL-0003-001_Grounding Works | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 3:39 PM | Dec 28, 2023 5:44 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-EL-0003-001_Grounding Works.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0003-001_Grounding Works |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 28, 2023 5:36 PM): Many comments from AUR, To protect miss communication. please resubmits with AUR comments.
CLOSED | 371 | 522803-01-MS-CSA-0005-001_Method statement of retaining wall and fence gutter | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 3:29 PM | Jan 8, 2024 9:39 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0005-001_Method statement of retaining wall and fence gutter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0005-001_Method statement of retaining wall and fence gutter |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 368 | 522803-01-RPT-ST-0006-001_Trial mix report of Qmix10Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 11:53 AM | Dec 20, 2023 9:03 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RPT-ST-0006-001_Trial mix report of Qmix10Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0006-001_Trial mix report of Qmix10Nov23 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 367 | 522803-01-RPT-ST-0005-001_Trial mix report of Qmix2Nov23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 11:53 AM | Dec 20, 2023 9:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0005-001_Trial mix report of Qmix2Nov23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0005-001_Trial mix report of Qmix2Nov23 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 366 | 522803-01-RPT-ST-0004-001_Trial mix report of Namheng17&18Oct23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 11:51 AM | Dec 20, 2023 8:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0004-001_Trial mix report of Namheng17&18Oct23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0004-001_Trial mix report of Namheng17&18Oct23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 365 | 522803-01-RPT-ST-0003-001_Trial mix report of Qmix16Oct23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 11:50 AM | Dec 20, 2023 8:57 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0003-001_Trial mix report of Qmix16Oct23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0003-001_Trial mix report of Qmix16Oct23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 363 | 522803-01-RFAM-HY-0013-001_Water Heater | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 14, 2023 11:16 AM | Jan 9, 2024 4:12 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0013-001_Water Heater.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0013-001_Water Heater |  | V1 | 0 | Approved | Updated review status
CLOSED | 359 | 522803-01-RFAM-EL-0036-001_Power Outlet | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 13, 2023 3:37 PM | Dec 29, 2023 12:39 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0036-001_Power Outlet.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0036-001_Power Outlet |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Dec 29, 2023 12:38 AM): Jedsada: Please add the power outlet: 3P,N+ G power outlet i.e. staging room as it is missing from the list
CLOSED | 358 | 522803-01-RFAM-EL-0017-001_Raceway for Fiber Optic | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 13, 2023 3:30 PM | Dec 29, 2023 12:50 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0017-001_Raceway for Fiber Optic.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0017-001_Raceway for Fiber Optic |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Dec 29, 2023 12:49 AM): Please recheck layout for internal network (ECMS, Security, internal network) We will use ELV riser for vertical routing (Edited Dec 29, 2023 12:49 AM)
CLOSED | 357 | 522803-01-RFAM-EL-0038-001_Earth Fault Relay | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 13, 2023 2:26 PM | Dec 29, 2023 12:54 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0038-001_Earth Fault Relay.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0038-001_Earth Fault Relay |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 29, 2023 12:53 AM): Please recheck earth fault/GF relay quantity shall install follow the drawing, and please follow AUR comment
CLOSED | 356 | 522803-01-RFAM-ST-0010-003_CPAC s ready mix concrete_Change crystalline to SIKA brand | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 13, 2023 2:07 PM | Dec 20, 2023 12:28 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0010-003_CPAC s ready mix concrete_Change crystalline to SIKA brand.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0010-003_CPAC s ready mix concrete_Change crystalline to SIKA brand |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 355 | 522803-01-RFAM-HY-0012-001 Fuel Tank Monitoring Panel | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 13, 2023 11:45 AM | Dec 28, 2023 11:25 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0012-001_Fuel Tank Monitoring Panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0012-001_Fuel Tank Monitoring Panel |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 354 | 522803-01-RFAM-ST-0012-003_Siam city ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 1:59 PM | Dec 19, 2023 8:03 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0012-003_Siam city ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0012-003_Siam city ready mix concrete |  | V2 | 0 | Approved | Updated review status
CLOSED | 349 | 522803-01-RFAM-HY-0009-001_DOUBLE SKINNED FUEL PIPE | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 12:13 PM | Dec 28, 2023 10:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0009-001_DOUBLE SKINNED FUEL PIPE.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0009-001_DOUBLE SKINNED FUEL PIPE |  | V1 | 0 | Approved | Updated review status
CLOSED | 348 | 522803-01-RFAM-ME-0004-001_BTU, Flow Meter | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 11:28 AM | Dec 26, 2023 1:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0004-001_BTU, Flow Meter.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0004-001_BTU, Flow Meter |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Dec 25, 2023 9:28 AM): ME commented in DC
CLOSED | 347 | 522803-01-RFAM-HY-0008-001_Fuel Polishing System | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 10:48 AM | Dec 26, 2023 9:45 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0008-001_Fuel Polishing System.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0008-001_Fuel Polishing System |  | V1 | 0 | Approved | Updated review status
CLOSED | 346 | 522803-01-RFAM-HY-0007-001_Booster and Transfer Pump | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 10:47 AM | Dec 26, 2023 11:49 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0007-001_Booster and Transfer Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0007-001_Booster and Transfer Pump |  | V1 | 0 | Approved | Updated review status
CLOSED | 345 | 522803-01-RFAM-ME-0005-001_CHW, CDW Pump | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 10:46 AM | Jan 10, 2024 5:06 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0005-001_CHW, CDW Pump.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0005-001_CHW, CDW Pump |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Kloer Chongchaikit(Jan 8, 2024 1:23 AM): ME reviewed.
CLOSED | 344 | 522803-01-RFAM-ME-0003-001_Chilled and Condenser water pipe (Pipe size 700mm and above) | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 10:46 AM | Dec 20, 2023 8:42 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0003-001_Chilled and Condenser water pipe (Pipe size 700mm and above).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0003-001_Chilled and Condenser water pipe (Pipe size 700mm and above) |  | V1 | 0 | Approved | Updated review status | Kloer Chongchaikit(Dec 20, 2023 5:23 PM): Approved with detail as noted inside.
CLOSED | 343 | 522803-01-RFAM-ME-0002-001_Expansion Tank | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 12, 2023 10:44 AM | Dec 28, 2023 10:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0002-001_Expansion Tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0002-001_Expansion Tank |  | V1 | 0 | Approved | Updated review status | Kloer Chongchaikit(Dec 25, 2023 10:16 AM): ME commented in DC
CLOSED | 339 | 522803-01-RFAS-ST-0003-004_PAVEMENT PILING PLAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 8, 2023 10:49 AM | Dec 19, 2023 12:03 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-004_PAVEMENT PILING PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-004_PAVEMENT PILING PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 339 | 522803-01-RFAS-ST-0003-004_PAVEMENT PILING PLAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 8, 2023 10:49 AM | Dec 19, 2023 12:03 PM | 2 | 2 | 0 | 100% | Review closed | 4 | TTI_V23_NEXT-01_EXTERNAL WORK_SHOP_CIVIL_20231208.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-004_PAVEMENT PILING PLAN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 338 | 522803-01-RFAM-ME-0001-001_VSD | (TTI) Request for Approval (AUR_Mechanical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 8, 2023 10:37 AM | Jan 10, 2024 11:45 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ME-0001-001_VSD.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1167_RFAM-ME_Request for Approval Material (Mechanical)/522803-01-RFAM-ME-0001-001_VSD |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Jan 10, 2024 11:45 AM): please recheck and resubmit harmonics calculation, The transformer in Next01 project calculated base on THDI lower than 5% please see harmonic K-Factor,Tx calculation file from AUR
CLOSED | 334 | 522803-01-RFAM-FP-0003-001_Pre-Action Valve with Compressor | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 8, 2023 9:47 AM | Dec 20, 2023 8:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0003-001_Pre-Action Valve with Compressor.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0003-001_Pre-Action Valve with Compressor |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 333 | 522803-01-RFAM-ST-0019-002_Sand backfill of D.point_Add Report | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 8, 2023 8:27 AM | Dec 19, 2023 12:27 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0019-002_Sand backfill of D.point_Add Report.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0019-002_Sand backfill of D.point_Add Reportv |  | V1 | 0 | Approved | Updated review status
CLOSED | 332 | 522803-01-RFAM-EL-0037-001_Metallic Conduit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 7, 2023 2:49 PM | Dec 14, 2023 12:22 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0037-001_Metallic Conduit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0037-001_Metallic Conduit |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 330 | 522803-01-RPT-ST-0002-001_Trial mix report of Cpac_28Oct23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 7, 2023 9:48 AM | Dec 18, 2023 9:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0002-001_Trial mix report of Cpac_28Oct23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0002-001_Trial mix report of Cpac_28Oct23 |  | V1 | 0 | Approved | Updated review status
CLOSED | 326 | 522803-01-RFA-HSE-0003-002_Certificate equipment lifting hook | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 6, 2023 4:21 PM | Dec 18, 2023 9:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0003-002_Certificate equipment lifting hook.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0003-002_Certificate equipment lifting hook |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 325 | 522803-01-MS-CSA-0004-002_Method statement of foundation deep zone (Additional safety procedure) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 6, 2023 3:54 PM | Dec 9, 2023 11:24 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0004-002_Method statement of foundation deep zone (Additional safety procedure).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0004-002_Method statement of foundation deep zone (Additional safety procedure) |  | V3 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 324 | 522803-01-RPT-ST-0001-001_Trial mix of M concrete on 27Oct23 report | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 6, 2023 2:51 PM | Dec 18, 2023 9:11 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-ST-0001-001_Trial mix of M concrete on 27Oct23 report.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1466_RPT-ST_Request for Approval Report (Structure)/522803-01-RPT-ST-0001-001_Trial mix of M concrete on 27Oct23 report |  | V1 | 0 | Approved | Updated review status
CLOSED | 310 | 522803-01-RFAM-ST-0019-001_Sand backfill of D.point | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 5, 2023 10:32 AM | Dec 8, 2023 10:14 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0019-001_Sand backfill of D.point.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0019-001_Sand backfill of D.point |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 309 | 522803-01-RFAM-ST-0017-001_Bonding concrete liquid | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 5, 2023 10:22 AM | Dec 8, 2023 10:11 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0017-001_Bonding concrete liquid.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0017-001 Bonding concrete liquid |  | V1 | 0 | Approved | Updated review status
CLOSED | 307 | 522803-01-MRPT-GEN-0002_001_TTI Monthly Construction No.02_November 2023 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 4:46 PM | Jan 9, 2024 8:32 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0002_001_TTI Monthly Construction No.02_November 2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0002-001_TTI Monthly Construction No.02_November 2023 |  | V3 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 306 | 522803-01-RFAM-HY-0006-001_FUEL FLOW METER | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 3:51 PM | Dec 19, 2023 3:58 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0006-001_FUEL FLOW METER.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0006-001_FUEL FLOW METER |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 304 | 522803-01-RFAM-FP-0004-001_Fire Pump and Jockey pump with controller | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 1:02 PM | Dec 14, 2023 11:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0004-001_Fire Pump and Jockey pump with controller.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0004-001_Fire Pump and Jockey pump with controller |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 303 | 522803-01-MS-HY-0002-001_NON-METALLIC PIPES Connection | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 12:42 PM | Dec 18, 2023 9:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-HY-0002-001_NON-METALLIC PIPES Connection.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0002-001_NON-METALLIC PIPES Connection |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 302 | 522803-01-MS-HY-0001-001_PIPE UNDERGROUND WORK (HDPE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 12:37 PM | Dec 18, 2023 9:46 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-HY-0001-001_PIPE UNDERGROUND WORK (HDPE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1048_MS-HY_Request for Approval Method Statement (Hydraulics Plumbing Sanitary Fuel)/522803-01-MS-HY-0001-001_PIPE UNDERGROUND WORK (HDPE) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 301 | 522803-01-MS-FP-0001-001_UG PIPE WORK (HDPE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 12:22 PM | Dec 18, 2023 10:05 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-FP-0001-001_UG PIPE WORK (HDPE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1049_MS-FP_Request for Approval Method Statement (Fire Protection)/522803-01-MS-FP-0001-001_UG PIPE WORK (HDPE) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 298 | 522803-01-RFAM-ST-0007-005_Leed document for SSS factory | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 11:36 AM | Dec 7, 2023 11:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0007-005_Leed document for SSS factory.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0007-005_Leed document for SSS factory |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 296 | 522803-01-RFAM-CV-0004-001_Cover for retention tank | (TTI) Request for Approval (AUR_Civil Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 10:47 AM | Dec 9, 2023 11:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0004-001_Cover for retention tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0004-001_Cover for retention tank |  | V1 | 0 | Approved | Updated review status
CLOSED | 292 | 522803-01-RFAM-ST-0003-004_ORC ready mix concrete_SIKA crystalline | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 9:50 AM | Dec 7, 2023 11:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0003-004_ORC ready mix concrete_SIKA crystalline.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0003-004_ORC ready mix concrete_SIKA crystalline |  | V1 | 0 | Approved | Updated review status
CLOSED | 291 | 522803-01-RFAM-ST-018 Sub-con for chemical rebar or bolt | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Dec 4, 2023 9:39 AM | Dec 7, 2023 12:03 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0018-001_Sub-con for chemical rebar or bolt.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0018-001_ Sub-con for chemical rebar or bolt |  | V1 | 0 | Approved | Updated review status
CLOSED | 285 | 522803-01-RFAM-EL-0019-001_Cable Termination Kit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 2, 2023 9:49 AM | Dec 13, 2023 2:56 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0019-001_Cable Termination Kit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0019-001_Cable Termination Kit |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 284 | 522803-01-RFAM-EL-0016-001_Cable Cleats | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 2, 2023 9:48 AM | Dec 13, 2023 3:02 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0016-001_Cable Cleats.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0016-001_Cable Cleats |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 283 | 522803-01-RFAM-EL-0025-001_Power Metering | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 5:03 PM | Dec 29, 2023 2:43 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0025-001_Power Metering.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0025-001_Power Metering |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 29, 2023 2:42 AM): please clarify all deviated item
CLOSED | 282 | 522803-01-RFAM-EL-0026-001_LV Circuit Breaker | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 4:32 PM | Dec 19, 2023 6:08 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0026-001_LV Circuit Breaker.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0026-001_LV Circuit Breaker |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 19, 2023 6:08 PM): please recheck with AUR comment
CLOSED | 281 | 522803-01-RFAM-EL-0011-001_Raceway | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 4:14 PM | Dec 13, 2023 3:13 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0011-001_Raceway.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0011-001_Raceway |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 280 | 522803-01-RFAM-EL-0029-001_Fire alarm system | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 4:07 PM | Dec 25, 2023 10:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0029-001_Fire alarm system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0029-001_Fire alarm system |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 279 | 522803-01-RFAM-HY-0001-002 HDPE Pipe | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 3:52 PM | Dec 19, 2023 12:06 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0001-002 HDPE Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0001-002 HDPE Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 278 | 522803-01-RFAM-FP-0001-002_HDPE Pipe | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 3:44 PM | Dec 8, 2023 6:14 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0001-002_HDPE Pipe.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0001-002_HDPE Pipe |  | V1 | 0 | Approved | Updated review status
CLOSED | 277 | 522803-01-RFAM-EL-0018-001_Shield Twisted Pair Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 3:34 PM | Dec 14, 2023 9:10 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0018-001_Shield Twisted Pair Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0018-001_Shield Twisted Pair Cable |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 276 | 522803-01-RFAM-EL-0022-001_Surge protection device | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 3:27 PM | Dec 25, 2023 10:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0022-001_Surge protection device.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0022-001_Surge protection device |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 275 | 522803-01-RFAM-EL-0023-001_Transfer Switch | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Dec 1, 2023 3:10 PM | Dec 24, 2023 5:01 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0023-001_Transfer Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0023-001_Transfer Switch |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 24, 2023 5:00 PM): Please recheck the function of ATS - withdraw type - Neutral delay if use transfer switch type please check it require ACB for protection or not
CLOSED | 265 | 522803-01-ITP-CSA-0001-002_CSA Project Quality plan (ITP Plan) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | Nuttharoj Thosok | -- | -- | Nov 28, 2023 9:35 AM | Dec 18, 2023 9:05 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-ITP-CSA-0001-002_CSA Project Quality plan (ITP Plan).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-CSA-0001-002_CSA Project Quality plan (ITP Plan) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 260 | 522803-01-RFAM-ST-0012-002_RFA_Siam city_s ready mix concrete_Change crystalline to SIKA brand | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 24, 2023 11:43 AM | Nov 28, 2023 9:57 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0012-002_RFA_Siam city_s ready mix concrete_Change crystalline to SIKA brand.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0012-002_RFA_Siam city_s ready mix concrete_Change crystalline to SIKA brand |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 259 | 522803-01-RFAM-ST-0006-005_Q Concrete_s ready mix concrete_Change to SIKA crystalline | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 24, 2023 11:34 AM | Nov 28, 2023 9:54 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0006-005_Q Concrete_s ready mix concrete_Change to SIKA crystalline.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0006-005_Q Concrete_s ready mix concrete_Change to SIKA crystalline |  | V1 | 0 | Approved | Updated review status
CLOSED | 258 | 522803-01-RFA-HSE-0007-001_Legal list for safety control at NEXT 01 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 24, 2023 11:25 AM | Dec 9, 2023 11:36 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0007-001_Legal list for safety control at NEXT 01.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0007-001_Legal list for safety control at NEXT 01 |  | V1 | 0 | Approved | Updated review status
CLOSED | 257 | 522803-01-RFAM-EL-0002-002_HDPE CONDUIT UNDERGROUND (COMMU. INCOMING) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 24, 2023 9:49 AM | Dec 13, 2023 4:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0002-002_HDPE CONDUIT UNDERGROUND (COMMU. INCOMING).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0002-002_HDPE CONDUIT UNDERGROUND (COMMU. INCOMING) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 256 | 522803-01-RFAM-EL-0012-001_HDPE CONDUIT (ELECTRICAL) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 24, 2023 9:37 AM | Dec 13, 2023 4:46 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0012-001_HDPE CONDUIT (ELECTRICAL).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0012-001_HDPE CONDUIT (ELECTRICAL) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 255 | 522803-01-RFAM-EL-0015-001_Lightning Arrester | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 23, 2023 11:48 AM | Dec 25, 2023 10:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0015-001_Lightning Arrester.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0015-001_Lightning Arrester |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Dec 25, 2023 10:22 AM): please follow AUR comment
CLOSED | 254 | 522803-01-RFAM-EL-0014-001_Load Break Switch | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 23, 2023 11:46 AM | Dec 18, 2023 4:58 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0014-001_Load Break Switch.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0014-001_Load Break Switch |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 18, 2023 4:57 PM): please resubmit with AUR comment
CLOSED | 253 | 522803-01-RFAM-EL-0013-001_Cable Basket Tray | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 23, 2023 11:10 AM | Dec 25, 2023 10:19 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0013-001_Cable Basket Tray.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0013-001_Cable Basket Tray |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Dec 25, 2023 10:16 AM): Jedsada : please propose correct high on tray Height shall be 105mm. but in data sheet high 55mm.
CLOSED | 250 | 522803-01-RFAM-EL-0009-001_Medium Voltage Cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 23, 2023 10:01 AM | Dec 14, 2023 1:44 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0009-001_Medium Voltage Cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0009-001_Medium Voltage Cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 242 | 522803-01-RFI-HY-0005-001_Floor depressed layout changed at Chiller plant, Pump Room and Garage | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Nov 22, 2023 3:57 PM | Dec 12, 2023 9:51 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFI-HY-0005-001_Floor depressed layout changed at Chiller plant, Pump Room and Garage.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1248_RFI-HY_Request for Information (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFI-HY-0005-001_Floor depressed layout changed at Chiller plant, Pump Room and Garage |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 241 | 522803-01-RFAM-EL-0008-001_MCT (Multi Core Transit) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 22, 2023 3:17 PM | Dec 25, 2023 9:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0008-001_MCT (Multi Core Transit).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0008-001_MCT (Multi Core Transit) |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Dec 14, 2023 4:15 PM): Jedsada : Please consider fire compartment at the room has contain the MCT for example if MCT install in fire compartment room fire rated 2 hours the MCT should fire rated 2 Hours as well GSA CLIENT(Dec 25, 2023 9:34 AM): Please refer. EIT standard as attached
CLOSED | 237 | 522803-01-RFAM-HY-0005-001_Underground fuel tank | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Nov 22, 2023 10:10 AM | Dec 8, 2023 5:38 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0005-001_Underground fuel tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0005-001_Underground fuel tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 236 | 522803-01-MS-EL-0002-001_UG MH of MV and COM Installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 22, 2023 9:48 AM | Dec 29, 2023 3:02 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-EL-0002-001_UG MH of MV and COM Installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0002-001_UG MH of MV and COM Installation |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 234 | 522803-01-RFAS-EL-0002-001_DETAIL OF MANHOLE (MV and COMMU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 21, 2023 11:03 AM | Dec 14, 2023 8:44 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0002-001_CAD_Detail of manhole type A3-1 and type MH.C1 _ MH.C2 _16-11-2023.rar | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-001_DETAIL OF MANHOLE (MV and COMMU) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 234 | 522803-01-RFAS-EL-0002-001_DETAIL OF MANHOLE (MV and COMMU) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 21, 2023 11:03 AM | Dec 14, 2023 8:44 AM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0002-001_DETAIL OF MANHOLE (MV and COMMU).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0002-001_DETAIL OF MANHOLE (MV and COMMU) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 232 | 522803-01-RFA-LE-0001-001_ESC Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 21, 2023 9:09 AM | Dec 9, 2023 11:35 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-LE-0001-001_ESC Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0001-001_ESC Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 231 | 522803-01-RFAM-HY-0004-001_Packaged WWTP | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Nov 20, 2023 7:12 PM | Dec 8, 2023 4:09 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0004-001_Packaged WWTP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0004-001_Packaged WWTP |  | V1 | 0 | Approved | Updated review status
CLOSED | 230 | 522803-01-RFA-LE-0002-001_Waste Management Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 20, 2023 9:35 AM | Dec 9, 2023 11:38 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-LE-0002-001_Waste Management Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1035_RFA-LE_Request for Approval (LEED)/522803-01-RFA-LE-0002-001_Waste Management Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 229 | 522803-01-RFA-HSE-0003-001_Certificate equipment lifting hook | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 20, 2023 9:21 AM | Nov 23, 2023 9:39 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0003-001_Certificate equipment lifting hook.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0003-001_Certificate equipment lifting hook |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 227 | 522803-01-RFA-HSE-0004-001_SAFETY REWARD AND SAFETY CAMPAIGN | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 19, 2023 4:57 PM | Nov 23, 2023 9:41 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0004-001_SAFETY REWARD AND SAFETY CAMPAIGN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0004-001_SAFETY REWARD AND SAFETY CAMPAIGN |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 225 | 522803-01-RFAM-ST-0016-001_PC panel | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 17, 2023 3:38 PM | Nov 21, 2023 2:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0016-001_PC panel.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0016-001_PC panel |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 224 | 522803-01-ORG-HSE-0001-002_Safety Committee | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 17, 2023 1:17 PM | Nov 23, 2023 9:08 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-ORG-HSE-0001-002_Safety Committee.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1006_ORG-XXX_Request for Approval Organisation (For all types of Discipline)/522803-01-ORG-HSE-0001-002_Safety Committee |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 220 | 522803-01-RFAM-ST-0015-001_Postension slab | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 3:01 PM | Nov 21, 2023 8:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0015-001_Postension slab.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0015-001_Postension slab |  | V1 | 0 | Approved | Updated review status
CLOSED | 219 | 522803-01-RFAS-ST-0002-003_Structure Water tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 1:36 PM | Nov 24, 2023 12:35 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0002-003_Structure Water tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0002-003_Structure Water tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 219 | 522803-01-RFAS-ST-0002-003_Structure Water tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 1:36 PM | Nov 24, 2023 12:35 PM | 2 | 2 | 0 | 100% | Review closed | 4 | TTI_V23_NEXT-01_DC1 BUILDING _SHOP_STR WATER TANK 20231115.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0002-003_Structure Water tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 218 | 522803-01-RFAS-ST-0001-004_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 1:30 PM | Nov 24, 2023 12:32 PM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-004_Structure Foundation Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-004_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 218 | 522803-01-RFAS-ST-0001-004_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 1:30 PM | Nov 24, 2023 12:32 PM | 2 | 2 | 0 | 100% | Review closed | 4 | TTI_V23_NEXT-01_DC1 BUILDING _SHOP_STR FOUNDATION 20231115.nwc | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-004_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 217 | 522803-01-RFAM-ST-0014-001_Sika 614T | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 15, 2023 9:48 AM | Nov 17, 2023 9:24 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0014-001_Sika 614T.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0014-001_Sika 614T |  | V1 | 0 | Approved | Updated review status
CLOSED | 215 | 522803-01-MS-CSA-0004-001_Method statement of foundation deep zone | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 14, 2023 3:21 PM | Nov 29, 2023 8:48 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0004-001_Method statement of foundation deep zone.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0004-001_Method statement of foundation deep zone |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 214 | 522803-01-RFA-MEP-0001-002_MEP_Application schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 14, 2023 11:17 AM | Nov 29, 2023 8:59 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-MEP-0001-002_MEP_Application schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1021_RFA-XXX_Request for Approval (For exceptional types of discipline)/522803-01-RFA-MEP-0001-002_MEP_Application schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 213 | 522803-01-RFAM-EL-0004-002_MANHOLE ACCESSORIES & HARDWARE (INCOMING) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 14, 2023 11:02 AM | Dec 9, 2023 11:43 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0004-002_MANHOLE ACCESSORIES & HARDWARE (INCOMING).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0004-002_MANHOLE ACCESSORIES & HARDWARE (INCOMING) |  | V1 | 0 | Approved | Updated review status
CLOSED | 210 | 522803-01-ITP-MEP-0001-001_MEP INSPECTION_TEST PLAN | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 13, 2023 4:37 PM | Nov 23, 2023 9:21 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ITP-MEP-0001-001_MEP INSPECTION_TEST PLAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-MEP-0001-001_MEP INSPECTION_TEST PLAN |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 207 | 522803-01-RFAM-ST-0009-002_B.bond epoxy for Chemical bolt & rebar_Hilti RE500 V3 | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 13, 2023 9:29 AM | Nov 15, 2023 8:22 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0009-002_B.bond epoxy for Chemical bolt & rebar_Hilti RE500 V3.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0009-002_B.bond epoxy for Chemical bolt & rebar_Hilti RE500 V3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 206 | 522803-01-RFAM-EL-0010-001_Fire resistance cable | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 13, 2023 8:46 AM | Dec 9, 2023 11:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0010-001_Fire resistance cable.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0010-001_Fire resistance cable |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 205 | 522803-01-RFAS-ST-0003-003_PAVEMENT PILING PLAN ALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 10, 2023 3:58 PM | Nov 21, 2023 1:16 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-003_PAVEMENT PILING PLAN ALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-003_PAVEMENT PILING PLAN ALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 203 | 522803-01-RFAM-MEP-0002-002_MEP Equipment list and schedule_Cx | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 9, 2023 2:53 PM | Nov 23, 2023 9:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-MEP-0002-002_MEP Equipment list and schedule_Cx.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0002-002_MEP Equipment list and schedule_Cx |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 202 | 522803-01-RFAM-MEP-0001-002_MEP Equipment list and schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 9, 2023 2:47 PM | Dec 14, 2023 12:35 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-MEP-0001-002_MEP Equipment list and schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0001-002_MEP Equipment list and schedule |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Dec 14, 2023 12:35 PM): please revise as AUR comment
CLOSED | 193 | 522803-01-RFA-HSE-0002-001_Regulation for labor camp for information | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 8, 2023 1:01 PM | Nov 20, 2023 7:04 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0002-001_Regulation for labor camp for information.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0002-001_Regulation for labor camp for information |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 192 | 522803-01-RFAM-ST-0013-001_Sika grout -212 GP | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 8, 2023 10:59 AM | Nov 10, 2023 11:30 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0013-001_Sika grout -212 GP.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0013-001_Sika grout -212 GP |  | V1 | 0 | Approved | Updated review status
CLOSED | 191 | 522803-01-MS-CSA-0002-002_Method statement and safety procedure to Tower crane installation_Additional | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 8, 2023 10:23 AM | Nov 23, 2023 9:14 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0002-002_Method statement and safety procedure to Tower crane installation_Additional.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0002-002_Method statement and safety procedure to Tower crane installation_Additional |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 190 | 522803-01-ITP-HSE-0001-001_Environmental workplace monitoring plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 8, 2023 8:55 AM | Nov 10, 2023 7:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-ITP-HSE-0001-001_Environmental workplace monitoring plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-HSE-0001-001_Environmental workplace monitoring plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 188 | 522803-01-RFAM-EL-0007-001_Earthing and Lightning system | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 7, 2023 11:25 AM | Dec 9, 2023 11:49 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0007-001_Earthing and Lightning system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0007-001_Earthing and Lightning system |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 187 | 522803-01-RFAM-EL-0006-001_uPVC Conduit | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 7, 2023 11:17 AM | Dec 9, 2023 11:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0006-001_uPVC Conduit.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0006-001_uPVC Conduit |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 182 | 522803-01-RFAM-ST-0004-004_Namheng_s ready mix concrete (Revise mix concrete which fly ash over 25%) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 7, 2023 9:18 AM | Nov 9, 2023 1:47 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0004-004_Namheng_s ready mix concrete (Revise mix concrete which fly ash over 25%).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0004-004_Namheng_s ready mix concrete (Revise mix concrete which fly ash over 25%) |  | V1 | 0 | Approved | Updated review status
CLOSED | 181 | 522803-01-RFAM-ST-0007-004_Rebar_Leed Document | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 7, 2023 9:04 AM | Nov 9, 2023 2:01 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0007-004_Rebar_Leed Document.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0007-004_Rebar_Leed Document |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 180 | 522803-01-RFAM-EL-0005-002_READY MIXED CONCRET (DUCTBANK & MANHOLE | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 6, 2023 3:47 PM | Nov 10, 2023 8:18 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0005-002_READY MIXED CONCRET (DUCTBANK & MANHOLE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0005-002_READY MIXED CONCRET (DUCTBANK & MANHOLE) |  | V1 | 0 | Approved | Updated review status
CLOSED | 177 | 522803-01-RFAS-EL-0001-001_ELECTRICAL SERVICES MV & COMS ROTING LAYOUT (UNDERGROUND) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Nov 3, 2023 3:26 PM | Dec 28, 2023 10:35 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-EL-0001-001_ELECTRICAL SERVICES MV & COMS ROTING LAYOUT (UNDERGROUND).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1150_RFAS-EL_Request for Approval Shop Drawings (Electrical)/522803-01-RFAS-EL-0001-001_ELECTRICAL SERVICES MV & COMS ROTING LAYOUT (UNDERGROUND) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 175 | 522803-01-RFAM-CV-0002-002_PC pile_Clearify deviation of water from mix design | (TTI) Request for Approval (AUR_Civil Team Review) - Main Contractor | nittaya p | -- | -- | Nov 3, 2023 11:06 AM | Nov 10, 2023 11:08 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0002-002_PC pile_Clearify deviation of water from mix design.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0002-002_PC pile_Clearify deviation of water from mix design |  | V1 | 0 | Approved | Updated review status
CLOSED | 174 | 522803-01-RFAM-ST-0010-002_CPAC_s ready mix concrete (Revise mix which fly ash over 25%) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 3, 2023 9:14 AM | Nov 9, 2023 2:07 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0010-002_CPAC_s ready mix concrete (Revise mix which fly ash over 25%).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0010-002_CPAC_s ready mix concrete (Revise mix which fly ash over 25%) |  | V1 | 0 | Approved | Updated review status
CLOSED | 172 | 522803-01-RFAM-EL-0005-001_READY MIXED CONCRET (DUCTBANK & MANHOLE) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 2, 2023 9:40 AM | Nov 6, 2023 1:58 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0005-001_READY MIXED CONCRET (DUCTBANK & MANHOLE).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0005-001_READY MIXED CONCRET (DUCTBANK & MANHOLE) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Nov 6, 2023 1:57 PM): Please follow MEA's spec as minimum
CLOSED | 170 | 522803-01-RFAM-HY-0003-001_Valve for cold water and drainage system | (TTI) Request for Approval (AUR_Hydraulics Team Review) - Main Contractor | nittaya p | -- | -- | Nov 1, 2023 3:47 PM | Nov 6, 2023 4:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0003-001_Valve for cold water and drainage system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0003-001_Valve for cold water and drainage system |  | V1 | 0 | Approved | Updated review status
CLOSED | 169 | 522803-01-RFAS-ST-0001-003_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 1, 2023 2:11 PM | Nov 8, 2023 3:27 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-003_Structure Foundation Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-003_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 168 | 522803-01-RFAM-ST-0006-004_Q Concrete_s ready mix concrete_(Revise mix which fly ash over 25%) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 1, 2023 2:02 PM | Nov 6, 2023 11:08 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0006-004_Q Concrete_s ready mix concrete_(Revise mix which fly ash over 25%).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0006-004_Q Concrete_s ready mix concrete_(Revise mix which fly ash over 25%) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 167 | 522803-01-RFAM-ST-0003-003_ORC_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Nov 1, 2023 9:48 AM | Nov 6, 2023 10:24 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0003-003_ORC_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0003-003_ORC_s ready mix concrete |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 166 | 522803-01-RFAS-CSA-0002-002_CSA Shop Drawing List and schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Nov 1, 2023 9:32 AM | Nov 15, 2023 8:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CSA-0002-002_CSA Shop Drawing List and schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1143_RFAS-CSA_Request for Approval Shop Drawings (Civil Structural Architectural)/522803-01-RFAS-CSA-0002-002_CSA Shop Drawing List and schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 165 | 522803-01-RFAM-EL-0004-001_MANHOLE ACCESSORIES & HARDWARE (INCOMING) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Oct 31, 2023 7:30 PM | Nov 13, 2023 4:18 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0004-001_MANHOLE ACCESSORIES & HARDWARE (INCOMING).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0004-001_MANHOLE ACCESSORIES & HARDWARE (INCOMING) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 164 | 522803-01-RFAM-ST-0007-003_Rebar | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 31, 2023 1:32 PM | Nov 6, 2023 9:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0007-003_Rebar.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0007-003_Rebar |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 162 | 522803-01-RFAM-FP-0002-001_Valve for Fire Protection system | (TTI) Request for Approval (AUR_Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Oct 30, 2023 6:20 PM | Nov 6, 2023 3:56 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0002-001_Valve for Fire Protection system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0002-001_Valve for Fire Protection system |  | V1 | 0 | Approved | Updated review status
CLOSED | 160 | 522803-01-RFAS-ST-0002-002_Structure Water tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 28, 2023 1:25 PM | Nov 6, 2023 12:50 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0002-002_Structure Water tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0002-002_Structure Water tank |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 159 | 522803-01-MS-EL-0001-001_MS to Underground duct bank of medium voltage and communication installation work | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 27, 2023 5:16 PM | Nov 29, 2023 8:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-EL-0001-001_MS to Underground duct bank of medium voltage and communication installation work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1050_MS-EL_Request for Approval Method Statement (Electrical)/522803-01-MS-EL-0001-001_MS to Underground duct bank of medium voltage and communication installation work |  | V2 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 155 | 522803-01-RFAM-EL-0003-001_MH Cover | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Oct 27, 2023 10:53 AM | Nov 13, 2023 10:38 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0003-001_MH Cover.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0003-001_MH Cover |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 154 | 522803-01-MRPT-GEN-0001_001_Monthly Report No.01_Oct-2023 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 27, 2023 10:42 AM | Nov 10, 2023 7:47 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MRPT-GEN-0001_001_Monthly Report No.01_Oct-2023.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1440_MRPT-GEN_Monthly Report (General)/522803-01-MRPT-GEN-0001_001_TTI Monthly Construction Report No.01_October 2023 |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 153 | 522803-01-RFAM-ST-0011-001 Curing compound | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 27, 2023 10:25 AM | Nov 1, 2023 2:10 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0011-001 Curing compound.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0011-001 Curing compound |  | V1 | 0 | Approved | Updated review status
CLOSED | 151 | 522803-01-RFAM-EL-0002-001_HDPE | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Oct 27, 2023 8:47 AM | Nov 13, 2023 3:00 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0002-001_HDPE.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0002-001_HDPE |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 150 | 522803-01-MS-CSA-0003-001_Method Statement and Procedure of pile cutting | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 26, 2023 3:46 PM | Nov 1, 2023 9:56 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0003-001_Method Statement and Procedure of pile cutting.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0003-001_Method Statement and Procedure of pile cutting |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 148 | 522803-01-RFAM-ST-0012-001_Siam city_s ready mix concrete_Additional | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 26, 2023 3:27 PM | Nov 2, 2023 8:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0012-001_Siam city_s ready mix concrete_Additional.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0012-001_Siam city_s ready mix concrete (Additional) |  | V1 | 0 | Approved | Updated review status
CLOSED | 145 | 522803-01-RFAM-ST-0010-001_CPAC_s ready mix concrete (Additional) | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 26, 2023 8:08 AM | Nov 2, 2023 8:59 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0010-001_CPAC_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0010-001_CPAC_s ready mix concrete (Additional) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 144 | 522803-01-RFAS-ST-0003-001_PAVEMENT PILING PLAN ALL | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 7:17 PM | Nov 6, 2023 9:37 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0003-001_PAVEMENT PILING PLAN ALL.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0003-001_PAVEMENT PILING PLAN ALL |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 143 | 522803-01-RFAM-ST-0009-001_B.bond epoxy for Chemical bolt & rebar | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 2:27 PM | Oct 27, 2023 4:05 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0009-001_B.bond epoxy for Chemical bolt & rebar.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0009-001_B.bond epoxy for Chemical bolt & rebar |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 142 | 522803-01-RFAM-EL-0001-001_CATALOGUE for RTRC CONDUIT UNDERGROUND (MV. INCOMING) | (TTI) Request for Approval (AUR_Electrical Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 11:12 AM | Nov 13, 2023 9:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-EL-0001-001_CATALOGUE for RTRC CONDUIT UNDERGROUND (MV. INCOMING).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1170_RFAM-EL_Request for Approval Material (Electrical)/522803-01-RFAM-EL-0001-001_CATALOGUE for RTRC CONDUIT UNDERGROUND (MV. INCOMING) |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 141 | 522803-01-RPT-GEN-0003-001_Survey Report of Neighbors_School | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 9:57 AM | Oct 31, 2023 3:37 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-GEN-0003-001_Survey Report of Neighbors_School.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1460_RPT-GEN_Request for Approval Report (General)/522803-01-RPT-GEN-0003-001_Survey Report of Neighbors_School |  | V1 | 0 | Approved | Updated review status
CLOSED | 140 | 522803-01-RPT-GEN-0002-001_Survey Report of Neighbors_Thai Watsadu | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 9:56 AM | Oct 31, 2023 3:34 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-GEN-0002-001_Survey Report of Neighbors_Thai Watsadu.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1460_RPT-GEN_Request for Approval Report (General)/522803-01-RPT-GEN-0002-001_Survey Report of Neighbors_Thai Watsadu |  | V1 | 0 | Approved | Updated review status
CLOSED | 139 | 522803-01-MS-CSA-0002-001_Method statement and safety procedure to Tower crane installation | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 25, 2023 8:55 AM | Nov 1, 2023 9:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-CSA-0002-001_Method statement and safety procedure to Tower crane installation.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0002-001_Method statement and safety procedure to Tower crane installation |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 138 | 522803-01-RFAM-ST-0007-002_Rebar | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 24, 2023 5:12 PM | Oct 26, 2023 9:37 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0007-002_Rebar.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0007-002_Rebar |  | V1 | 0 | Approved | Updated review status
CLOSED | 137 | 522803-01-RFAS-ST-0001-002_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 24, 2023 1:32 PM | Oct 30, 2023 7:55 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-002_Structure Foundation Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-002_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 135 | 522803-01-RFA-MEP-0001-001_MEP_Application schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 19, 2023 4:54 PM | Nov 1, 2023 10:03 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFA-MEP-0001-001_MEP_Application schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1021_RFA-XXX_Request for Approval (For exceptional types of discipline)/522803-01-RFA-MEP-0001-001_MEP_Application schedule |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 134 | 522803-01-RFAM-CV-0003-001_Spun Pile | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 19, 2023 11:27 AM | Nov 3, 2023 9:58 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0003-001_Spun Pile.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0003-001_Spun Pile |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 133 | 522803-01-RFAM-ST-0005-002_M Concrete s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 19, 2023 9:37 AM | Oct 24, 2023 11:33 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0005-002_M Concrete s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0005-002_M Concrete s ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 132 | 522803-01-RFAM-ST-0003-002_ORC_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 17, 2023 10:06 PM | Oct 24, 2023 11:37 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0003-002_ORC_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0003-002_ORC_s ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 131 | 522803-01-RFAM-HY-0002-001_CATALOGUE for CLEAN OUT, FLOOR CLEAN OUT AND FLOOR DRAIN | (TTI) Request for Approval (AUR_Hydraulics and Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Oct 17, 2023 7:11 PM | Oct 27, 2023 4:49 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0002-001_CATALOGUE for CLEAN OUT, FLOOR CLEAN OUT AND FLOOR DRAIN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0002-001_CATALOGUE for CLEAN OUT, FLOOR CLEAN OUT AND FLOOR DRAIN |  | V1 | 0 | Approved | Updated review status
CLOSED | 129 | 522803-01-RFAM-FP-0001-01_CATALOGUE for HDPE Pipe of Fire Protection system | (TTI) Request for Approval (AUR_Hydraulics and Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Oct 17, 2023 6:04 PM | Oct 27, 2023 4:36 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-FP-0001-001_CATALOGUE for HDPE Pipe of Fire Protection system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1169_RFAM-FP_Request for Approval Material (Fire Protection)/522803-01-RFAM-FP-0001-001_CATALOGUE for HDPE Pipe of Fire Protection system |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 128 | 22803-01-RFAM-HY-0001-001_CATALOGUE for HDPE Pipe of Hydraulics system | (TTI) Request for Approval (AUR_Hydraulics and Fire Protection Team Review) - Main Contractor | nittaya p | -- | -- | Oct 17, 2023 4:21 PM | Oct 27, 2023 4:42 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-HY-0001-001_CATALOGUE for HDPE Pipe of Hydraulics system.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1168_RFAM-HY_Request for Approval Material (Hydraulics Plumbing Sanitary Fuel)/522803-01-RFAM-HY-0001-001_CATALOGUE for HDPE Pipe of Hydraulics system |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 127 | 522803-01-ITP-CSA-0001-001_CSA Project Quality plan (ITP Plan) | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 14, 2023 4:31 PM | Nov 1, 2023 9:49 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ITP-CSA-0001-001_CSA Project Quality plan (ITP Plan).pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1009_ITP-XXX_Request for Approval Inspection Test Plan (For all types of Discipline)/522803-01-ITP-CSA-0001-001_CSA Project Quality plan (ITP Plan) |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 126 | 522803-01-MS-ST-0002-001_Method Statement_JSA_to Piling work | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 14, 2023 11:01 AM | Oct 20, 2023 7:44 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0002-001_Method Statement_JSA_to Piling work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0002-001_Method Statement_JSA_to Piling work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 125 | 522803-01-RFA-HSE-0001-001_HSE Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 7:52 PM | Oct 17, 2023 9:04 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-HSE-0001-001_HSE Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1022_RFA-HSE_Request for Approval (Health Safety Environment)/522803-01-RFA-HSE-0001-001_HSE Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 124 | 522803-01-ORG-HSE-0001-001_Safety Committee | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 7:47 PM | Oct 19, 2023 9:05 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-ORG-HSE-0001-001_Safety Committee.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1006_ORG-XXX_Request for Approval Organisation (For all types of Discipline)/522803-01-ORG-HSE-0001-001_Safety Committee |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 123 | 522803-01-RFAM-CV-0002-001_PC pile company_PC pile material | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 2:24 PM | Nov 2, 2023 11:17 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0002-001_PC pile company_PC pile material.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0002-001_PC pile company_PC pile material |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 122 | 522803-01-RFAM-ST-0004-003_Namheng_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 1:55 PM | Oct 18, 2023 8:28 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0004-003_Namheng_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0004-003_Namheng's ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 121 | 522803-01-RPT-GEN-0001-001_Notification of construction in the neighborhoods Report | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 9:25 AM | Oct 17, 2023 8:46 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RPT-GEN-0001-001_Notification of construction in the neighborhoods Report.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1460_RPT-GEN_Request for Approval Report (General)/522803-01-RPT-GEN-0001-001_Notification of construction in the neighborhoods Report |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 120 | 522803-01-RFAM-ST-0006-003_Q Concrete_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 13, 2023 9:17 AM | Oct 19, 2023 7:10 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0006-003_Q Concrete_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0006-003_Q Concrete_s ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 119 | 522803-01-RFAM-CV-0001-001_Tripod bore pile company | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 12, 2023 5:45 PM | Oct 19, 2023 7:31 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CV-0001-001_Tripod bore pile company.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1171_RFAM-CV_Request for Approval Material (Civil)/522803-01-RFAM-CV-0001-001_Tripod bore pile company |  | V1 | 0 | Approved | Updated review status
CLOSED | 117 | 522803-01-RFAM-ST-0001-002_CPAC_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 10, 2023 3:18 PM | Oct 14, 2023 1:38 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0001-002_CPAC_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0001-002_CPAC's ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 116 | 522803-01-ORG-MEP-0001-001_Cx Organization w CV | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 10, 2023 8:36 AM | Nov 3, 2023 1:32 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-ORG-MEP-0001-001_Cx Organization w CV.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1006_ORG-XXX_Request for Approval Organisation (For all types of Discipline)/522803-01-ORG-MEP-0001-001_Cx Organization chart and CV |  | V1 | 0 | Approved | Updated review status
CLOSED | 114 | 522803-01-RFAS-ST-0002-001_Structure Water tank | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 9, 2023 1:09 PM | Oct 15, 2023 10:43 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0002-001_Structure Water tank.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0002-001_Structure Water tank |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 113 | 522803-01-RFAM-MEP-0002-001_MEP Eqment list and schedule_Cx | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 9, 2023 1:07 PM | Oct 20, 2023 7:52 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-MEP-0002-001_MEP Eqment list and schedule_Cx.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0002-001_MEP Equipment list and schedule for submission_Cx |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Oct 17, 2023 7:05 PM): GSA comment at attached file, after revise the document Cx subject should be loop Sygna to involve this document
CLOSED | 111 | 522803-01-IMG-GEN-0001-001_Drone camera view for VDO Time lapse_60M_90M | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 8, 2023 6:21 PM | Oct 12, 2023 4:55 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-IMG-GEN-0001-001_Drone camera view for VDO Time lapse_60M_90M.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1012_IMG-XXX_Image (Photo and Video) (For all types of Discipline) [upload and email only]/522803-01-IMG-GEN-0001-001_Drone camera view for VDO Time lapse_60M_90M |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Oct 12, 2023 4:55 PM): Jedsada : Please check insurance expire date enough before use the drone Please follow the CAAT, NBTC regulation
CLOSED | 110 | 522803-01-RFA-GEN-0001-001_RFA_Site Tempo Plan | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 8, 2023 1:59 PM | Oct 17, 2023 8:51 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFA-GEN-0001-001_RFA_Site Tempo Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1020_RFA-GEN_Request for Approval (General)/522803-01-RFA-GEN-0001-001_RFA_Site Tempo Plan |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 109 | 522803-01-MS-ST-0001-002_Method Statement_JSA_Cer_to Soil Protection Work | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 8, 2023 10:09 AM | Oct 20, 2023 7:40 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-ST-0001-002_Method Statement_JSA_Cer_to Soil Protection Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0001-002_Method Statement_JSA_Cer_to Soil Protection Work |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 108 | 522803-01-RFAS-ST-0001-001_Structure Foundation Plan | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 8, 2023 9:38 AM | Oct 15, 2023 10:42 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-ST-0001-001_Structure Foundation Plan.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1146_RFAS-ST_Request for Approval Shop Drawings (Structure)/522803-01-RFAS-ST-0001-001_Structure Foundation Plan |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 107 | 522803-01-RFAM-ST-0006-002_Q Concrete_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 6, 2023 10:33 AM | Oct 10, 2023 2:35 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0006-002_Q Concrete_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0006-002_Q Concrete_s ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 106 | 522803-01-RFAM-ST-0002-002_Siam city_s ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 6, 2023 10:30 AM | Oct 10, 2023 1:33 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0002-002_Siam city_s ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0002-002_Siam city_s ready mix concrete |  | V1 | 0 | Approved | Updated review status
CLOSED | 103 | 522803-01-RFAM-ST-0008-001_Coupler_TITAN | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 5, 2023 1:36 PM | Oct 11, 2023 12:08 PM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0008-001_Coupler_TITAN.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0008-001_Coupler_TAITAN |  | V1 | 0 | Approved | Updated review status
CLOSED | 101 | 522803-01-RFAM-ST-0007-001_Rebar | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Oct 4, 2023 9:14 PM | Oct 11, 2023 10:12 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0007-001_Rebar.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0007-001_Rebar |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 100 | 522803-01-RFAS-GEN-0001-001_Plan Sheet pile and section | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 4, 2023 6:00 PM | Oct 9, 2023 9:10 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-GEN-0001-001_Plan Sheet pile and section.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1141_RFAS-XXX_Request for Approval Shop Drawings (For exceptional types of discipline)/522803-01-RFAS-GEN-0001-001_Plan Sheet pile and section |  | V2 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 98 | 522803-01-BIM-GEN-0001-001_BIM project Execution Plan Construction Phase_DRAFT | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 4, 2023 3:32 PM | Nov 1, 2023 9:37 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-BIM-GEN-0001-001_BIM project Execution Plan Construction Phase_DRAFT.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1008_BIM-GEN_Request for Approval BIM (General)/522803-01-BIM-GEN-0001-001_BIM project Execution Plan Construction Phase_Draft |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 96 | 522803-01-MS-CSA-0001-001_CSA Method statement submittal schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Oct 1, 2023 12:31 PM | Oct 12, 2023 8:36 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-MS-CSA-0001-001_CSA Method statement submittal schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1043_MS-CSA_Request for Approval Method Statement (Civil Structural Architectural)/522803-01-MS-CSA-0001-001_CSA Method statement submittal schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 95 | 522803-01-RFAM-CSA-0001-001_Material submittal schedule_30Sep23 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 30, 2023 7:59 PM | Oct 12, 2023 8:43 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-CSA-0001-001_Material submittal schedule_30Sep23.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1163_RFAM-CSA_Request for Approval Material (Civil Structural Architectural)/522803-01-RFAM-CSA-0001-001_Material submittal schedule_30Sep23 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 94 | 522803-01-RFAS-CSA-0002-001_CSA Shop Drawing List and schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 30, 2023 2:01 PM | Oct 12, 2023 8:39 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAS-CSA-0002-001_CSA Shop Drawing List and schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1143_RFAS-CSA_Request for Approval Shop Drawings (Civil Structural Architectural)/522803-01-RFAS-CSA-0002-001_CSA Shop Drawing List and schedule |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 92 | 522803-01-MS-MEP-0001-001_MEP MS & JSA Schedule R1 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 29, 2023 5:19 PM | Oct 12, 2023 4:25 PM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-MEP-0001-001_MEP MS & JSA Schedule R1.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1044_MS-MEP_Request for Approval Method Statement (Mechanical Electrical and Plumbing)/522803-01-MS-MEP-0001-001_MEP MS & JSA Schedule R1 |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Oct 9, 2023 2:49 PM): ๋้Jedsada: All activity must have create MS and JSA review before do working if we have some more activity TTI shall send document for approval again
CLOSED | 91 | 522803-01-RFAS-CSA-0001-001_FRAME A1 SHOP NEXT-01_R3 | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 29, 2023 11:09 AM | Oct 2, 2023 10:42 AM | 1 | 1 | 0 | 100% | Review closed | 4 | 522803-01-RFAS-CSA-0001-001_FRAME A1 SHOP NEXT-01_R3.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1143_RFAS-CSA_Request for Approval Shop Drawings (Civil Structural Architectural)/522803-01-RFAS-CSA-0001-001_FRAME A1 SHOP NEXT-01_R3 |  | V1 | 0 | Make correction as noted & proceed | Updated review status
CLOSED | 90 | 522803-01-RFAM-ST-0006-001_Q Concrete's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:29 AM | Oct 3, 2023 8:40 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0006-001_Q Concrete's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0006-001_Q Concrete's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | Nattawipa Pimpasalee(Sep 28, 2023 1:42 PM): The name file: should be entered "mix" after the word "Q" because it is the name of supplier Ex. 522803-01-RFAM-ST-0006-001_Q "mix" Concrete's ready mix concrete.
CLOSED | 89 | 522803-01-RFAM-ST-0005-001_M Concrete's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:28 AM | Oct 3, 2023 8:46 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0005-001_M Concrete's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0005-001_M Concrete's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 88 | 522803-01-RFAM-ST-0004-001_Namheng's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:27 AM | Oct 2, 2023 10:53 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0004-001_Namheng's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0004-001_Namheng's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 87 | 522803-01-RFAM-ST-0003-001_ORC's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:26 AM | Oct 2, 2023 10:51 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0003-001_ORC's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0003-001_ORC's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 86 | 522803-01-RFAM-ST-0002-001_Siam city's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:25 AM | Oct 2, 2023 10:49 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0002-001_Siam city's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0002-001_Siam city's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 85 | 522803-01-RFAM-ST-0001-001_CPAC's ready mix concrete | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 11:23 AM | Oct 2, 2023 10:45 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-RFAM-ST-0001-001_CPAC's ready mix concrete.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1166_RFAM-ST_Request for Approval Material (Structure)/522803-01-RFAM-ST-0001-001_CPAC's ready mix concrete |  | V1 | 0 | Make correction as noted & resubmit | Updated review status
CLOSED | 84 | 522803-01-RFAM-MEP-0001-001_MEP MAT Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 9:19 AM | Oct 10, 2023 9:04 AM | 2 | 2 | 0 | 100% | Review closed | 4 | 522803-01-RFAM-MEP-0001-001_MEP MAT Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0001-001_MEP MAT Schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Oct 10, 2023 9:02 AM): Jedsada K: Please revise all comment as AUR and GSA comment *This MEP list is can be adjustable and any document GSA can request more than in MEP List
CLOSED | 84 | 522803-01-RFAM-MEP-0001-001_MEP MAT Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 28, 2023 9:19 AM | Oct 10, 2023 9:04 AM | 2 | 2 | 0 | 100% | Review closed | 4 | '@20230924_MEP Material Schedule for submission.xlsx | Project Files/03_Construction Stage/02_Main Contractor TTI/1164_RFAM-MEP_Request for Approval Material (Mechanical Electrical and Plumbing)/522803-01-RFAM-MEP-0001-001_MEP MAT Schedule |  | V1 | 0 | Make correction as noted & proceed | Updated review status | GSA CLIENT(Oct 10, 2023 9:03 AM): Jedsada K: Please revise all comment as AUR and GSA comment *This MEP list is can be adjustable and any document GSA can request more than in MEP List
CLOSED | 82 | 522803-01-RFAS-MEP-0001-001_MEP SD Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 26, 2023 5:35 PM | Oct 9, 2023 2:28 PM | 2 | 0 | 2 | 100% | Review closed | 4 | 522803-01-RFAS-MEP-0001-001_MEP SD Schedule.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1144_RFAS-MEP_Request for Approval Shop Drawings (Mechanical Electrical and Plumbing)/522803-01-RFAS-MEP-0001-001_MEP SD Schedule |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Oct 9, 2023 2:27 PM): please revise as AUR comment
CLOSED | 82 | 522803-01-RFAS-MEP-0001-001_MEP SD Schedule | (TTI) Request for Approval (AUR PMCM_Site Team Review) - Main Contractor | nittaya p | -- | -- | Sep 26, 2023 5:35 PM | Oct 9, 2023 2:28 PM | 2 | 0 | 2 | 100% | Review closed | 4 | '@20230924_MEP Shop drawing schedule for submission.xlsx | Project Files/03_Construction Stage/02_Main Contractor TTI/1144_RFAS-MEP_Request for Approval Shop Drawings (Mechanical Electrical and Plumbing)/522803-01-RFAS-MEP-0001-001_MEP SD Schedule |  | V1 | 0 | Make correction as noted & resubmit | Updated review status | GSA CLIENT(Oct 9, 2023 2:28 PM): please revise as AUR comment
CLOSED | 80 | 522803-01-MS-ST-0001-001_Method Statement_JSA_Cer_to Soil Protection Work | (TTI) Request for Approval (AUR_Structure Team Review) - Main Contractor | nittaya p | -- | -- | Sep 25, 2023 12:18 PM | Oct 2, 2023 9:47 AM | 1 | 0 | 1 | 100% | Review closed | 4 | 522803-01-MS-ST-0001-001_Method Statement_JSA_Cer_to Soil Protection Work.pdf | Project Files/03_Construction Stage/02_Main Contractor TTI/1046_MS-ST_Request for Approval Method Statement (Structure)/522803-01-MS-ST-0001-001_Method Statement_JSA_Cer_to Soil Protection Work |  | V1 | 0 | Make correction as noted & resubmit | Updated review status